## CAPACITY (hidden)
BM | TM | STATO | Progetto | WO |  |  | 2022-01-03 |  |  | 2022-01-10 |  |  | 2022-01-17 |  |  | 2022-01-24 |  |  | 2022-01-31 |  |  | 2022-02-07 |  |  | 2022-02-14 |  |  | 2022-02-21 |  |  | 2022-02-28 |  |  | 2022-03-07 |  |  | 2022-03-14 |  |  | 2022-03-21 |  |  | 2022-03-28 |  |  | 2022-04-04 |  |  | 2022-04-11 |  |  | 2022-04-18 |  |  | 2022-04-25 |  |  | 2022-05-02 |  |  | 2022-05-09 |  |  | 2022-05-16 |  |  | 2022-05-23 |  |  | 2022-05-30 |  |  | 2022-06-06 |  |  | 2022-06-13 |  |  | 2022-06-20 |  |  | 2022-06-27 |  |  | 2022-07-04
| TM | STATO PRJ |  | WO |  |  | 2022-01-09 |  |  | 2022-01-16 |  |  | 2022-01-23 |  |  | 2022-01-30 |  |  | 2022-02-06 |  |  | 2022-02-13 |  |  | 2022-02-20 |  |  | 2022-02-27 |  |  | 2022-03-06 |  |  | 2022-03-13 |  |  | 2022-03-20 |  |  | 2022-03-27 |  |  | 2022-04-03 |  |  | 2022-04-10 |  |  | 2022-04-17 |  |  | 2022-04-24 |  |  | 2022-05-01 |  |  | 2022-05-08 |  |  | 2022-05-15 |  |  | 2022-05-22 |  |  | 2022-05-29 |  |  | 2022-06-05 |  |  | 2022-06-12 |  |  | 2022-06-19 |  |  | 2022-06-26 |  |  | 2022-07-03 |  |  | 2022-07-10
[5 empty] | DATA INIZIO | DATA FINE | s2 |  |  | s3 |  |  | s4 |  |  | s5 |  |  | s6 |  |  | s7 |  |  | s8 |  |  | s9 |  |  | s10 |  |  | s11 |  |  | s12 |  |  | s13 |  |  | s14 |  |  | s15 |  |  | s16 |  |  | s17 |  |  | s18 |  |  | s19 |  |  | s20 |  |  | s21 |  |  | s22 |  |  | s23 |  |  | s24 |  |  | s25 |  |  | s26 |  |  | s27 |  |  | s28
[7 empty] | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget | FTE allocati | FTE richiesti | FTE budget
FBZ | AMD | - | CJUnico - Rel 03/22 | ISP20211007617CJUnico_Maggio_2022 | 2022-01-03 | 2022-03-03 | 5 | 5 | 6 | 8 | 8 | 11 | 8 | 8 | 11 | 8 | 8 | 11 | 8 | 8 | 11 | 5 | 5 | 7 | 2 | 2 | 6 | 2 | 2 | 6 | 1.2 | 1.5 | 3 | 0 | 0 | 0
FBZ | AMD | - | Integr. Metaconto - RLO 03 | ISP20211111220CJUnico_RLO_Metaconto | 2022-01-03 | 2022-03-03 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3.5 | 5 | 3 | 3 | 5 | 3 | 4 | 5 | 3 | 4 | 3 | 3 | 4 | 0.5 | 3 | 3 | 0.5 | 1.8 | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
FBZ | AMD | + | CJ Financial Aggregator 03 | ISP20220307135Unico_RLO_Model_Change | 2022-01-03 | 2022-03-03 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 2.4 | 2 | 1.8 | 2 | 2 | 1.5
FBZ | EMT | + | CJ unico R5 Integration Palandrani | - | 2022-01-24 | 2022-05-17 | [9 empty] | 4 | 4 | 4 | 4 | 4 | 3.5 | 4 | 4 | 3.5 | 4 | 4 | 3.5 | 4 | 4.5 | 4 | 5 | 4.5 | 4 | 4.5 | 5 | 6 | 4.5 | 5 | 6 | 4.5 | 5 | 6 | 4.5 | 5 | 6 | 4.5 | 5 | 6 | 4.5 | 5 | 5 | 1.5 | 1 | 2 | 1.5 | 1.5 | 2
FBZ | AMD | + | CJUNICO Model Change 05/22 - Petrosino |  | 2022-01-26 | 2022-05-17 | [9 empty] | 2.4 | 2.5 | 2.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0.8 | 0.8 | 3 | 3 | 3.5 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 4 | 4 | 2 | 2 | 3 | 1 | 2 | 2
FBZ | AMD | + | CJ unico R5 Integration Metaconto - Cateno |  | 2022-01-26 | 2022-05-17 | [9 empty] | 2.4 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 3 | 3.5 | 3.5 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 2 | 2.8 | 2 | 2 | 1.5
FBZ | AMD | + | CJ Breve termine Puf | ISP2021092383CJBreveTermineR11_2021 | 2022-01-17 | 2022-03-27 | [6 empty] | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0.5 | 0.5 | 1 | 2 | 2 | 2.5 | 1 | 1 | 2 | 0 | 0 | 0
FBZ | AMD | - | Dialogo_Industriale_evo_03_22 | ISP2021102129EvolutiveDialogo + ISP2021080290IntegrazioneNCC (15 gg) | 2022-02-21 | 2022-03-04 | [15 empty] | 1 | 1.5 | 1.5 | 0 | 0 | 0 | 1 | 1.5 | 2 | 0.8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FBZ | EMT | + | ECA 5.9.1 release |  | 2022-03-17 | 2022-04-01 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  | 2 | 2 |  | 2 | 2 |  | 2 | 2
FBZ | EMT | + | ECA BIB AO impl |  | 2022-03-14 | 2022-04-12 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2 | 2 |  | 2 | 2 |  | 2 | 2 |  | 2 | 2 |  | 1.5 | 1.5
FBZ | EMT | + | CMT enforcement Wave2 |  | 2022-04-25 | 2022-06-03 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [21 empty] | 2 | 2 |  | 2 | 2
FBZ | AMD | + | CJ SME Unico w1 |  | 2021-05-09 | 2021-06-03
FBZ | AMD | + | CJ SME Unico w2 |  | 2021-06-06 | 2021-10-07
FBZ | PCR | + | WMT 2022 |  | 2021-03-23 | 2021-06-03
FBZ | PCR | + | PROATTIVO |  | 2021-06-06 | 2021-07-04
FBZ | CRT | + | PULSE PGR |  | 23/03/201 | 2021-07-22
Note on D12: Chiara DE RIGGI: - ODA 7200172731 per 29 ggu su Evolutive 2022 --> OFFERTA: ISP2021102129EvolutiveDialogo - Scaliamo 15 gg dal plafond (di fatto azzerandolo) --> riferimento ISP2021080290IntegrazioneNCC - Restano 6 gg da coprire con future RDA AFU OK

## Foglio1 (hidden)
TM | Progetto | DATA INIZIO | DATA FINE | FTE RICHIESTE | FTE ALLOCATE | DELTA | Note
MALACRIDA | Dialogo_Industriale | 2022-02-21 | 2022-03-04 | 3 | 3
| ECA BIB AO impl | 2022-04-12 | 2022-04-30 | 2 | 1 | 1 | Previsto pricco per Eca pro tra maggio giugno (Musciotto +1 FTE)
| CMT enforcement Wave2 | 2022-04-25 | 2022-06-03 | 2 | 2
| CMT enforcement Wave3 | 2022-07-18 | 2022-08-22 | 2 | 2
| ECA 5.9_LoanAdmin_phase2 | 2022-05-24 | 2022-07-01 | 1 | 1
| ECA 5.10.1 CR | 2022-06-27 | 2022-07-08 | 2 | 2
| CJ SME Unico w1 | 2022-05-09 | 2022-06-03 | 4 | 4
| CJ SME Unico w2 | 2022-06-06 | 2022-10-07 | 3 | 3
| Dialogo Industriale Agile | 2022-05-23 | 2022-07-01 | 1 | 1
| ISYB Delibera (01/09) | 2022-09-01 | 2022-12-31 | 3 | 1 | 2 | NH: 2 Tester
| ISYB FE (01/09) | 2022-09-15 | 2022-12-31 | 5 | 1 | 4 | Team: Di Giacomo: 4 Tester per Execution
| DP ISYB | 2022-07-01 | 2022-12-31 | 4 | 3 | 1
| DP RLO | 2022-07-01 | 2022-12-31 | 4 | 3 | 1
| CJ unico R7 | 2022-06-13 | 2022-07-08 | 7 | 7
| CJ unico R8 | 2022-09-01 | 2022-12-31 | 8 | 6 | 2
| TOTALE FTE |  |  | 51 | 40
CIRO | WMT 2022 | 2022-03-23 | 2022-07-22 | 5 | 5
| PROATTIVO | 2022-06-06 | 2022-07-04 | 2 | 2
| PULSE PGR | 2022-03-23 | 2022-07-22 | 2 | 1 | 1 | Non nel primo semestre, in attesa di Piano per PGR
| TOTALE FTE |  |  | 9 | 8
Note on G1: Chiara DE RIGGI: Delta rosso: esubero di FTE Delta Verde: richiesta di FTE
Note on B2: Chiara DE RIGGI: - ODA 7200172731 per 29 ggu su Evolutive 2022 --> OFFERTA: ISP2021102129EvolutiveDialogo - Scaliamo 15 gg dal plafond (di fatto azzerandolo) --> riferimento ISP2021080290IntegrazioneNCC - Restano 6 gg da coprire con future RDA AFU OK

## LifeCycle (hidden)
Data | 2023-06-24 | [13 empty] | #REF!
SAL
| 1 |  | 4 | 6 | 3 | 4 | 5 | 6 | 8 | 9 | 13 | 2 | 3 | 10 | [8 empty] | 21 | 21 | 11
| 3 |  | 3 | 3 | 11 | 11 | 11 | 11 | 3 | 3 | 3 | 3 | 3 | 3 | [8 empty] | 3 | 4 | 3
Nome Foglio | Progetti |  | Ambito | Release | Stime | Pian | GO | Offerta | Bucket | % Compl. | Stato | Responsabile | Richiedente | Prossima Milestone | G/U | BCWS | EV | ACWP | CPI | SPI | CV | SV | data inizio | data fine | Offerta | Giorni da stima | Residuo | REV_TAB
PULSE Skiptracing | #REF! | PULSE Skiptracing | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Credito Anomalo 2022 | #REF! | Credito Anomalo 2022 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Cessione NPL Calculation agent | #REF! | Cessione NPL Calculation agent | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CJ unico Maggio 2022 03 | #REF! | CJ unico Maggio 2022 03 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CJ unico R5 Integration Paland. | #REF! | CJ unico R5 Integration Paland. | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
CJ unico R5 Integration Cateno | CJ unico R5 Integration Cateno (metaconto) | CJ unico R5 Integration Cateno | - |  | SI | NO | SI | SI | Design | 100% | Coerente | Malacrida Alessandro | Maccarrone Cateno | 2022-01-10 | [8 empty] | 2022-01-24
CJ METACONTO RLO 03 | #REF! | CJ METACONTO RLO 03 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CJ F AGGREGATOR 22 03 | #REF! | CJ F AGGREGATOR 22 03 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
BRB 208 | #REF! | BRB 208 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
BRB 212 | #REF! | BRB 212 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CSOFF STRALCI FISC BRB 221 | #REF! | CSOFF STRALCI FISC BRB 221 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
BRB 222 | #REF! | BRB 222 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
BRB 223 ID 10 e P2 | #REF! | BRB 223 ID 10 e P2 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
BRB 226 Revisione bonis | #REF! | BRB 226 Revisione bonis | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
BRB 227 Delibere (2022) | BRB 227 Delibere | BRB 227 Delibere (2022) | - |  | SI | SI | SI | SI | Da Avviare | 89.84% | Coerente | Malacrida Alessandro | Dambra | TBD | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2022-04-05 | 2022-07-08 | - | 123 | #REF! | #REF!
PRESTITI PERSONALI - AI-SALES P | #REF! | PRESTITI PERSONALI - AI-SALES P | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PRESTITI PERSONALI - CQP Wave 2 | #REF! | PRESTITI PERSONALI - CQP Wave 2 | #REF! | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Dialogo Industriale - WB | #REF! | Dialogo Industriale - WB | #REF! | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Framework settoriale | #REF! | Framework settoriale | #REF! | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #VALUE! |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #REF! | #REF! |  |  |  | <
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #VALUE! |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #VALUE! |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #VALUE! |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #VALUE! |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #REF! | #REF!
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #VALUE! |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #REF! | #REF!

## REV TAB (hidden)
Progetti gestiti: 26 | REV_TAB s27 (29/06-05/07) | REV_TAB s28 (06/07-12/07) | REV_TAB s29 (13/07-19/07) | REV_TAB s30 (20/07-26/07) | REV_TAB s31 (27/07-02/08) | REV_TAB s32 (03/08-09/08) | REV_TAB s33 (10/08-16/08) | REV_TAB s34 (17/08-23/08) | REV_TAB s35 (24/08-30/08) | Rev Tab Agosto | REV_TAB s36 (31/08-06/09) | REV_TAB s37 (07/09-13/09) | REV_TAB s38 (14/09-20/09) | REV_TAB s39 (21/09-27/09) | REV_TAB s40 (28/09-04/10) | REV_TAB s41 (05/10-11/10) | REV_TAB s42 (12/10-18/10) | REV_TAB s43 (19/10-25/10) | REV_TAB s44 (26/10-01/11) | REV_TAB s45 (02/11-08/11) | REV_TAB s46 (09/11-15/11) | REV_TAB s47 (16/11-22/11) | REV_TAB s48 (23/11-29/11) | REV_TAB s49 (30/11-06/12) | REV_TAB s50 (07/12-13/12) | REV_TAB s51 (13/12-20/12)
CONTRATTI DIGITALI | 36669.3 | 39534.425 | 44710.58 | 49155.375 | 51938.6 | 52336.095 | 52620.02 | 52620.02 | 53187.87 | 851.775 | 64673.2 | 67571.405 | 69700.975 | 72017.745 | 73427.315 | 76194.765 | 78352.185 | 79777.785 | 79777.79 | 81008.99 | 81008.99
CRUSCOTTO ABC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036.5 | 2254.5 | 2937 | 3912.7 | 4830 | 4830 | 6440 | 6440 | 8313.25
SALESFORCE | [9 empty] | 0 | 0 | 0 | 0 | 230 | 729.84 | 2019.84 | 3767.84 | 4375 | 4659.8 | 4659.8 | 4659.8
SMERETAIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226.6 | 6404.6 | 9048.7 | 12126.792 | 18275.012 | 22797.632 | 27971.602 | 32645.6 | 36020 | 40619.42
CO - B ROWSING | 0 | 0 | 0 | 0 | 0 | 0 | 831 | 831 | 831 | 831 | 831 | 831 | 831 | 831 | 2593.475 | 2984.6625 | 2984.6625 | 4352.6625 | 8222.432 | 8222.432 | 8222.432
INCASSI | 4803.486 | 5974.584 | 6998.28 | 7514.568 | 7808.232 | 8258.232 | 8330.232 | 8330.232 | 8330.232 | 72 | 9441.456 | 10526.448 | 10852.428 | 11395.356 | 12000.6 | 12701.844 | 13651.446 | 13872.036 | 14027.826 | 14356.542 | 14423.7
Credito Anomalo | 177905.06 | 185495.89 | 191028.6375 | 198130.9575 | 202424.0775 | 207191.6775 | 211311.9975 | 212211.9975 | 213291.9975 | 6100.32 | 226574.9655 | 227285.0295 | 227285.0295 | 227285.0295 | 227285.0295 | 227285.0295 | 227285.0295 | 227285.0295 | 235820.4585 | 235820.4585 | 235820.4585
Credito Anomalo H2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6978 | 14683.656 | 10849.656 | 22826.13 | 29891.12 | 33057.08 | 36972.2 | 40139.53 | 44954.17 | 51103.74 | 57096.84
Credito Anomalo Automation Test | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTESA - APP INBIZ | 14720.7 | 15471.42 | 16071.42 | 16093.92 | 16093.92 | 16206.42 | 16206.42 | 16206.42 | 16206.42 | 0 | 16746.42 | 16926.42 | 17152.5 | 17858.1 | 18123.3 | 18303.3 | 19318.5 | 19376.1 | 19376.1 | 19376.1 | 19376.1
SMART LENDING w2- w3 | 17012.4 | 18531.6 | 20115.6 | 20763.6 | 20763.6 | 20763.6 | 20763.6 | 20763.6 | 20763.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GEVOC | 930.64 | 962.64 | 2434.64 | 4585.29 | 4585.29 | 5388.14 | 5310.58 | 5432.46 | 5688.46 | 300.32 | 6248.052 | 6689.8 | 7009.8 | 7009.8 | 7009.8 | 7009.8 | 7009.8 | 7009.8 | 7009.8 | 7041.8 | 7041.8
Evolutive OMEGA | 3851.088 | 3915.088 | 3915.088 | 6213.92 | 6213.92 | 6213.92 | 8009.44 | 8009.44 | 9916.64 | 3702.72 | 10817.044 | 14040.072 | 14040.072 | 15073.192 | 15587.584 | 16469.24 | 16700.36 | 16739.08 | 16771.08 | 16803.08 | 16803.08
Evolutive OMEGA 175 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.13 | 1568.63 | 1568.63
CJ Breve termine | 10528.32 | 13733.04 | 15998.09 | 17748.41 | 18318.65 | 20270.568 | 22005.588 | 23251.908 | 25882.608 | 5612.04 | 27588.24 | 30487.2 | 32622.042 | 34723.308 | 36178.428 | 37608.2 | 39287.97 | 40949.99 | 42251.03 | 45105.78 | 47936.69
ARUBA CERTIFIED CLOUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AVVERA 2 | 10580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AVVERA - Performance | 10800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ARUBA FATTURAZIONE EL. | 400 | 1400 | 2450 | 3100 | 4220 | 5220 | 6370 | 6370 | 6370 | 1150 | 7990 | 8990 | 10790 | 10170 | 11170 | 12170 | 13570 | 14770 | 16070.1 | 16070.1 | 16970.1
ARUBA PEC PSW | 3660 | 3660 | 3660 | 3660 | 3660 | 3660 | 4218 | 4218 | 4218 | 558 | 0 | 0 | 0 | 4020 | 4020 | 4020 | 4020 | 4020 | 0 | 0 | 0
ARUBA SSL E-commerce | 6169 | 6409 | 6409 | 7049 | 7289 | 7529 | 9113 | 9113 | 9593 | 2064 | 10473 | 10673 | 10873 | 15833 | 15833 | 15833 | 15833 | 15833 | 16174.1 | 16174.1 | 16174.1
ARUBA ACi INFORMATICA | 2080 | 2280 | 2480 | 2920 | 3360 | 3360 | 3360 | 3360 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CA 2 ruote | 800 | 1000 | 1360 | 2120 | 2320 | 2320 | 4780 | 5580 | 5580 | 3260 | 5580 | 6230 | 6230 | 6430 | 6630 | 6730 | 6730 | 6730 | 0 | 0 | 0
CA Protezione e salute | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 900 | 900 | 900 | 1360 | 2560 | 4420 | 5900 | 6100 | 6300 | 6300 | 6300 | 0 | 0 | 0
CA Small Business | 440 | 1630 | 2670 | 3510 | 3510 | 3510 | 3510 | 3510 | 3510 | 0 | 3510 | 3510 | 3510 | 3510 | 3510 | 3510 | 3510 | 3510 | 0 | 0 | 0
Nexi MPOS | 0 | 0 | 1120 | 1120 | 1120 | 2010 | 3300 | 3980 | 4370 | 2360 | 7500 | 11350 | 14360 | 16860 | 18880 | 20660 | 22200 | 24700 | 24700 | 24700 | 24700
ARUBA DE VISU | [9 empty] | 0 | 0 | 0 | 300 | 1400 | 2100 | 2840 | 3040 | 3640 | 3640 | 3640 | 3640
ARUBA B7 | [9 empty] | 0 | - | - | 0 | 1000 | 1200 | 1880 | 3240 | 3440 | 3440 | 3440 | 3440
0
TOTALE ROMANO | 266420.994 | 283618.687 | 301272.3355 | 320206.0405 | 328146.2895 | 336628.6525 | 345388.8775 | 347657.0775 | 354098.8275 | 17470.175 | 369898.3775 | 390267.6305 | 397784.6025 | 420552.8605 | 437890.2835 | 455821.473 | 472957.625 | 486678.615 | 512092.2165 | 527527.3525 | 542891.1905
TOTALE PELUSO | 34929 | 29179 | 32949 | 36279 | 38279 | 40409 | 48151 | 49831 | 50701 | 10292 | 36413 | 43313 | 50483 | 65123 | 69443 | 73943 | 78443 | 82943 | 64024.2 | 64024.2 | 64924.2
Credit Agricole | [10 empty] | 10450 | 12300 | 14160 | 15840 | 16240 | 16540 | 16540 | 16540

## Project_1
PROJECT OVERVIEW
| Project Name | Project 1 |  | Estimation | yes
| Responsible | Test Manager Green Team |  | Sceduling | yes | [47 empty] | AC(AD) | AC(27) | 62654 |  | Acn(ADn=1) | 0.53704
| Client | Bank 1 | [5 empty] | Business Unit | Financial Services |  | Assumptions
| Area | Crediti | [5 empty] | Prectice | Testing |  | Client charge | Test Manager | 330
| Resource number | 8 | [5 empty] | Sub-practice level 1 | Area Operations |  | €/gg | Tester | 200 | [39 empty] | ADn | 1
| Starting date | 2022-09-01 | [5 empty] | Sub-practice level 2 | Credit Management
| Release (Go live) | 2023-03-10 | [5 empty] | Sub-practice level 3 | Non-performing Credit Operations | [31 empty] | Project Planned Elapsed time
| Main Activities | Desing, DP, Execution, Management and UAT | [5 empty] | Activity Description | Credits with temporary borrower noncompliance. The aim is to seek the best possible interventions to come back to the normal relation conditions, or, conversely, the arrangement of the necessary documentation for the suffering side | [31 empty] | 27 | weeks
| %completion | 100%
| Next Milestone | N/A
| TM Estimate Name | Estimate 1: Project_1_2022.xls
| Estimate Budget | 122498.25
BASELINE | [40 empty] | Week | Time Unit | TPn | BASELINE | BCWS | EV | ES | Actual Costs | ACWP | CPI | SPI | SPIt | CV | SV | RFI | RV | CEACn=BACn | CEACn=BACn-CVn | CEACn=BCAn/CPI | CEACn=BACn/(CPI*SPI) | CEACn=BACn/ ( .8 CPI + .2 SPI) | CEACn=BACn/(CPI*SPIt) | CEACn=BACn/ ( .8 CPI + .2 SPIt) | WS | WP | ACn | BACn | ESn | CVn | SVn | RVn
[42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 2022-09-05 | 2022-09-09 | S37 | 1 | 0.037037 | 2495 | 2495 | 1094.505 | 0.43868 | 2662 | 2662 | 0.41116 | 0.43868 | 0.43868 | -1567.495 | -1400.495 | 0.93727 | -167 | 1 | 1.0134 | 2.4321 | 5.5443 | 2.4 | 5.5443 | 2.4 | 0.021386 | 0.0093816 | 0.022817 | 1 | 0.016247 | -0.013436 | -1.2% | -0.0014314
[39 empty] | 2022-09-12 | 2022-09-16 | S38 | 2 | 0.074074 | 2495 | 4990 | 2489.01 | 0.9976 | 1566 | 4228 | 0.5887 | 0.4988 | 0.4988 | -1738.99 | -2500.99 | 1.1802 | 762 | 1 | 1.0149 | 1.6987 | 3.4055 | 1.7522 | 3.4055 | 1.7522 | 0.042772 | 0.021335 | 0.036241 | 1 | 0.036948 | -0.014906 | -2.144% | 0.0065315
|  | Project Activities | [8 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2022-09-19 | 2022-09-23 | S39 | 3 | 0.11111 | 2495 | 7485 | 7483.515 | 2.9994 | 2338 | 6566 | 1.1397 | 0.9998 | 0.9998 | 917.515 | -1.485 | 1.14 | 919 | 1 | 0.99214 | 0.8774 | 0.87757 | 0.89948 | 0.87757 | 0.89948 | 0.064158 | 0.064145 | 0.056281 | 1 | 0.11109 | 0.0078645 | -0.001273% | 0.0078773
|  | Start Date | End Date | Starting week number | Ending week number | FTEs | FTE figure | Weight | Budget x activity |  | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2022-09-26 | 2022-09-30 | S40 | 4 | 0.14815 | 4145 | 11630 | 8708.02 | 3.2951 | 2148 | 8714 | 0.99931 | 0.74875 | 0.82376 | -5.98 | -2921.98 | 1.3346 | 2916 | 1 | 1.0001 | 1.0007 | 1.3365 | 1.0535 | 1.2148 | 1.0371 | 0.099687 | 0.074641 | 0.074692 | 1 | 0.12204 | -5.1258e-05 | -2.505% | 0.024995
| Project 1 | 2022-09-05 | 2023-03-10 | 37 | 10 |  |  | 100% | overall budget - allocation plan | Scheduling | € | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | 2022-10-03 | 2022-10-07 | S41 | 5 | 0.18519 | 4145 | 15775 | 10662.525 | 3.7666 | 2094 | 10808 | 0.98654 | 0.67591 | 0.75332 | -145.475 | -5112.475 | 1.4596 | 4967 | 1 | 1.0012 | 1.0136 | 1.4997 | 1.0818 | 1.3456 | 1.0639 | 0.13522 | 0.091394 | 0.092641 | 1 | 0.1395 | -0.0012469 | -4.382% | 0.042575
| Testbook Design | 2022-09-05 | 2022-09-22 | 37 | 39 | 2/day | Test Analyst | 5.143% | 6000 | Testbook Design | 6000 | 2000 | 2000 | 2000 | [24 empty] | 2022-10-10 | 2022-10-14 | S42 | 6 | 0.22222 | 4145 | 19920 | 14077.03 | 4.5904 | 1766 | 12574 | 1.1195 | 0.70668 | 0.76506 | 1503.03 | -5842.97 | 1.5842 | 7346 | 1 | 0.98712 | 0.89323 | 1.264 | 0.96435 | 1.1675 | 0.95362 | 0.17075 | 0.12066 | 0.10778 | 1 | 0.17001 | 0.012883 | -5.008% | 0.062967
| Data preparation | 2022-09-26 | 2022-10-20 | 40 | 43 | 3/day | Test Analyst; Test Manager | 12.51% | 14600 | Data preparation | 14600 |  |  |  | 3650 | 3650 | 3650 | 3650 | [20 empty] | 2022-10-17 | 2022-10-21 | S43 | 7 | 0.25926 | 7145 | 27065 | 21583.535 | 6.2328 | 4358 | 16932 | 1.2747 | 0.79747 | 0.8904 | 4651.535 | -5481.465 | 1.5985 | 10133 | 1 | 0.96013 | 0.78449 | 0.98372 | 0.84798 | 0.88105 | 0.83483 | 0.23199 | 0.185 | 0.14513 | 1 | 0.23085 | 0.039871 | -4.698% | 0.086856
| Integration | 2022-10-21 | 2022-10-31 | 43 | 45 | 3/day | Test Analyst; Software Tester | 7.714% | 9000 | Integration | 9000 | [6 empty] | 3000 | 3000 | 3000 | [18 empty] | 2022-10-24 | 2022-10-28 | S44 | 8 | 0.2963 | 3495 | 30560 | 26676.04 | 6.9456 | 2095 | 19027 | 1.402 | 0.87291 | 0.8682 | 7649.04 | -3883.96 | 1.6061 | 11533 | 1 | 0.93444 | 0.71326 | 0.81711 | 0.77149 | 0.82155 | 0.77205 | 0.26195 | 0.22866 | 0.16309 | 1 | 0.25724 | 0.065564 | -3.329% | 0.098856
| Execution | 2022-11-03 | 2022-12-21 | 45 | 52 | 5/day | Test Analyst; Software Tester; Test Manager | 38.74% | 45200 | Execution | 45200 | [8 empty] | 5650 | 5650 | 5650 | 5650 | 5650 | 5650 | 5650 | 5650 | [11 empty] | 2022-10-31 | 2022-11-04 | S45 | 9 | 0.33333 | 9645 | 40205 | 33358.545 | 8.6525 | 4875 | 23902 | 1.3956 | 0.82971 | 0.96139 | 9456.545 | -6846.455 | 1.6821 | 16303 | 1 | 0.91894 | 0.71652 | 0.86358 | 0.77976 | 0.74529 | 0.76407 | 0.34462 | 0.28593 | 0.20488 | 1 | 0.32046 | 0.081057 | -5.868% | 0.13974
| Retest | 2023-01-09 | 2023-01-19 | 2 | 3 | 2/day | Software Tester | 3.429% | 4000 | Retest | 4000 | [18 empty] | 2000 | 2000 | [7 empty] | 2022-11-07 | 2022-11-11 | S46 | 10 | 0.37037 | 6645 | 46850 | 40365.05 | 9.0241 | 4907 | 28809 | 1.4011 | 0.86158 | 0.90241 | 11556.05 | -6484.95 | 1.6262 | 18041 | 1 | 0.90095 | 0.71371 | 0.82837 | 0.77327 | 0.7909 | 0.76841 | 0.40158 | 0.34599 | 0.24694 | 1 | 0.33423 | 0.099053 | -5.559% | 0.15464
| Management | 2022-09-05 | 2023-03-10 | 37 | 10 | 1,5/week | Test Manager | 11.46% | 13365 | Management | 13365 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 2022-11-14 | 2022-11-18 | S47 | 11 | 0.40741 | 6645 | 53495 | 42413.555 | 9.3324 | 3154 | 31963 | 1.327 | 0.79285 | 0.8484 | 10450.555 | -11081.445 | 1.6737 | 21532 | 1 | 0.91042 | 0.7536 | 0.9505 | 0.81958 | 0.88827 | 0.81219 | 0.45854 | 0.36355 | 0.27397 | 1 | 0.34564 | 0.089577 | -9.499% | 0.18456
| ALM maintenance | 2023-01-20 | 2023-02-10 | 3 | 6 | 1,5/day | Software Tester | 5.143% | 6000 | ALM maintenance | 6000 | [19 empty] | 1500 | 1500 | 1500 | 1500 |  |  |  |  | 2022-11-21 | 2022-11-25 | S48 | 12 | 0.44444 | 6645 | 60140 | 46722.06 | 9.9807 | 5382 | 37345 | 1.2511 | 0.77689 | 0.83173 | 9377.06 | -13417.94 | 1.6104 | 22795 | 1 | 0.91962 | 0.7993 | 1.0288 | 0.86486 | 0.96101 | 0.85674 | 0.51549 | 0.40048 | 0.3201 | 1 | 0.36966 | 0.080376 | -11.5% | 0.19539
| Reporting activities | 2022-11-03 | 2023-02-10 | 45 | 6 | 0,5/day | Test Analyst | 5.572% | 6500 | Reporting activities | 6500 | [8 empty] | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 |  |  | 500 | 500 | 500 | 500 | 500 |  |  |  |  | 2022-11-28 | 2022-12-02 | S49 | 13 | 0.48148 | 6645 | 66785 | 61878.565 | 12.2616 | 3959 | 41304 | 1.4981 | 0.92653 | 0.9432 | 20574.565 | -4906.435 | 1.6169 | 25481 | 1 | 0.82364 | 0.6675 | 0.72043 | 0.72264 | 0.7077 | 0.72091 | 0.57245 | 0.5304 | 0.35404 | 1 | 0.45413 | 0.17636 | -4.206% | 0.21841
| UAT support | 2023-02-13 | 2023-03-10 | 7 | 10 | 3/day | Test Analyst; Software Tester | 10.29% | 12000 | UAT support | 12000 | [23 empty] | 3000 | 3000 | 3000 | 3000 | 2022-12-05 | 2022-12-09 | S50 | 14 | 0.51852 | 6645 | 73430 | 67543.07 | 13.1141 | 2552 | 43856 | 1.5401 | 0.91983 | 0.93672 | 23687.07 | -5886.93 | 1.6743 | 29574 | 1 | 0.79697 | 0.6493 | 0.7059 | 0.70619 | 0.69317 | 0.70451 | 0.62941 | 0.57895 | 0.37591 | 1 | 0.48571 | 0.20303 | -5.046% | 0.2535
[11 empty] | 116665 | 2495 | 2495 | 2495 | 4145 | 4145 | 4145 | 7145 | 3495 | 9645 | 6645 | 6645 | 6645 | 6645 | 6645 | 6645 | 6645 | 495 | 495 | 2995 | 4495 | 2495 | 2495 | 2495 | 3495 | 3495 | 3495 | 3495 | 2022-12-12 | 2022-12-16 | S51 | 15 | 0.55556 | 6645 | 80075 | 75721.575 | 14.3449 | 4205 | 48061 | 1.5755 | 0.94563 | 0.95632 | 27660.575 | -4353.425 | 1.6661 | 32014 | 1 | 0.76291 | 0.63471 | 0.6712 | 0.68987 | 0.66369 | 0.68885 | 0.68637 | 0.64905 | 0.41196 | 1 | 0.53129 | 0.23709 | -3.732% | 0.27441
[10 empty] | Contingency up to the project type | 5833.25 | [27 empty] | 2022-12-19 | 2022-12-23 | S52 | 16 | 0.59259 | 6645 | 86720 | 78476.08 | 14.7594 | 3814 | 51875 | 1.5128 | 0.90494 | 0.92246 | 26601.08 | -8243.92 | 1.6717 | 34845 | 1 | 0.77199 | 0.66103 | 0.73047 | 0.71879 | 0.71659 | 0.71699 | 0.74332 | 0.67266 | 0.44465 | 1 | 0.54664 | 0.22801 | -7.066% | 0.29868
[10 empty] | >10%--> highly risk project | [28 empty] | 2022-12-26 | 2022-12-30 | S53 | 17 | 0.62963 | 495 | 87215 | 87106.585 | 16.781 | 592 | 52467 | 1.6602 | 0.99876 | 0.98712 | 34639.585 | -108.415 | 1.6623 | 34748 | 1 | 0.70309 | 0.60233 | 0.60308 | 0.65448 | 0.61019 | 0.65548 | 0.74757 | 0.74664 | 0.44972 | 1 | 0.62152 | 0.29691 | -0.09293% | 0.29784
[10 empty] | btw 5% and 10% --> medium risk project | [28 empty] | 2023-01-02 | 2023-01-06 | S1 | 18 | 0.66667 | 495 | 87710 | 88001.09 | 18.0972 | 135 | 52602 | 1.673 | 1.0033 | 1.0054 | 35399.09 | 291.09 | 1.6674 | 35108 | 1 | 0.69657 | 0.59774 | 0.59577 | 0.64976 | 0.59453 | 0.64958 | 0.75181 | 0.75431 | 0.45088 | 1 | 0.67027 | 0.30343 | 0.2495% | 0.30093
[10 empty] | <5% --> low risk project | [28 empty] | 2023-01-09 | 2023-01-13 | S2 | 19 | 0.7037 | 2995 | 90705 | 90000.595 | 18.7648 | 1495 | 54097 | 1.6637 | 0.99223 | 0.98762 | 35903.595 | -704.405 | 1.6767 | 36608 | 1 | 0.69225 | 0.60107 | 0.60578 | 0.65385 | 0.60861 | 0.65425 | 0.77748 | 0.77144 | 0.4637 | 1 | 0.69499 | 0.30775 | -0.6038% | 0.31379
ACTUAL COSTS | [38 empty] | 2023-01-16 | 2023-01-20 | S3 | 20 | 0.74074 | 4495 | 95200 | 91895.1 | 19.2648 | 1325 | 55422 | 1.6581 | 0.96528 | 0.96324 | 36473.1 | -3304.9 | 1.7177 | 39778 | 1 | 0.68737 | 0.6031 | 0.62479 | 0.6581 | 0.62612 | 0.65827 | 0.81601 | 0.78768 | 0.47505 | 1 | 0.71351 | 0.31263 | -2.833% | 0.34096
[39 empty] | 2023-01-23 | 2023-01-27 | S4 | 21 | 0.77778 | 2495 | 97695 | 97384.605 | 20.8756 | 600 | 56022 | 1.7383 | 0.99682 | 0.99408 | 41362.605 | -310.395 | 1.7439 | 41673 | 1 | 0.64546 | 0.57527 | 0.5771 | 0.62892 | 0.57869 | 0.62914 | 0.8374 | 0.83474 | 0.4802 | 1 | 0.77317 | 0.35454 | -0.2661% | 0.3572
[39 empty] | 2023-01-30 | 2023-02-03 | S5 | 22 | 0.81481 | 2495 | 100190 | 99259.11 | 21.6269 | 344 | 56366 | 1.761 | 0.99071 | 0.98304 | 42893.11 | -930.89 | 1.7775 | 43824 | 1 | 0.63234 | 0.56787 | 0.57319 | 0.62231 | 0.57766 | 0.6229 | 0.85878 | 0.8508 | 0.48314 | 1 | 0.801 | 0.36766 | -0.7979% | 0.37564
[11 empty] | Price List €/h | 11 | [26 empty] | 2023-02-06 | 2023-02-10 | S6 | 23 | 0.85185 | 2495 | 102685 | 102673.615 | 22.9954 | 410 | 56776 | 1.8084 | 0.99989 | 0.9998 | 45897.615 | -11.385 | 1.8086 | 45909 | 1 | 0.60659 | 0.55298 | 0.55304 | 0.60728 | 0.55309 | 0.60728 | 0.88017 | 0.88007 | 0.48666 | 1 | 0.85168 | 0.39341 | -0.009759% | 0.39351
[11 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-02-13 | 2023-02-17 | S7 | 24 | 0.88889 | 3495 | 106180 | 105568.12 | 23.8249 | 1639 | 58415 | 1.8072 | 0.99424 | 0.99271 | 47153.12 | -611.88 | 1.8177 | 47765 | 1 | 0.59582 | 0.55334 | 0.55655 | 0.60805 | 0.55741 | 0.60816 | 0.91013 | 0.90488 | 0.50071 | 1 | 0.8824 | 0.40418 | -0.5245% | 0.40942
[11 empty] | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-02-20 | 2023-02-24 | S8 | 25 | 0.92593 | 3495 | 109675 | 112062.625 | 25.6832 | 1448 | 59863 | 1.872 | 1.0218 | 1.0273 | 52199.625 | 2387.625 | 1.8321 | 49812 | 1 | 0.55257 | 0.53419 | 0.52281 | 0.58756 | 0.51998 | 0.58718 | 0.94008 | 0.96055 | 0.51312 | 1 | 0.95123 | 0.44743 | 2.047% | 0.42697
[10 empty] | Software Tester 1 (stage) |  | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | 2023-02-27 | 2023-03-03 | S9 | 26 | 0.96296 | 3495 | 113170 | 115437.13 | 26.6487 | 1831 | 61694 | 1.8711 | 1.02 | 1.0249 | 53743.13 | 2267.13 | 1.8344 | 51476 | 1 | 0.53934 | 0.53444 | 0.52394 | 0.58792 | 0.52143 | 0.58758 | 0.97004 | 0.98948 | 0.52881 | 1 | 0.98699 | 0.46066 | 1.943% | 0.44123
[10 empty] | Testbook Design | 0 | [27 empty] | 2023-03-06 | 2023-03-10 | S10 | 27 | 1 | 3495 | 116665 | 116665 | 27 | 960 | 62654 | 1.8621 | 1 | 1 | 54011 | 1.4552e-11 | 1.8621 | 54011 | 1 | -0.45243 | 0.53704 | 0.53704 | 0.59184 | 0.53704 | 0.59184 | 1 | 1.9895 | 0.53704 | 1 | 1 | 1.4524 | 98.95% | 0.46296
[10 empty] | Data preparation | 0
[10 empty] | Integration | 120 | S43: 40; S44: 40; S45: 32; S46: 8
[10 empty] | Execution | 256 | S46: 48; S47: 12; S48: 40; S49: 40; S50: 32; S51: 40; S52: 44
[10 empty] | Retest | 80 | S2: 40; S3: 40
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 128 | S7: 40; S8: 40; S9: 32; S10: 16
[11 empty] | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 32 | 56 | 12 | 40 | 40 | 32 | 40 | 44 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 40 | 40 | 32 | 16
[11 empty] | Price List €/h | S37: 11
[11 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06
[11 empty] | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10
[10 empty] | Software Tester 2 (stage) |  | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 280 | S45: 32; S46: 40; S47: 40; S48: 40; S49: 32; S50: 16; S51: 40; S52: 40
[10 empty] | Retest | 80 | S2: 40; S3: 40
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 16 | S3: 2; S4: 12; S6: 2
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 88 | S7: 8; S8: 40; S9: 24; S10: 16
[11 empty] | 464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 40 | 40 | 40 | 32 | 16 | 40 | 40 | 0 | 0 | 40 | 42 | 12 | 0 | 2 | 8 | 40 | 24 | 16
[11 empty] | Price List €/h | S37: 22
[11 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06
[11 empty] | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10
[10 empty] | Software Tester 3 (apprenticeship) |  | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 104 | S43: 32; S44: 32; S45: 32; S46: 8
[10 empty] | Execution | 277 | S46: 40; S47: 40; S48: 40; S49: 45; S50: 32; S51: 40; S52: 40
[10 empty] | Retest | 18 | S4: 16; S5: 2
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 27 | S3: 8; S4: 4; S5: 4; S6: 8; S7: 3
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 88 | S7: 40; S8: 16; S9: 24; S10: 8
[11 empty] | 514 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 48 | 40 | 40 | 45 | 32 | 40 | 40 | 0 | 0 | 0 | 8 | 20 | 6 | 8 | 43 | 16 | 24 | 8
[11 empty] | Price List €/h | S37: 28
[11 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06
[11 empty] | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10
[10 empty] | Test Analyst 1 |  | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10
[10 empty] | Testbook Design | 110 | S37: 40; S38: 30; S39: 40
[10 empty] | Data preparation | 96 | S40: 40; S41: 16; S42: 32; S43: 8
[10 empty] | Integration | 104 | S43: 32; S44: 32; S45: 32; S46: 8
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 27 | S45: 2; S46: 2; S47: 2; S48: 2; S49: 2; S50: 2; S51: 2; S52: 2; S2: 4; S3: 4; S4: 1; S5: 1; S6: 1
[10 empty] | UAT support | 0
[11 empty] | 337 | 40 | 30 | 40 | 40 | 16 | 32 | 40 | 32 | 34 | 10 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 4 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0
[11 empty] | Price List €/h | S37: 28
[11 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06
[11 empty] | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10
[10 empty] | Test Analyst 2 |  | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10
[10 empty] | Testbook Design | 99 | S37: 40; S38: 24; S39: 35
[10 empty] | Data preparation | 100 | S40: 20; S41: 24; S42: 16; S43: 40
[10 empty] | Integration | 0
[10 empty] | Execution | 288 | S45: 32; S46: 32; S47: 24; S48: 44; S49: 44; S50: 32; S51: 40; S52: 32; S53: 8
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 487 | 40 | 24 | 35 | 20 | 24 | 16 | 40 | 0 | 32 | 32 | 24 | 44 | 44 | 32 | 40 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Price List €/h | S37: 46
[11 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06
[11 empty] | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10
[10 empty] | Test Manager |  | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 53 | S40: 5; S41: 20; S42: 8; S43: 20
[10 empty] | Integration | 0
[10 empty] | Execution | 183 | S45: 32; S46: 32; S47: 16; S48: 32; S49: 8; S50: 8; S51: 24; S52: 23; S53: 8
[10 empty] | Retest | 0
[10 empty] | Management | 60 | S37: 8; S39: 4; S40: 4; S45: 2; S46: 2; S47: 4; S48: 8; S2: 8; S5: 4; S6: 4; S9: 12
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 296 | 8 | 0 | 4 | 9 | 20 | 8 | 20 | 0 | 34 | 34 | 20 | 40 | 8 | 8 | 24 | 23 | 8 | 0 | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 12 | 0
[11 empty] | Price List €/h | S37: 55
[11 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06
[11 empty] | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10
[10 empty] | Service Manager |  | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 16 | S48: 8; S49: 8
[10 empty] | Retest | 0
[10 empty] | Management | 9 | S44: 1; S45: 1; S46: 1; S51: 3; S7: 3
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 8 | 8 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
[11 empty] | Price List €/h | S37: 27
[11 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06
[11 empty] | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10
[10 empty] | PMO |  | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 65 | S37: 2; S38: 2; S39: 2; S40: 2; S41: 2; S42: 2; S43: 2; S47: 2; S48: 2; S49: 3; S1: 5; S2: 5; S3: 5; S8: 8; S9: 5; S10: 16
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 65 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 16
[11 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06
[11 empty] | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10
[10 empty] | Actual Total Costs | 62654 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10
[10 empty] | Testbook Design | 5852 | 2240 | 1512 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Data preparation | 7926 | 0 | 0 | 0 | 1910 | 2040 | 1712 | 2264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Integration | 6520 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 2040 | 1952 | 488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Execution | 29352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2720 | 4216 | 2860 | 4904 | 3822 | 2496 | 3984 | 3758 | 592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Retest | 2156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 880 | 352 | 44 | 0 | 0 | 0 | 0 | 0
[10 empty] | Management | 5010 | 422 | 54 | 238 | 238 | 54 | 54 | 54 | 55 | 147 | 147 | 238 | 422 | 81 | 0 | 165 | 0 | 0 | 135 | 503 | 135 | 0 | 184 | 184 | 165 | 216 | 687 | 432
[10 empty] | ALM maintenance | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 220 | 88 | 198 | 66 | 0 | 0 | 0
[10 empty] | Reporting activities | 756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 0 | 0 | 112 | 112 | 28 | 28 | 28 | 0 | 0 | 0 | 0
[10 empty] | UAT support | 4312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1408 | 1232 | 1144 | 528
[12 empty] | 2662 | 1566 | 2338 | 2148 | 2094 | 1766 | 4358 | 2095 | 4875 | 4907 | 3154 | 5382 | 3959 | 2552 | 4205 | 3814 | 592 | 135 | 1495 | 1325 | 600 | 344 | 410 | 1639 | 1448 | 1831 | 960
EARNED VALUE
[11 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06
[11 empty] | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10
[10 empty] | %Progress | 100% | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10
[10 empty] | Testbook Design | 100% | 10% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Data preparation | 100% | 0% | 0% | 0% | 5% | 15% | 35% | 67% | 80% | 92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Integration | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 26% | 56% | 83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Execution | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3% | 10% | 12% | 19% | 50% | 60% | 77% | 82% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Retest | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 33% | 57% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Management | 100% | 3.7% | 7.4% | 11.1% | 14.8% | 18.5% | 22.2% | 25.9% | 29.6% | 33.3% | 37% | 40.7% | 44.4% | 48.1% | 51.8% | 55.5% | 59.2% | 62.9% | 66.6% | 70.3% | 74% | 77.7% | 81.4% | 85.1% | 88.8% | 92.5% | 96.2% | 100%
[10 empty] | ALM maintenance | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3% | 50% | 60% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Reporting activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 50% | 60% | 60% | 60% | 60% | 60% | 69% | 73% | 80% | 92% | 100% | 100% | 100% | 100% | 100%
[10 empty] | UAT support | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 70% | 94% | 100%
[12 empty] | 0.9382% | 2.133% | 6.415% | 7.464% | 9.139% | 12.07% | 18.5% | 22.87% | 28.59% | 34.6% | 36.35% | 40.05% | 53.04% | 57.89% | 64.91% | 67.27% | 74.66% | 75.43% | 77.14% | 78.77% | 83.47% | 85.08% | 88.01% | 90.49% | 96.06% | 98.95% | 100%
[11 empty] | FROM | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06
[11 empty] | TO | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10
[10 empty] | EV | 116665 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10
[10 empty] | Testbook Design | 6000 | 600 | 1500 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
[10 empty] | Data preparation | 14600 | 0 | 0 | 0 | 730 | 2190 | 5110 | 9782 | 11680 | 13432 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600 | 14600
[10 empty] | Integration | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 2340 | 5040 | 7470 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000
[10 empty] | Execution | 45200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1356 | 4520 | 5424 | 8588 | 22600 | 27120 | 34804 | 37064 | 45200 | 45200 | 45200 | 45200 | 45200 | 45200 | 45200 | 45200 | 45200 | 45200 | 45200
[10 empty] | Retest | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 1320 | 2280 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
[10 empty] | Management | 13365 | 494.505 | 989.01 | 1483.515 | 1978.02 | 2472.525 | 2967.03 | 3461.535 | 3956.04 | 4450.545 | 4945.05 | 5439.555 | 5934.06 | 6428.565 | 6923.07 | 7417.575 | 7912.08 | 8406.585 | 8901.09 | 9395.595 | 9890.1 | 10384.605 | 10879.11 | 11373.615 | 11868.12 | 12362.625 | 12857.13 | 13365
[10 empty] | ALM maintenance | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 3000 | 3600 | 6000 | 6000 | 6000 | 6000 | 6000
[10 empty] | Reporting activities | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1300 | 1950 | 2600 | 3250 | 3900 | 3900 | 3900 | 3900 | 3900 | 4485 | 4745 | 5200 | 5980 | 6500 | 6500 | 6500 | 6500 | 6500
[10 empty] | UAT support | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 8400 | 11280 | 12000
[12 empty] | 1094.505 | 2489.01 | 7483.515 | 8708.02 | 10662.525 | 14077.03 | 21583.535 | 26676.04 | 33358.545 | 40365.05 | 42413.555 | 46722.06 | 61878.565 | 67543.07 | 75721.575 | 78476.08 | 87106.585 | 88001.09 | 90000.595 | 91895.1 | 97384.605 | 99259.11 | 102673.615 | 105568.12 | 112062.625 | 115437.13 | 116665
Formulas:
Test Manager = [Test Manager, row above]+4
Bank 1 = MIN([Bank 1, row below]:C30)

## Project_2
PROJECT OVERVIEW
| Project Name | Project 2 |  | Estimation | yes
| Responsible | Test Manager Green Team |  | Sceduling | yes | [38 empty] | AC(AD) | AC(21) |  | 58572 |  | Acn(ADn=1) | 0.84581
| Client | Bank 1 | [5 empty] | Business Unit | Financial Services |  | Assumptions
| Area | Crediti | [5 empty] | Prectice | Testing |  | Client charge | Test Manager | 330
| Resource number | 6 | [5 empty] | Sub-practice level 1 | Area Operations |  | €/gg | Tester | 200 | [30 empty] | ADn | 1
| Starting date | 2022-08-01 | [5 empty] | Sub-practice level 2 | Credit Management
| Release (Go live) | 2022-12-23 | [5 empty] | Sub-practice level 3 | Credit Granting | [24 empty] | Project Planned Elapsed time
| Main Activities | Desing, DP, Execution, Management and UAT | [5 empty] | Activity Description | Process with the aim of credit granting to clinets. Compilation, arrangement, and insertion of the necassary documentation and information in ordert to analyze the reliability of the client who asks for the granting . | [24 empty] | 21 | weeks
| %completion | 100%
| Next Milestone | N/A
| TM Estimate Name | Estimate 2: Project_2_.xls
| Estimate Budget | 72100
BASELINE | [34 empty] | Week | Time Unit | TPn | BASELINE | BCWS | EV | ES | Actual Costs | ACWP | CPI | SPI | SPIt | CV | SV | RFI | RV | CEACn=BACn | CEACn=BACn-CVn | CEACn=BCAn/CPI | CEACn=BACn/(CPI*SPI) | CEACn=BACn/ ( .8 CPI + .2 SPI) | CEACn=BACn/(CPI*SPIt) | CEACn=BACn/ ( .8 CPI + .2 SPIt) | WS | WP | ACn | BACn | Esn | CVn | SVn | RVn
[36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[33 empty] | 2022-08-01 | 2022-08-05 | S32 | 1 | 0.047619 | 2330 | 2330 | 1807.9 | 0.77592 | 2409 | 2409 | 0.75048 | 0.77592 | 0.77592 | -601.1 | -522.1 | 0.96721 | -79 | 1 | 1.0087 | 1.3325 | 1.7173 | 1.3235 | 1.7173 | 1.3235 | 0.033646 | 0.026107 | 0.034787 | 1 | 0.036949 | -0.0086801 | -0.0075394 | -0.0011408
[33 empty] | 2022-08-08 | 2022-08-12 | S33 | 2 | 0.095238 | 2330 | 4660 | 4293 | 1.8425 | 2608 | 5017 | 0.85569 | 0.92124 | 0.92124 | -724 | -367 | 0.92884 | -357 | 1 | 1.0105 | 1.1686 | 1.2686 | 1.151 | 1.2686 | 1.151 | 0.067292 | 0.061993 | 0.072448 | 1 | 0.087738 | -0.010455 | -0.0052996 | -0.0051552
|  | Project Activities | [8 empty] | FROM | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-08-15 | 2022-08-19 | S34 | 3 | 0.14286 | 2330 | 6990 | 7643.71 | 3.1707 | 2700 | 7717 | 0.9905 | 1.0935 | 1.0569 | -73.29 | 653.71 | 0.90579 | -727 | 1 | 1.0011 | 1.0096 | 0.92325 | 0.98902 | 0.95524 | 0.99623 | 0.10094 | 0.11038 | 0.11144 | 1 | 0.15098 | -0.0010583 | 0.0094399 | -0.010498
|  | Start Date | End Date | Starting week number | Ending week number | FTEs | FTE figure | Weight | Budget x activity |  | TO | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-08-22 | 2022-08-26 | S35 | 4 | 0.19048 | 3830 | 10820 | 10379.42 | 3.885 | 3270 | 10987 | 0.9447 | 0.95928 | 0.97124 | -607.58 | -440.58 | 0.9848 | -167 | 1 | 1.0088 | 1.0585 | 1.1035 | 1.0553 | 1.0899 | 1.0526 | 0.15625 | 0.14988 | 0.15866 | 1 | 0.185 | -0.0087737 | -0.0063622 | -0.0024116
| Project 2 | 2022-08-02 | 2022-12-22 | 32 | 52 |  |  | 100% | overall budget - allocation plan | Scheduling | € | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | 2022-08-29 | 2022-09-02 | S36 | 5 | 0.2381 | 1830 | 12650 | 12010.13 | 4.6503 | 1088 | 12075 | 0.99463 | 0.94942 | 0.93007 | -64.87 | -639.87 | 1.0476 | 575 | 1 | 1.0009 | 1.0054 | 1.059 | 1.0146 | 1.081 | 1.0186 | 0.18267 | 0.17343 | 0.17437 | 1 | 0.22144 | -0.00093675 | -0.00924 | 0.0083032
| Testbook Design | 2022-08-02 | 2022-08-23 | 32 | 35 | 2/day | Test Analyst | 11.55% | 8000 | Testbook Design | 8000 | 2000 | 2000 | 2000 | 2000 | [17 empty] | 2022-09-05 | 2022-09-09 | S37 | 6 | 0.28571 | 1830 | 14480 | 12920.84 | 5.148 | 1216 | 13291 | 0.97215 | 0.89232 | 0.858 | -370.16 | -1559.16 | 1.0895 | 1189 | 1 | 1.0053 | 1.0286 | 1.1528 | 1.0458 | 1.1989 | 1.0534 | 0.2091 | 0.18658 | 0.19193 | 1 | 0.24514 | -0.0053453 | -0.022515 | 0.01717
| Data preparation | 2022-08-24 | 2022-09-07 | 35 | 37 | 1,5/day | Test Analyst; Software Tester | 6.498% | 4500 | Data preparation | 4500 |  |  |  | 1500 | 1500 | 1500 | [15 empty] | 2022-09-12 | 2022-09-16 | S38 | 7 | 0.33333 | 1330 | 15810 | 14776.55 | 6.223 | 1807 | 15098 | 0.97871 | 0.93463 | 0.889 | -321.45 | -1033.45 | 1.0472 | 712 | 1 | 1.0046 | 1.0218 | 1.0932 | 1.031 | 1.1493 | 1.0408 | 0.2283 | 0.21338 | 0.21802 | 1 | 0.29633 | -0.0046419 | -0.014923 | 0.010282
| Integration | 2022-09-12 | 2022-09-30 | 38 | 40 | 1/day | Software Tester | 4.332% | 3000 | Integration | 3000 | [6 empty] | 1000 | 1000 | 1000 | [12 empty] | 2022-09-19 | 2022-09-23 | S39 | 8 | 0.38095 | 1330 | 17140 | 17568.05 | 8.3218 | 1535 | 16633 | 1.0562 | 1.025 | 1.0402 | 935.05 | 428.05 | 1.0305 | 507 | 1 | 0.9865 | 0.94678 | 0.92371 | 0.95241 | 0.91016 | 0.94965 | 0.24751 | 0.25369 | 0.24019 | 1 | 0.39628 | 0.013503 | 0.0061812 | 0.0073213
| Execution | 2022-10-03 | 2022-11-24 | 41 | 48 | 3/day+0,5/week | Test Analyst; Software Tester; Test Manager | 36.56% | 25320 | Execution | 25320 | [9 empty] | 3165 | 3165 | 3165 | 3165 | 3165 | 3165 | 3165 | 3165 |  |  |  |  | 2022-09-26 | 2022-09-30 | S40 | 9 | 0.42857 | 1330 | 18470 | 18018.05 | 8.6602 | 1320 | 17953 | 1.0036 | 0.97553 | 0.96224 | 65.05 | -451.95 | 1.0288 | 517 | 1 | 0.99906 | 0.99639 | 1.0214 | 1.002 | 1.0355 | 1.0047 | 0.26671 | 0.26019 | 0.25925 | 1 | 0.41239 | 0.00093935 | -0.0065264 | 0.0074657
| Retest | 2022-11-25 | 2022-12-09 | 48 | 50 | 1/day | Software Tester | 4.332% | 3000 | Retest | 3000 | [16 empty] | 1000 | 1000 | 1000 |  |  | 2022-10-03 | 2022-10-07 | S41 | 10 | 0.47619 | 4495 | 22965 | 20434.05 | 9.4369 | 3656 | 21609 | 0.94563 | 0.88979 | 0.94369 | -1174.95 | -2530.95 | 1.0628 | 1356 | 1 | 1.017 | 1.0575 | 1.1885 | 1.0701 | 1.1206 | 1.0579 | 0.33162 | 0.29508 | 0.31204 | 1 | 0.44938 | -0.016967 | -0.036548 | 0.019581
| Management | 2022-08-02 | 2022-12-22 | 32 | 52 | 1/week | Test Manager | 10.01% | 6930 | Management | 6930 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 2022-10-10 | 2022-10-14 | S42 | 11 | 0.52381 | 4495 | 27460 | 22700.05 | 9.9411 | 2662 | 24271 | 0.93527 | 0.82666 | 0.90373 | -1570.95 | -4759.95 | 1.1314 | 3189 | 1 | 1.0227 | 1.0692 | 1.2934 | 1.0946 | 1.1831 | 1.0765 | 0.39653 | 0.3278 | 0.35048 | 1 | 0.47338 | -0.022685 | -0.068736 | 0.046051
| ALM maintenance | 2022-11-25 | 2022-12-09 | 48 | 50 | 1,5/day | Software Tester; Test Analyst | 6.498% | 4500 | ALM maintenance | 4500 | [16 empty] | 1500 | 1500 | 1500 |  |  | 2022-10-17 | 2022-10-21 | S43 | 12 | 0.57143 | 4495 | 31955 | 25219.25 | 10.5015 | 3192 | 27463 | 0.9183 | 0.78921 | 0.87513 | -2243.75 | -6735.75 | 1.1636 | 4492 | 1 | 1.0324 | 1.089 | 1.3798 | 1.1205 | 1.2444 | 1.0993 | 0.46144 | 0.36418 | 0.39658 | 1 | 0.50007 | -0.032401 | -0.097267 | 0.064866
| Reporting activities | 2022-10-03 | 2022-12-09 | 41 | 50 | 1/day | Test Analyst | 14.44% | 10000 | Reporting activities | 10000 | [9 empty] | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  |  | 2022-10-24 | 2022-10-28 | S44 | 13 | 0.61905 | 4495 | 36450 | 27232.05 | 10.9493 | 3238 | 30701 | 0.88701 | 0.74711 | 0.84225 | -3468.95 | -9217.95 | 1.1873 | 5749 | 1 | 1.0501 | 1.1274 | 1.509 | 1.1641 | 1.3385 | 1.1389 | 0.52635 | 0.39324 | 0.44334 | 1 | 0.52139 | -0.050093 | -0.13311 | 0.083018
| UAT support | 2022-12-12 | 2022-12-22 | 51 | 52 | 2/day | Software Tester; Test Analyst | 5.776% | 4000 | UAT support | 4000 | [19 empty] | 2000 | 2000 | 2022-10-31 | 2022-11-04 | S45 | 14 | 0.66667 | 4495 | 40945 | 30548.2 | 11.687 | 3812 | 34513 | 0.88512 | 0.74608 | 0.83479 | -3964.8 | -10396.8 | 1.1864 | 6432 | 1 | 1.0573 | 1.1298 | 1.5143 | 1.1664 | 1.3534 | 1.1428 | 0.59126 | 0.44113 | 0.49838 | 1 | 0.55653 | -0.057253 | -0.15013 | 0.092881
[11 empty] | 69250 | 2330 | 2330 | 2330 | 3830 | 1830 | 1830 | 1330 | 1330 | 1330 | 4495 | 4495 | 4495 | 4495 | 4495 | 4495 | 4495 | 6995 | 3830 | 3830 | 2330 | 2330 | 2022-11-07 | 2022-11-11 | S46 | 15 | 0.71429 | 4495 | 45440 | 35439.5 | 12.7752 | 4336 | 38849 | 0.91224 | 0.77992 | 0.85168 | -3409.5 | -10000.5 | 1.1697 | 6591 | 1 | 1.0492 | 1.0962 | 1.4055 | 1.129 | 1.2871 | 1.111 | 0.65617 | 0.51176 | 0.561 | 1 | 0.60834 | -0.049235 | -0.14441 | 0.095177
[10 empty] | Contingency up to the project type | 2850 | [21 empty] | 2022-11-14 | 2022-11-18 | S47 | 16 | 0.7619 | 4495 | 49935 | 41436.9 | 14.1094 | 4247 | 43096 | 0.9615 | 0.82982 | 0.88184 | -1659.1 | -8498.1 | 1.1587 | 6839 | 1 | 1.024 | 1.04 | 1.2533 | 1.0693 | 1.1794 | 1.0576 | 0.72108 | 0.59837 | 0.62232 | 1 | 0.67188 | -0.023958 | -0.12272 | 0.098758
[10 empty] | >10%--> highly risk project | [22 empty] | 2022-11-21 | 2022-11-25 | S48 | 17 | 0.80952 | 6995 | 56930 | 55531 | 16.8 | 5208 | 48304 | 1.1496 | 0.97543 | 0.98824 | 7227 | -1399 | 1.1786 | 8626 | 1 | 0.89564 | 0.86986 | 0.89177 | 0.89704 | 0.88021 | 0.89498 | 0.82209 | 0.80189 | 0.69753 | 1 | 0.8 | 0.10436 | -0.020202 | 0.12456
[10 empty] | btw 5% and 10% --> medium risk project | [22 empty] | 2022-11-28 | 2022-12-02 | S49 | 18 | 0.85714 | 3830 | 60760 | 58782.5 | 17.4837 | 3626 | 51930 | 1.132 | 0.96745 | 0.97132 | 6852.5 | -1977.5 | 1.17 | 8830 | 1 | 0.90105 | 0.88343 | 0.91315 | 0.90987 | 0.90952 | 0.90923 | 0.8774 | 0.84884 | 0.74989 | 1 | 0.83256 | 0.098953 | -0.028556 | 0.12751
[10 empty] | <5% --> low risk project | [22 empty] | 2022-12-05 | 2022-12-09 | S50 | 19 | 0.90476 | 3830 | 64590 | 64229.1 | 18.9058 | 2412 | 54342 | 1.1819 | 0.99441 | 0.99504 | 9887.1 | -360.9 | 1.1886 | 10248 | 1 | 0.85723 | 0.84607 | 0.85082 | 0.87379 | 0.85028 | 0.8737 | 0.93271 | 0.9275 | 0.78472 | 1 | 0.90027 | 0.14277 | -0.0052116 | 0.14799
ACTUAL COSTS | [32 empty] | 2022-12-12 | 2022-12-16 | S51 | 20 | 0.95238 | 2330 | 66920 | 66103.5 | 19.6496 | 2620 | 56962 | 1.1605 | 0.9878 | 0.98248 | 9141.5 | -816.5 | 1.1748 | 9958 | 1 | 0.86799 | 0.86171 | 0.87235 | 0.88814 | 0.87708 | 0.88898 | 0.96635 | 0.95456 | 0.82256 | 1 | 0.93569 | 0.13201 | -0.011791 | 0.1438
[33 empty] | 2022-12-19 | 2022-12-23 | S52 | 21 | 1 | 2330 | 69250 | 69250 | 21 | 1610 | 58572 | 1.1823 | 1 | 1 | 10678 | 0 | 1.1823 | 10678 | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | #VALUE! | FINE | FINE
[11 empty] | Price List €/h | 11
[11 empty] | FROM | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Software Tester 1 (stage) |  | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 131 | S35: 40; S36: 40; S37: 40; S38: 3; S39: 8
[10 empty] | Integration | 124 | S38: 40; S39: 44; S40: 40
[10 empty] | Execution | 265 | S41: 32; S42: 16; S43: 40; S44: 45; S45: 12; S46: 40; S47: 40; S48: 40
[10 empty] | Retest | 128 | S48: 40; S49: 40; S50: 32; S51: 16
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 86 | S51: 40; S52: 46
[11 empty] | 734 | 0 | 0 | 0 | 40 | 40 | 40 | 43 | 52 | 40 | 32 | 16 | 40 | 45 | 12 | 40 | 40 | 80 | 40 | 32 | 56 | 46
[11 empty] | Price List €/h | S32: 22
[11 empty] | FROM | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Software Tester 2 (apprenticeship) |  | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 120 | S38: 40; S39: 40; S40: 40
[10 empty] | Integration | 0
[10 empty] | Execution | 261 | S41: 40; S42: 13; S43: 32; S44: 24; S45: 32; S46: 40; S47: 40; S48: 40
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 124 | S48: 40; S49: 44; S50: 32; S51: 8
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 13 | 32 | 24 | 32 | 40 | 40 | 80 | 44 | 32 | 8 | 0
[11 empty] | Price List €/h | S32: 28
[11 empty] | FROM | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Test Analyst 1 |  | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 152 | S32: 40; S33: 40; S34: 40; S35: 32
[10 empty] | Data preparation | 38 | S35: 10; S36: 10; S37: 8; S38: 8; S39: 2
[10 empty] | Integration | 0
[10 empty] | Execution | 324 | S41: 40; S42: 40; S43: 44; S44: 40; S45: 40; S46: 48; S47: 40; S48: 32
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 64 | S51: 40; S52: 24
[11 empty] | 578 | 40 | 40 | 40 | 42 | 10 | 8 | 8 | 2 | 0 | 40 | 40 | 44 | 40 | 40 | 48 | 40 | 32 | 0 | 0 | 40 | 24
[11 empty] | Price List €/h | S32: 28
[11 empty] | FROM | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Test Analyst 2 |  | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 154 | S32: 30; S33: 40; S34: 40; S35: 44
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 82 | S48: 24; S49: 16; S50: 20; S51: 22
[10 empty] | Reporting activities | 268 | S41: 40; S42: 32; S43: 16; S44: 8; S45: 40; S46: 40; S47: 40; S48: 16; S49: 24; S50: 12
[10 empty] | UAT support | 0
[11 empty] | 504 | 30 | 40 | 40 | 44 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 16 | 8 | 40 | 40 | 40 | 40 | 40 | 32 | 22 | 0
[11 empty] | Price List €/h | S32: 46
[11 empty] | FROM | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Test Manager |  | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 54 | S41: 4; S42: 4; S43: 8; S44: 8; S45: 8; S46: 4; S47: 4; S48: 4; S49: 8; S50: 2
[10 empty] | Retest | 0
[10 empty] | Management | 119 | 8 | 8 | 10 | 8 | 8 | 12 | 5 | [5 empty] | 8 | 8 | 8 | 8 | 8 | 10 | 8 | 2
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 173 | 8 | 8 | 10 | 8 | 8 | 12 | 5 | 0 | 0 | 4 | 4 | 8 | 16 | 16 | 12 | 12 | 12 | 18 | 10 | 2 | 0
[11 empty] | Price List €/h | S32: 27
[11 empty] | FROM | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | PMO |  | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 42 | S32: 3; S35: 2; S39: 1; S44: 5; S47: 5; S49: 10; S52: 16
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 42 | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 10 | 0 | 0 | 16
[11 empty] | FROM | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Actual Total Costs | 58572 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 8568 | 1960 | 2240 | 2240 | 2128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Data preparation | 5145 | 0 | 0 | 0 | 720 | 720 | 664 | 1137 | 1024 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Integration | 1364 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 484 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Execution | 20213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2536 | 1766 | 2744 | 2511 | 2324 | 2848 | 2624 | 2400 | 368 | 92 | 0 | 0
[10 empty] | Retest | 1408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 440 | 352 | 176 | 0
[10 empty] | Management | 6608 | 449 | 368 | 460 | 422 | 368 | 552 | 230 | 27 | 0 | 0 | 0 | 0 | 503 | 368 | 368 | 503 | 368 | 730 | 368 | 92 | 432
[10 empty] | ALM maintenance | 5024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552 | 1416 | 1264 | 792 | 0
[10 empty] | Reporting activities | 7504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120 | 896 | 448 | 224 | 1120 | 1120 | 1120 | 448 | 672 | 336 | 0 | 0
[10 empty] | UAT support | 2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560 | 1178
[12 empty] | 2409 | 2608 | 2700 | 3270 | 1088 | 1216 | 1807 | 1535 | 1320 | 3656 | 2662 | 3192 | 3238 | 3812 | 4336 | 4247 | 5208 | 3626 | 2412 | 2620 | 1610
EARNED VALUE
[11 empty] | FROM | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | %Progress | 100% | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 100% | 20% | 45% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Data preparation | 100% | 0% | 0% | 5% | 23% | 52% | 65% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Integration | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 6% | 80% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Execution | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 10% | 16% | 20% | 26% | 40% | 57% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Retest | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17% | 55% | 96% | 100% | 100%
[10 empty] | Management | 100% | 3% | 10% | 14.7% | 19.4% | 24.1% | 28.8% | 33.5% | 38.5% | 38.5% | 38.5% | 38.5% | 38.5% | 38.5% | 50% | 55% | 65% | 70% | 75% | 87% | 95% | 100%
[10 empty] | ALM maintenance | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 47% | 100% | 100% | 100%
[10 empty] | Reporting activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100% | 100% | 100%
[10 empty] | UAT support | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100%
[12 empty] | 2.611% | 6.199% | 11.04% | 14.99% | 17.34% | 18.66% | 21.34% | 25.37% | 26.02% | 29.51% | 32.78% | 36.42% | 39.32% | 44.11% | 51.18% | 59.84% | 80.19% | 84.88% | 92.75% | 95.46% | 100%
[11 empty] | FROM | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | EV | 69250 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 8000 | 1600 | 3600 | 6400 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
[10 empty] | Data preparation | 4500 | 0 | 0 | 225 | 1035 | 2340 | 2925 | 4275 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500
[10 empty] | Integration | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 2400 | 2850 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000
[10 empty] | Execution | 25320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1266 | 2532 | 4051.2 | 5064 | 6583.2 | 10128 | 14432.4 | 25320 | 25320 | 25320 | 25320 | 25320
[10 empty] | Retest | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 1650 | 2880 | 3000 | 3000
[10 empty] | Management | 6930 | 207.9 | 693 | 1018.71 | 1344.42 | 1670.13 | 1995.84 | 2321.55 | 2668.05 | 2668.05 | 2668.05 | 2668.05 | 2668.05 | 2668.05 | 3465 | 3811.5 | 4504.5 | 4851 | 5197.5 | 6029.1 | 6583.5 | 6930
[10 empty] | ALM maintenance | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 2115 | 4500 | 4500 | 4500
[10 empty] | Reporting activities | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 2000 | 3000 | 4000 | 5000 | 6000 | 7000 | 8000 | 9000 | 10000 | 10000 | 10000
[10 empty] | UAT support | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4000
[12 empty] | 1807.9 | 4293 | 7643.71 | 10379.42 | 12010.13 | 12920.84 | 14776.55 | 17568.05 | 18018.05 | 20434.05 | 22700.05 | 25219.25 | 27232.05 | 30548.2 | 35439.5 | 41436.9 | 55531 | 58782.5 | 64229.1 | 66103.5 | 69250
Formulas:
Test Manager = [Test Manager, row above]+4
Bank 1 = MIN([Bank 1, row below]:C30)

## Project_3
PROJECT OVERVIEW
| Project Name | Project 3 |  | Estimation | yes
| Responsible | Test Manager Blue Team |  | Sceduling | yes | [17 empty] | Assumptions | [32 empty] | AC(AD) | AC(33) |  | 145814 |  | Acn(ADn=1) | 0.90509
| Client | Bank 1 | [5 empty] | Business Unit | Financial Services | [13 empty] | Client charge | Test Manager | 330
| Area | Crediti | [5 empty] | Prectice | Testing | [13 empty] | €/gg | Tester | 200
| Resource number | 9 | [5 empty] | Sub-practice level 1 | Area Operations | [46 empty] | ADn | 1
| Starting date | 2022-07-12 | [5 empty] | Sub-practice level 2 | Credit Management
| Release (Go live) | 2023-02-28 | [5 empty] | Sub-practice level 3 | Credit Perfectioning | [36 empty] | Project Planned Elapsed time
| Main Activities | Desing, DP, Execution, Management and UAT | [5 empty] | Activity Description | Activities involved: credit guarantor document fulfillments necessary for supporing the credit concession; perfectioning of these warranties in terms of date, information insertion, confirmation receipt and transmission to the perfectioned warranties archive. | [36 empty] | 33 | weeks
| %completion | 100%
| Next Milestone | N/A
| TM Estimate Name | Estimate 3: Project_3_.xls
| Estimate Budget | 167890
BASELINE | [46 empty] | Week | Time Unit | TPn | BASELINE | BCWS | EV | ES | Actual Costs | ACWP | CPI | SPI | SPIt | CV | SV | RFI | RV | CEACn=BACn | CEACn=BACn-CVn | CEACn=BCAn/CPI | CEACn=BACn/(CPI*SPI) | CEACn=BACn/ ( .8 CPI + .2 SPI) | CEACn=BACn/(CPI*SPIt) | CEACn=BACn/ ( .8 CPI + .2 SPIt) | WS | WP | ACn | BACn | Esn | CVn | SVn | RVn
[48 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[45 empty] | 2022-07-11 | 2022-07-15 | S29 | 1 | 0.030303 | 3660 | 3660 | 5133.6 | 1.4026 | 4626 | 4626 | 1.1097 | 1.4026 | 1.4026 | 507.6 | 1473.6 | 0.79118 | -966 | 1 | 0.99685 | 0.90112 | 0.64245 | 0.85594 | 0.64245 | 0.85594 | 0.022718 | 0.031865 | 0.028714 | 1 | 0.042504 | 0.0031507 | 0.0091468 | -0.0059961
[45 empty] | 2022-07-18 | 2022-07-22 | S30 | 2 | 0.060606 | 3660 | 7320 | 7027.2 | 1.92 | 4151 | 8777 | 0.80064 | 0.96 | 0.96 | -1749.8 | -292.8 | 0.834 | -1457 | 1 | 1.0109 | 1.249 | 1.301 | 1.2012 | 1.301 | 1.2012 | 0.045436 | 0.043619 | 0.05448 | 1 | 0.058182 | -0.010861 | -0.0018174 | -0.0090438
|  | Project Activities | [8 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2022-07-25 | 2022-07-29 | S31 | 3 | 0.090909 | 3660 | 10980 | 11980.8 | 3.2734 | 4689 | 13466 | 0.88971 | 1.0911 | 1.0911 | -1485.2 | 1000.8 | 0.81539 | -2486 | 1 | 1.0092 | 1.124 | 1.0301 | 1.0753 | 1.0301 | 1.0753 | 0.068154 | 0.074366 | 0.083585 | 1 | 0.099195 | -0.0092188 | 0.0062121 | -0.015431
|  | Start Date | End Date | Starting week number | Ending week number | FTEs | FTE figure | Weight | Budget x activity |  | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2022-08-01 | 2022-08-05 | S32 | 4 | 0.12121 | 3660 | 14640 | 15134.4 | 4.1351 | 4190 | 17656 | 0.85718 | 1.0338 | 1.0338 | -2521.6 | 494.4 | 0.82918 | -3016 | 1 | 1.0157 | 1.1666 | 1.1285 | 1.1204 | 1.1285 | 1.1204 | 0.090872 | 0.093941 | 0.10959 | 1 | 0.12531 | -0.015652 | 0.0030688 | -0.018721
| Project 3 | 2022-07-12 | 2023-02-24 | 29 | 8 |  |  | 100% | overall budget - allocation plan | Scheduling | € | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | 2022-08-08 | 2022-08-12 | S33 | 5 | 0.15152 | 3660 | 18300 | 19188 | 5.1569 | 4806 | 22462 | 0.85424 | 1.0485 | 1.0314 | -3274 | 888 | 0.81471 | -4162 | 1 | 1.0203 | 1.1706 | 1.1165 | 1.1197 | 1.135 | 1.124 | 0.11359 | 0.1191 | 0.13942 | 1 | 0.15627 | -0.020322 | 0.0055119 | -0.025834
| Testbook Design | 2022-07-12 | 2022-08-15 | 29 | 34 | 3/day | Test Analyst | 11.17% | 18000 | Testbook Design | 18000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | [27 empty] | 2022-08-15 | 2022-08-19 | S34 | 6 | 0.18182 | 5660 | 23960 | 22601.6 | 5.76 | 5607 | 28069 | 0.80522 | 0.94331 | 0.96 | -5467.4 | -1358.4 | 0.85361 | -4109 | 1 | 1.0339 | 1.2419 | 1.3165 | 1.2007 | 1.2936 | 1.1959 | 0.14872 | 0.14029 | 0.17423 | 1 | 0.17455 | -0.033937 | -0.0084318 | -0.025505
| Data preparation | 2022-08-16 | 2022-09-09 | 34 | 37 | 2/day | Test Analyst; Software Tester | 4.966% | 8000 | Data preparation | 8000 | [5 empty] | 2000 | 2000 | 2000 | 2000 | [24 empty] | 2022-08-22 | 2022-08-26 | S35 | 7 | 0.21212 | 2660 | 26620 | 24035.2 | 6.0283 | 3302 | 31371 | 0.76616 | 0.9029 | 0.86118 | -7335.8 | -2584.8 | 0.84855 | -4751 | 1 | 1.0455 | 1.3052 | 1.4456 | 1.2602 | 1.5156 | 1.2736 | 0.16523 | 0.14919 | 0.19472 | 1 | 0.18267 | -0.045534 | -0.016044 | -0.02949
| Integration | 2022-09-12 | 2022-09-30 | 38 | 40 | 1,5/day | Software Tester | 2.793% | 4500 | Integration | 4500 | [9 empty] | 1500 | 1500 | 1500 | [21 empty] | 2022-08-29 | 2022-09-02 | S36 | 8 | 0.24242 | 2660 | 29280 | 28668.8 | 7.7702 | 2920 | 34291 | 0.83604 | 0.97913 | 0.97128 | -5622.2 | -611.2 | 0.85387 | -5011 | 1 | 1.0349 | 1.1961 | 1.2216 | 1.1565 | 1.2315 | 1.1586 | 0.18174 | 0.17795 | 0.21285 | 1 | 0.23546 | -0.034898 | -0.0037938 | -0.031104
| Execution | 2022-10-03 | 2022-11-30 | 41 | 49 | 6/day+0,5/week | Test Analyst; Software Tester; Test Manager | 34.44% | 55485 | Execution | 55485 | [12 empty] | 6165 | 6165 | 6165 | 6165 | 6165 | 6165 | 6165 | 6165 | 6165 | [12 empty] | 2022-09-05 | 2022-09-09 | S37 | 9 | 0.27273 | 2660 | 31940 | 31702.4 | 8.9107 | 3329 | 37620 | 0.8427 | 0.99256 | 0.99008 | -5917.6 | -237.6 | 0.84902 | -5680 | 1 | 1.0367 | 1.1867 | 1.1956 | 1.1459 | 1.1986 | 1.1466 | 0.19826 | 0.19678 | 0.23351 | 1 | 0.27002 | -0.036731 | -0.0014748 | -0.035257
| Retest | 2022-12-01 | 2022-12-23 | 49 | 52 | 3/day | Software Tester | 7.449% | 12000 | Retest | 12000 | [20 empty] | 3000 | 3000 | 3000 | 3000 | [9 empty] | 2022-09-12 | 2022-09-16 | S38 | 10 | 0.30303 | 2160 | 34100 | 34586 | 10.225 | 880 | 38500 | 0.89834 | 1.0143 | 1.0225 | -3914 | 486 | 0.88571 | -4400 | 1 | 1.0243 | 1.1132 | 1.0975 | 1.0852 | 1.0887 | 1.0832 | 0.21166 | 0.21468 | 0.23897 | 1 | 0.30985 | -0.024295 | 0.0030167 | -0.027311
| Management | 2022-07-12 | 2023-02-24 | 29 | 8 | 2/week | Test Manager | 13.11% | 21120 | Management | 21120 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 |  | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 2022-09-19 | 2022-09-23 | S39 | 11 | 0.33333 | 2160 | 36260 | 36569.6 | 11.1433 | 1644 | 40144 | 0.91096 | 1.0085 | 1.013 | -3574.4 | 309.6 | 0.90325 | -3884 | 1 | 1.0222 | 1.0977 | 1.0884 | 1.0747 | 1.0836 | 1.0737 | 0.22507 | 0.22699 | 0.24918 | 1 | 0.33768 | -0.022187 | 0.0019217 | -0.024109
| ALM maintenance | 2022-12-01 | 2022-12-23 | 49 | 52 | 1,5/day | Software Tester | 3.724% | 6000 | ALM maintenance | 6000 | [24 empty] | 1500 | 1500 | 1500 | 1500 | [5 empty] | 2022-09-26 | 2022-09-30 | S40 | 12 | 0.36364 | 2160 | 38420 | 38103.2 | 11.8533 | 1393 | 41537 | 0.91733 | 0.99175 | 0.98778 | -3433.8 | -316.8 | 0.92496 | -3117 | 1 | 1.0213 | 1.0901 | 1.0992 | 1.0727 | 1.1036 | 1.0736 | 0.23848 | 0.23651 | 0.25783 | 1 | 0.35919 | -0.021314 | -0.0019664 | -0.019348
| Reporting activities | 2022-10-03 | 2022-12-23 | 41 | 52 | 1/day | Test Analyst | 7.449% | 12000 | Reporting activities | 12000 | [12 empty] | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | [9 empty] | 2022-10-03 | 2022-10-07 | S41 | 13 | 0.39394 | 7825 | 46245 | 42111.05 | 12.4717 | 7000 | 48537 | 0.86761 | 0.91061 | 0.95936 | -6425.95 | -4133.95 | 0.95278 | -2292 | 1 | 1.0399 | 1.1526 | 1.2657 | 1.1413 | 1.2014 | 1.1287 | 0.28705 | 0.26139 | 0.30128 | 1 | 0.37793 | -0.039887 | -0.02566 | -0.014227
| UAT support | 2023-01-02 | 2023-02-24 | 1 | 8 | 3/day | Test Analyst; Software Tester | 14.9% | 24000 | UAT support | 24000 | [25 empty] | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 2022-10-10 | 2022-10-14 | S42 | 14 | 0.42424 | 7825 | 54070 | 49170.575 | 13.3739 | 7428 | 55965 | 0.8786 | 0.90939 | 0.95528 | -6794.425 | -4899.425 | 0.96614 | -1895 | 1 | 1.0422 | 1.1382 | 1.2516 | 1.1303 | 1.1915 | 1.1187 | 0.33562 | 0.30521 | 0.34738 | 1 | 0.40527 | -0.042174 | -0.030411 | -0.011763
[11 empty] | 161105 | 3660 | 3660 | 3660 | 3660 | 3660 | 5660 | 2660 | 2660 | 2660 | 2160 | 2160 | 2160 | 7825 | 7825 | 7825 | 7825 | 7825 | 7825 | 7825 | 7825 | 10825 | 4660 | 4660 | 4660 | 1500 | 5160 | 5160 | 5160 | 3660 | 3660 | 3660 | 3660 | 3660 | 2022-10-17 | 2022-10-21 | S43 | 15 | 0.45455 | 7825 | 61895 | 65662.55 | 15.4815 | 6887 | 62852 | 1.0447 | 1.0609 | 1.0321 | 2810.55 | 3767.55 | 0.98477 | -957 | 1 | 0.98255 | 0.9572 | 0.90228 | 0.95425 | 0.92743 | 0.95951 | 0.38419 | 0.40758 | 0.39013 | 1 | 0.46914 | 0.017445 | 0.023386 | -0.0059402
[10 empty] | Contingency up to the project type | 6785 | [33 empty] | 2022-10-24 | 2022-10-28 | S44 | 16 | 0.48485 | 7825 | 69720 | 73554.35 | 16.49 | 6766 | 69618 | 1.0565 | 1.055 | 1.0306 | 3936.35 | 3834.35 | 1.0015 | 102 | 1 | 0.97557 | 0.94648 | 0.89714 | 0.94676 | 0.91836 | 0.95115 | 0.43276 | 0.45656 | 0.43213 | 1 | 0.4997 | 0.024433 | 0.0238 | 0.00063313
[10 empty] | >10%--> highly risk project | [34 empty] | 2022-10-31 | 2022-11-04 | S45 | 17 | 0.51515 | 7825 | 77545 | 77007.35 | 16.9313 | 5036 | 74654 | 1.0315 | 0.99307 | 0.99596 | 2353.35 | -537.65 | 1.0387 | 2891 | 1 | 0.98539 | 0.96944 | 0.97621 | 0.97672 | 0.97337 | 0.97617 | 0.48133 | 0.47799 | 0.46339 | 1 | 0.51307 | 0.014608 | -0.0033373 | 0.017945
[10 empty] | btw 5% and 10% --> medium risk project | [34 empty] | 2022-11-07 | 2022-11-11 | S46 | 18 | 0.54545 | 7825 | 85370 | 88228.25 | 18.3653 | 7106 | 81760 | 1.0791 | 1.0335 | 1.0203 | 6468.25 | 2858.25 | 1.0442 | 3610 | 1 | 0.95985 | 0.92669 | 0.89667 | 0.93459 | 0.90826 | 0.9369 | 0.5299 | 0.54764 | 0.5075 | 1 | 0.55652 | 0.040149 | 0.017742 | 0.022408
[10 empty] | <5% --> low risk project | [34 empty] | 2022-11-14 | 2022-11-18 | S47 | 19 | 0.57576 | 7825 | 93195 | 89461.85 | 18.5229 | 5940 | 87700 | 1.0201 | 0.95994 | 0.97489 | 1761.85 | -3733.15 | 1.0627 | 5495 | 1 | 0.98906 | 0.98031 | 1.0212 | 0.992 | 1.0056 | 0.98907 | 0.57847 | 0.5553 | 0.54437 | 1 | 0.5613 | 0.010936 | -0.023172 | 0.034108
ACTUAL COSTS | [44 empty] | 2022-11-21 | 2022-11-25 | S48 | 20 | 0.60606 | 7825 | 101020 | 97683.95 | 19.5737 | 6210 | 93910 | 1.0402 | 0.96698 | 0.97868 | 3773.95 | -3336.05 | 1.0757 | 7110 | 1 | 0.97657 | 0.96137 | 0.9942 | 0.97509 | 0.98231 | 0.97287 | 0.62704 | 0.60634 | 0.58291 | 1 | 0.59314 | 0.023425 | -0.020707 | 0.044133
[45 empty] | 2022-11-28 | 2022-12-02 | S49 | 21 | 0.63636 | 10825 | 111845 | 106236.35 | 20.4819 | 6866 | 100776 | 1.0542 | 0.94985 | 0.97533 | 5460.35 | -5608.65 | 1.1098 | 11069 | 1 | 0.96611 | 0.9486 | 0.99868 | 0.96776 | 0.9726 | 0.96301 | 0.69424 | 0.65942 | 0.62553 | 1 | 0.62066 | 0.033893 | -0.034814 | 0.068707
[45 empty] | 2022-12-05 | 2022-12-09 | S50 | 22 | 0.66667 | 4660 | 116505 | 114324.2 | 21.532 | 3460 | 104236 | 1.0968 | 0.98128 | 0.97873 | 10088.2 | -2180.8 | 1.1177 | 12269 | 1 | 0.93738 | 0.91176 | 0.92915 | 0.93137 | 0.93157 | 0.93182 | 0.72316 | 0.70963 | 0.64701 | 1 | 0.65249 | 0.062619 | -0.013537 | 0.076155
[11 empty] | Price List €/h | 11 | [32 empty] | 2022-12-12 | 2022-12-16 | S51 | 23 | 0.69697 | 4660 | 121165 | 121437.8 | 23.0585 | 4186 | 108422 | 1.12 | 1.0023 | 1.0025 | 13015.8 | 272.8 | 1.1175 | 12743 | 1 | 0.91921 | 0.89282 | 0.89081 | 0.912 | 0.89055 | 0.91195 | 0.75209 | 0.75378 | 0.67299 | 1 | 0.69874 | 0.080791 | 0.0016933 | 0.079097
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2022-12-19 | 2022-12-23 | S52 | 24 | 0.72727 | 4660 | 125825 | 125191.4 | 23.864 | 3688 | 112110 | 1.1167 | 0.99496 | 0.99433 | 13081.4 | -633.6 | 1.1223 | 13715 | 1 | 0.9188 | 0.89551 | 0.90004 | 0.91547 | 0.90061 | 0.91557 | 0.78101 | 0.77708 | 0.69588 | 1 | 0.72315 | 0.081198 | -0.0039328 | 0.085131
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2022-12-26 | 2022-12-30 | S53 | 25 | 0.75758 | 1500 | 127325 | 126511.4 | 24.4576 | 792 | 112902 | 1.1205 | 0.99361 | 0.9783 | 13609.4 | -813.6 | 1.1277 | 14423 | 1 | 0.91552 | 0.89243 | 0.89816 | 0.91311 | 0.91222 | 0.91567 | 0.79032 | 0.78527 | 0.7008 | 1 | 0.74114 | 0.084475 | -0.0050501 | 0.089525
[10 empty] | Software Tester 1 (stage) |  | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | 2023-01-02 | 2023-01-06 | S1 | 26 | 0.78788 | 5160 | 132485 | 135905 | 26.6628 | 3954 | 116856 | 1.163 | 1.0258 | 1.0255 | 19049 | 3420 | 1.1337 | 15629 | 1 | 0.88176 | 0.85984 | 0.8382 | 0.88061 | 0.83846 | 0.88066 | 0.82235 | 0.84358 | 0.72534 | 1 | 0.80796 | 0.11824 | 0.021228 | 0.097011
[10 empty] | Testbook Design | 0 | [33 empty] | 2023-01-09 | 2023-01-13 | S2 | 27 | 0.81818 | 5160 | 137645 | 140558.6 | 27.5647 | 4500 | 121356 | 1.1582 | 1.0212 | 1.0209 | 19202.6 | 2913.6 | 1.1342 | 16289 | 1 | 0.88081 | 0.86338 | 0.84549 | 0.88431 | 0.8457 | 0.88435 | 0.85438 | 0.87247 | 0.75327 | 1 | 0.83529 | 0.11919 | 0.018085 | 0.10111
[10 empty] | Data preparation | 0 | [33 empty] | 2023-01-16 | 2023-01-20 | S3 | 28 | 0.84848 | 5160 | 142805 | 145092.2 | 28.6249 | 4698 | 126054 | 1.151 | 1.016 | 1.0223 | 19038.2 | 2287.2 | 1.1329 | 16751 | 1 | 0.88183 | 0.86879 | 0.85509 | 0.88966 | 0.84982 | 0.88866 | 0.88641 | 0.90061 | 0.78243 | 1 | 0.86742 | 0.11817 | 0.014197 | 0.10398
[10 empty] | Integration | 115 | S38: 40; S39: 40; S40: 35 | 2023-01-23 | 2023-01-27 | S4 | 29 | 0.87879 | 3660 | 146465 | 148125.8 | 29.4538 | 3504 | 129558 | 1.1433 | 1.0113 | 1.0156 | 18567.8 | 1660.8 | 1.1305 | 16907 | 1 | 0.88475 | 0.87465 | 0.86484 | 0.89532 | 0.86117 | 0.89463 | 0.90913 | 0.91944 | 0.80418 | 1 | 0.89254 | 0.11525 | 0.010309 | 0.10494
[10 empty] | Execution | 330 | S41: 32; S42: 40; S43: 36; S44: 40; S45: 24; S46: 40; S47: 40; S48: 40; S49: 38 | 2023-01-30 | 2023-02-03 | S5 | 30 | 0.90909 | 3660 | 150125 | 152359.4 | 30.6105 | 3264 | 132822 | 1.1471 | 1.0149 | 1.0203 | 19537.4 | 2234.4 | 1.1303 | 17303 | 1 | 0.87873 | 0.87177 | 0.85898 | 0.89234 | 0.85438 | 0.89147 | 0.93185 | 0.94571 | 0.82444 | 1 | 0.92759 | 0.12127 | 0.013869 | 0.1074
[10 empty] | Retest | 140 | S48: 8; S49: 18; S50: 32; S51: 42; S52: 40 | 2023-02-06 | 2023-02-10 | S6 | 31 | 0.93939 | 3660 | 153785 | 155393 | 31.4393 | 3504 | 136326 | 1.1399 | 1.0105 | 1.0142 | 19067 | 1608 | 1.1281 | 17459 | 1 | 0.88165 | 0.8773 | 0.86822 | 0.89768 | 0.86504 | 0.89708 | 0.95456 | 0.96454 | 0.84619 | 1 | 0.95271 | 0.11835 | 0.0099811 | 0.10837
[10 empty] | Management | 0 | [33 empty] | 2023-02-13 | 2023-02-17 | S7 | 32 | 0.9697 | 3660 | 157445 | 158426.6 | 32.2682 | 4598 | 140924 | 1.1242 | 1.0062 | 1.0084 | 17502.6 | 981.6 | 1.1172 | 16521 | 1 | 0.89136 | 0.88952 | 0.88401 | 0.90859 | 0.88213 | 0.90824 | 0.97728 | 0.98337 | 0.87473 | 1 | 0.97782 | 0.10864 | 0.0060929 | 0.10255
[10 empty] | ALM maintenance | 97 | S53: 24; S1: 19; S2: 24; S3: 30 | 2023-02-20 | 2023-02-24 | S8 | 33 | 1 | 3660 | 161105 | 161105 | 33 | 4890 | 145814 | 1.1049 | 1 | 1 | 15291 | 0 | 1.1049 | 15291 | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 35 | 32 | 40 | 36 | 40 | 24 | 40 | 40 | 48 | 56 | 32 | 42 | 40 | 24 | 19 | 24 | 30 | 0 | 0 | 0 | 0 | 0
[11 empty] | Price List €/h | S29: 22
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24
[10 empty] | Software Tester 2 (apprenticeship) |  | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 100 | S38: 20; S39: 20; S40: 20; S41: 20; S42: 20
[10 empty] | Execution | 330 | S41: 40; S42: 40; S43: 36; S44: 40; S45: 32; S46: 40; S47: 42; S48: 40; S49: 12; S51: 8
[10 empty] | Retest | 141 | S48: 8; S49: 28; S50: 32; S51: 33; S52: 40
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 136 | S53: 24; S1: 32; S2: 40; S3: 40
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 60 | 60 | 36 | 40 | 32 | 40 | 42 | 48 | 40 | 32 | 41 | 40 | 24 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0
[11 empty] | Price List €/h | S29: 22
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24
[10 empty] | Software Tester 3 (apprenticeship) |  | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 156 | S34: 32; S35: 44; S36: 40; S37: 40
[10 empty] | Integration | 0
[10 empty] | Execution | 305 | S39: 2; S40: 3; S41: 32; S42: 42; S43: 40; S44: 39; S45: 32; S46: 40; S47: 32; S48: 37; S49: 6
[10 empty] | Retest | 157 | S49: 40; S50: 37; S51: 40; S52: 40
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 304 | S1: 32; S2: 32; S3: 40; S4: 40; S5: 40; S6: 40; S7: 40; S8: 40
[11 empty] | 922 | 0 | 0 | 0 | 0 | 0 | 32 | 44 | 40 | 40 | 0 | 2 | 3 | 32 | 42 | 40 | 39 | 32 | 40 | 32 | 37 | 46 | 37 | 40 | 40 | 0 | 32 | 32 | 40 | 40 | 40 | 40 | 40 | 40
[11 empty] | Price List €/h | S29: 32
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24
[10 empty] | Test Analyst 1 |  | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
[10 empty] | Testbook Design | 252 | S29: 40; S30: 40; S31: 40; S32: 40; S33: 48; S34: 44
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 368 | S40: 8; S41: 40; S42: 40; S43: 40; S44: 44; S45: 32; S46: 44; S47: 40; S48: 40; S49: 40
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 286 | S1: 24; S2: 30; S3: 32; S4: 40; S5: 40; S6: 40; S7: 40; S8: 40
[11 empty] | 906 | 40 | 40 | 40 | 40 | 48 | 44 | 0 | 0 | 0 | 0 | 0 | 8 | 40 | 40 | 40 | 44 | 32 | 44 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 24 | 30 | 32 | 40 | 40 | 40 | 40 | 40
[11 empty] | Price List €/h | S29: 30
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24
[10 empty] | Test Analyst 2 |  | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
[10 empty] | Testbook Design | 250 | S29: 46; S30: 32; S31: 40; S32: 38; S33: 48; S34: 46
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 318 | S39: 16; S40: 5; S41: 32; S42: 8; S43: 40; S44: 32; S45: 32; S46: 35; S47: 32; S48: 30; S49: 32; S50: 24
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 147 | S41: 8; S42: 32; S43: 8; S44: 12; S46: 12; S47: 8; S48: 8; S49: 16; S50: 8; S51: 19; S52: 16
[10 empty] | UAT support | 272 | S1: 24; S2: 40; S3: 40; S4: 32; S5: 24; S6: 32; S7: 40; S8: 40
[11 empty] | 987 | 46 | 32 | 40 | 38 | 48 | 46 | 0 | 0 | 0 | 0 | 16 | 5 | 40 | 40 | 48 | 44 | 32 | 47 | 40 | 38 | 48 | 32 | 19 | 16 | 0 | 24 | 40 | 40 | 32 | 24 | 32 | 40 | 40
[11 empty] | Price List €/h | S29: 30
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24
[10 empty] | Test Analyst 3 |  | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
[10 empty] | Testbook Design | 222 | S29: 40; S30: 40; S31: 40; S32: 38; S33: 40; S34: 24
[10 empty] | Data preparation | 136 | S34: 20; S35: 44; S36: 32; S37: 40
[10 empty] | Integration | 0
[10 empty] | Execution | 339 | S41: 36; S42: 40; S43: 40; S44: 38; S45: 24; S46: 41; S47: 40; S48: 40; S49: 40
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 697 | 40 | 40 | 40 | 38 | 40 | 44 | 44 | 32 | 40 | 0 | 0 | 0 | 36 | 40 | 40 | 38 | 24 | 41 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Price List €/h | S29: 48
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24
[10 empty] | Test Manager |  | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 70 | S39: 5; S40: 2; S41: 4; S42: 4; S43: 4; S44: 6; S45: 7; S46: 10; S47: 4; S48: 4; S49: 8; S50: 12
[10 empty] | Retest | 0
[10 empty] | Management | 273 | S29: 12; S30: 12; S31: 12; S32: 12; S33: 12; S34: 12; S35: 20; S36: 18; S37: 18; S51: 24; S52: 21; S1: 16; S2: 8; S3: 8; S4: 8; S5: 8; S6: 8; S7: 19; S8: 25
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 343 | 12 | 12 | 12 | 12 | 12 | 12 | 20 | 18 | 18 | 0 | 5 | 2 | 4 | 4 | 4 | 6 | 7 | 10 | 4 | 4 | 8 | 12 | 24 | 21 | 0 | 16 | 8 | 8 | 8 | 8 | 8 | 19 | 25
[11 empty] | Price List €/h | S29: 27
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24
[10 empty] | PMO |  | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 149 | S29: 5; S30: 5; S31: 14; S32: 2; S33: 2; S34: 2; S35: 2; S36: 8; S41: 16; S42: 16; S43: 16; S44: 16; S45: 12; S46: 14; S49: 2; S50: 2; S1: 3; S2: 4; S7: 8
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 149 | 5 | 5 | 14 | 2 | 2 | 2 | 2 | 8 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 16 | 12 | 14 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 8 | 0
[11 empty] | Price List €/h | S29: 55
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24
[10 empty] | Service Manager |  | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 45 | S29: 1; S31: 1; S34: 3; S37: 7; S41: 8; S42: 8; S43: 5; S51: 4; S7: 2; S8: 6
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 45 | 1 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 7 | 0 | 0 | 0 | 8 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24
[10 empty] | Actual Total Costs | 145814 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
[10 empty] | Testbook Design | 22224 | 3860 | 3440 | 3680 | 3560 | 4176 | 3508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Data preparation | 7512 | 0 | 0 | 0 | 0 | 0 | 1304 | 2288 | 1840 | 2080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Integration | 3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 880 | 825 | 440 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Execution | 52446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764 | 568 | 5448 | 5156 | 5940 | 5974 | 4712 | 6368 | 5700 | 5706 | 4638 | 1296 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Retest | 8096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 1694 | 1870 | 2068 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Management | 19602 | 766 | 711 | 1009 | 630 | 630 | 795 | 1014 | 1080 | 1249 | 0 | 0 | 0 | 872 | 872 | 707 | 432 | 324 | 378 | 0 | 0 | 54 | 54 | 1372 | 1008 | 0 | 849 | 492 | 384 | 384 | 384 | 384 | 1238 | 1530
[10 empty] | ALM maintenance | 4059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792 | 913 | 1144 | 1210 | 0 | 0 | 0 | 0 | 0
[10 empty] | Reporting activities | 4410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 960 | 240 | 360 | 0 | 360 | 240 | 240 | 480 | 240 | 570 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | UAT support | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2192 | 2864 | 3104 | 3120 | 2880 | 3120 | 3360 | 3360
[12 empty] | 4626 | 4151 | 4689 | 4190 | 4806 | 5607 | 3302 | 2920 | 3329 | 880 | 1644 | 1393 | 7000 | 7428 | 6887 | 6766 | 5036 | 7106 | 5940 | 6210 | 6866 | 3460 | 4186 | 3688 | 792 | 3954 | 4500 | 4698 | 3504 | 3264 | 3504 | 4598 | 4890
EARNED VALUE
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24
[10 empty] | %Progress | 100% | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
[10 empty] | Testbook Design | 100% | 25% | 32% | 56% | 70% | 89% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Data preparation | 100% | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 70% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Integration | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Execution | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 15.5% | 43% | 55% | 59% | 77% | 77% | 87% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Retest | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 26% | 50% | 89% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Management | 100% | 3% | 6% | 9% | 12% | 15% | 18% | 21% | 24% | 27% | 30% | 33% | 36% | 39% | 42% | 45% | 48% | 51% | 54% | 57% | 60% | 63% | 66% | 69% | 72% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 100%
[10 empty] | ALM maintenance | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22% | 48% | 95% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Reporting activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 55% | 70% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | UAT support | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 35% | 50% | 60% | 75% | 85% | 95% | 100%
[12 empty] | 3.186% | 4.362% | 7.437% | 9.394% | 11.91% | 14.03% | 14.92% | 17.8% | 19.68% | 21.47% | 22.7% | 23.65% | 26.14% | 30.52% | 40.76% | 45.66% | 47.8% | 54.76% | 55.53% | 60.63% | 65.94% | 70.96% | 75.38% | 77.71% | 78.53% | 84.36% | 87.25% | 90.06% | 91.94% | 94.57% | 96.45% | 98.34% | 100%
[11 empty] | FROM | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | TO | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24
[10 empty] | EV | 161105 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
[10 empty] | Testbook Design | 18000 | 4500 | 5760 | 10080 | 12600 | 16020 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000
[10 empty] | Data preparation | 8000 | 0 | 0 | 0 | 0 | 0 | 800 | 1600 | 5600 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
[10 empty] | Integration | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 3600 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500
[10 empty] | Execution | 55485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2774.25 | 8600.175 | 23858.55 | 30516.75 | 32736.15 | 42723.45 | 42723.45 | 48271.95 | 52710.75 | 55485 | 55485 | 55485 | 55485 | 55485 | 55485 | 55485 | 55485 | 55485 | 55485 | 55485 | 55485
[10 empty] | Retest | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 3120 | 6000 | 10680 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000
[10 empty] | Management | 21120 | 633.6 | 1267.2 | 1900.8 | 2534.4 | 3168 | 3801.6 | 4435.2 | 5068.8 | 5702.4 | 6336 | 6969.6 | 7603.2 | 8236.8 | 8870.4 | 9504 | 10137.6 | 10771.2 | 11404.8 | 12038.4 | 12672 | 13305.6 | 13939.2 | 14572.8 | 15206.4 | 15206.4 | 15840 | 16473.6 | 17107.2 | 17740.8 | 18374.4 | 19008 | 19641.6 | 21120
[10 empty] | ALM maintenance | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320 | 2880 | 5700 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
[10 empty] | Reporting activities | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 1200 | 1800 | 2400 | 3000 | 3600 | 4200 | 4800 | 6600 | 8400 | 10200 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000
[10 empty] | UAT support | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 8400 | 12000 | 14400 | 18000 | 20400 | 22800 | 24000
[12 empty] | 5133.6 | 7027.2 | 11980.8 | 15134.4 | 19188 | 22601.6 | 24035.2 | 28668.8 | 31702.4 | 34586 | 36569.6 | 38103.2 | 42111.05 | 49170.575 | 65662.55 | 73554.35 | 77007.35 | 88228.25 | 89461.85 | 97683.95 | 106236.35 | 114324.2 | 121437.8 | 125191.4 | 126511.4 | 135905 | 140558.6 | 145092.2 | 148125.8 | 152359.4 | 155393 | 158426.6 | 161105
Formulas:
Bank 1 = MIN([Bank 1, row below]:C30)
Test Manager = [Client charge]+7

## Project_4
PROJECT OVERVIEW
| Project Name | Project 4 |  | Estimation | yes
| Responsible | Test Manager Blue Team |  | Sceduling | yes |  |  |  |  | Assumptions | [34 empty] | AC(AD) | AC(19) | 60476 |  | Acn(ADn=1,05) | 1.1115
| Client | Bank 1 | [5 empty] | Business Unit | Financial Services | Client charge | Test Manager | 330
| Area | Crediti | [5 empty] | Prectice | Testing | €/gg | Tester | 200
| Resource number | 5 | [5 empty] | Sub-practice level 1 | Area Operations | [35 empty] | ADn | 1.0556
| Starting date | 2022-11-14 | [5 empty] | Sub-practice level 2 | Credit Management
| Release (Go live) | 2023-02-17 | [5 empty] | Sub-practice level 3 | Credit Provision | [22 empty] | Project Planned Elapsed time
| Main Activities | Desing, Execution, and Management | [5 empty] | Activity Description | Credit provision under the following forms: facility credit, personal loans, leasing, factoring, mortages, and subsidies to open the credit. | [22 empty] | 18 | weeks
| %completion | 100%
| Next Milestone | N/A
| TM Estimate Name | Estimate 4: Project_4_.xls
| Estimate Budget | 59930
BASELINE | [32 empty] | Week | Time Unit | TPn | BASELINE | BCWS | EV | ES | Actual Costs | ACWP | CPI | SPI | SPIt | CV | SV | RFI | RV | CEACn=BACn | CEACn=BACn-CVn | CEACn=BCAn/CPI | CEACn=BACn/(CPI*SPI) | CEACn=BACn/ ( .8 CPI + .2 SPI) | CEACn=BACn/(CPI*SPIt) | CEACn=BACn/ ( .8 CPI + .2 SPIt) |  | WS | WP | ACn | BACn | Esn | CVn | SVn | RVn
[34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 2022-11-14 | 2022-11-18 | S47 | 1 | 0.055556 | 1995 | 1995 | 1390.05 | 0.69677 | 2909 | 2909 | 0.47784 | 0.69677 | 0.69677 | -1518.95 | -604.95 | 0.6858 | -914 | 1 | 1.0279 | 2.0927 | 3.0035 | 1.9171 | 3.0035 | 1.9171 |  | 0.036666 | 0.025548 | 0.053464 | 1 | 0.038709 | -0.027917 | -0.011118 | -0.016798
[31 empty] | 2022-11-21 | 2022-11-25 | S48 | 2 | 0.11111 | 1995 | 3990 | 3455.1 | 1.7319 | 2644 | 5553 | 0.6222 | 0.86594 | 0.86594 | -2097.9 | -534.9 | 0.71853 | -1563 | 1 | 1.0386 | 1.6072 | 1.856 | 1.4904 | 1.856 | 1.4904 |  | 0.073332 | 0.063501 | 0.10206 | 1 | 0.096216 | -0.038557 | -0.0098309 | -0.028726
|  | Project Activities | [8 empty] | FROM | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 |  | 2022-11-28 | 2022-12-02 | S49 | 3 | 0.16667 | 1995 | 5985 | 5970.15 | 2.9926 | 3032 | 8585 | 0.69542 | 0.99752 | 0.99752 | -2614.85 | -14.85 | 0.69715 | -2600 | 1 | 1.0481 | 1.438 | 1.4416 | 1.323 | 1.4416 | 1.323 |  | 0.11 | 0.10973 | 0.15778 | 1 | 0.16625 | -0.048058 | -0.00027293 | -0.047785
|  | Start Date | End Date | Starting week number | Ending week number | FTEs | FTE figure | Weight | Budget x activity |  | TO | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 |  | 2022-12-05 | 2022-12-09 | S50 | 4 | 0.22222 | 4495 | 10480 | 9410.2 | 3.762 | 3488 | 12073 | 0.77944 | 0.89792 | 0.9405 | -2662.8 | -1069.8 | 0.86805 | -1593 | 1 | 1.0489 | 1.283 | 1.4288 | 1.2451 | 1.3641 | 1.2321 |  | 0.19261 | 0.17295 | 0.22189 | 1 | 0.209 | -0.04894 | -0.019662 | -0.029278
| Project 4 | 2022-11-14 | 2023-02-16 | 47 | 7 |  |  | 100% | overall budget - allocation plan | Scheduling | € | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | DELAY | 2022-12-12 | 2022-12-16 | S51 | 5 | 0.27778 | 4495 | 14975 | 11320.25 | 4.1869 | 4368 | 16441 | 0.68854 | 0.75594 | 0.83739 | -5120.75 | -3654.75 | 0.91083 | -1466 | 1 | 1.0941 | 1.4524 | 1.9212 | 1.4245 | 1.7344 | 1.3922 |  | 0.27523 | 0.20805 | 0.30217 | 1 | 0.23261 | -0.094114 | -0.067171 | -0.026944
| Testbook Design | 2022-11-14 | 2022-12-02 | 47 | 49 | 1,5/day | Test Analyst | 8.271% | 4500 | Testbook Design | 4500 | 1500 | 1500 | 1500 | [16 empty] | 2022-12-19 | 2022-12-23 | S52 | 6 | 0.33333 | 4495 | 19470 | 16020.3 | 5.2325 | 3778 | 20219 | 0.79234 | 0.82282 | 0.87209 | -4198.7 | -3449.7 | 0.96296 | -749 | 1 | 1.0772 | 1.2621 | 1.5339 | 1.2525 | 1.4472 | 1.2372 |  | 0.35784 | 0.29444 | 0.3716 | 1 | 0.2907 | -0.077168 | -0.063402 | -0.013766
| Execution | 2022-12-05 | 2023-01-27 | 50 | 4 | 3/day | Test Analyst; Software Tester | 44.11% | 24000 | Execution | 24000 |  |  |  | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | [8 empty] | 2022-12-26 | 2022-12-30 | S53 | 7 | 0.38889 | 4495 | 23965 | 17060.35 | 5.4639 | 2072 | 22291 | 0.76535 | 0.71189 | 0.78056 | -5230.65 | -6904.65 | 1.0751 | 1674 | 1 | 1.0961 | 1.3066 | 1.8354 | 1.3251 | 1.6739 | 1.3014 |  | 0.44045 | 0.31355 | 0.40969 | 1 | 0.30355 | -0.096134 | -0.1269 | 0.030766
| Retest | 2023-01-30 | 2023-02-16 | 5 | 7 | 2/day | Software Tester | 11.03% | 6000 | Retest | 6000 | [11 empty] | 2000 | 2000 | 2000 | [5 empty] | 2023-01-02 | 2023-01-06 | S1 | 8 | 0.44444 | 4495 | 28460 | 19530.35 | 6.0134 | 2320 | 24611 | 0.79356 | 0.68624 | 0.75168 | -5080.65 | -8929.65 | 1.1564 | 3849 | 1 | 1.0934 | 1.2601 | 1.8363 | 1.2952 | 1.6764 | 1.2736 |  | 0.52307 | 0.35895 | 0.45232 | 1 | 0.33408 | -0.093377 | -0.16412 | 0.070741
| Management | 2022-11-14 | 2023-02-16 | 47 | 7 | 1,5/week | Test Manager | 16.38% | 8910 | Management | 8910 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 |  | 2023-01-09 | 2023-01-13 | S2 | 9 | 0.5 | 4495 | 32955 | 21414 | 6.4325 | 2794 | 27405 | 0.78139 | 0.6498 | 0.71472 | -5991 | -11541 | 1.2025 | 5550 | 1 | 1.1101 | 1.2798 | 1.9695 | 1.3244 | 1.7906 | 1.302 |  | 0.60568 | 0.39357 | 0.50368 | 1 | 0.35736 | -0.11011 | -0.21211 | 0.102
| Reporting activities | 2022-12-05 | 2023-02-16 | 50 | 7 | 1/day | Test Analyst | 20.22% | 11000 | Reporting activities | 11000 |  |  |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | [5 empty] | 2023-01-16 | 2023-01-20 | S3 | 10 | 0.55556 | 4495 | 37450 | 24199.5 | 7.0522 | 3294 | 30699 | 0.78828 | 0.64618 | 0.70522 | -6499.5 | -13250.5 | 1.2199 | 6751 | 1 | 1.1195 | 1.2686 | 1.9632 | 1.316 | 1.7989 | 1.2959 |  | 0.68829 | 0.44476 | 0.56422 | 1 | 0.39179 | -0.11945 | -0.24353 | 0.12408
[11 empty] | 54410 | 1995 | 1995 | 1995 | 4495 | 4495 | 4495 | 4495 | 4495 | 4495 | 4495 | 4495 | 3495 | 3495 | 3495 | 495 | 495 | 495 | 495 |  | 2023-01-23 | 2023-01-27 | S4 | 11 | 0.61111 | 4495 | 41945 | 28493.2 | 8.0074 | 3539 | 34238 | 0.83221 | 0.6793 | 0.72794 | -5744.8 | -13451.8 | 1.2251 | 7707 | 1 | 1.1056 | 1.2016 | 1.7689 | 1.2475 | 1.6507 | 1.2325 |  | 0.77091 | 0.52368 | 0.62926 | 1 | 0.44485 | -0.10558 | -0.24723 | 0.14165
[10 empty] | Contingency up to the project type | 5520 | [19 empty] | 2023-01-30 | 2023-02-03 | S5 | 12 | 0.66667 | 3495 | 45440 | 31943.25 | 8.7749 | 3402 | 37640 | 0.84865 | 0.70298 | 0.73124 | -5696.75 | -13496.75 | 1.2072 | 7800 | 1 | 1.1047 | 1.1783 | 1.6762 | 1.2202 | 1.6114 | 1.2119 |  | 0.83514 | 0.58708 | 0.69178 | 1 | 0.4875 | -0.1047 | -0.24806 | 0.14336
[10 empty] | >10%--> highly risk project | [20 empty] | 2023-02-06 | 2023-02-10 | S6 | 13 | 0.72222 | 3495 | 48935 | 35203.3 | 9.5002 | 3860 | 41500 | 0.84827 | 0.71939 | 0.73078 | -6296.7 | -13731.7 | 1.1792 | 7435 | 1 | 1.1157 | 1.1789 | 1.6387 | 1.2158 | 1.6132 | 1.2125 |  | 0.89938 | 0.647 | 0.76273 | 1 | 0.52779 | -0.11573 | -0.25237 | 0.13665
[10 empty] | btw 5% and 10% --> medium risk project | [20 empty] | 2023-02-13 | 2023-02-17 | S7 | 14 | 0.77778 | 3495 | 52430 | 37683.35 | 10.0519 | 3108 | 44608 | 0.84477 | 0.71874 | 0.71799 | -6924.65 | -14746.65 | 1.1753 | 7822 | 1 | 1.1273 | 1.1838 | 1.647 | 1.2202 | 1.6487 | 1.2204 |  | 0.96361 | 0.69258 | 0.81985 | 1 | 0.55844 | -0.12727 | -0.27103 | 0.14376
[10 empty] | <5% --> low risk project | [20 empty] | 2023-02-20 | 2023-02-24 | S8 | 15 | 0.83333 | 495 | 52925 | 42193.4 | 11.0711 | 2386 | 46994 | 0.89785 | 0.79723 | 0.73807 | -4800.6 | -10731.6 | 1.1262 | 5931 | 1 | 1.0882 | 1.1138 | 1.3971 | 1.1393 | 1.509 | 1.1549 |  | 0.97271 | 0.77547 | 0.8637 | 1 | 0.61506 | -0.08823 | -0.19724 | 0.10901
ACTUAL COSTS | [30 empty] | 2023-02-27 | 2023-03-03 | S9 | 16 | 0.88889 | 495 | 53420 | 43643.45 | 11.486 | 3420 | 50414 | 0.8657 | 0.81699 | 0.71787 | -6770.55 | -9776.55 | 1.0596 | 3006 | 1 | 1.1244 | 1.1551 | 1.4139 | 1.1683 | 1.6091 | 1.196 |  | 0.9818 | 0.80212 | 0.92656 | 1 | 0.63811 | -0.12444 | -0.17968 | 0.055247
[31 empty] | 2023-03-06 | 2023-03-10 | S10 | 17 | 0.94444 | 495 | 53915 | 48033.5 | 12.7421 | 3282 | 53696 | 0.89455 | 0.89091 | 0.74953 | -5662.5 | -5881.5 | 1.0041 | 219 | 1 | 1.1041 | 1.1179 | 1.2548 | 1.1188 | 1.4914 | 1.1553 |  | 0.9909 | 0.88281 | 0.98688 | 1 | 0.70789 | -0.10407 | -0.1081 | 0.004025
[31 empty] | 2023-03-13 | 2023-03-17 | S11 | 18 | 1 | 495 | 54410 | 50463.55 | 13.4374 | 3544 | 57240 | 0.88161 | 0.92747 | 0.74652 | -6776.45 | -3946.45 | 0.95056 | -2830 | 1 | 1.1245 | 1.1343 | 1.223 | 1.1226 | 1.5194 | 1.1701 |  | 1 | 0.92747 | 1.052 | 1 | 0.74652 | -0.12454 | -0.072532 | -0.052012
[31 empty] | 2023-03-20 | 2023-03-24 | S12 | 19 | 1.0556 | 0 | 54410 | 54410 | 19 | 3236 | 60476 | 0.8997 | 1 | 1 | -6066 | 0 | 0.8997 | -6066 | FINE | FINE | FINE | FINE | FINE | FINE | FINE | dw | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE
[11 empty] | Price List €/h | 28
[11 empty] | FROM | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20
[11 empty] | TO | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24
[10 empty] | Software Tester 1 |  | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12
[10 empty] | Testbook Design | 0
[10 empty] | Execution | 454 |  |  | 8 | 32 | 40 | 40 | 16 | 32 | 30 | 40 | 40 | 32 | 16 | 8 | 24 | 16 | 8 | 40 | 32
[10 empty] | Retest | 112 | S5: 8; S6: 24; S7: 32; S8: 8; S9: 24; S10: 8; S12: 8
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0
[11 empty] | 566 | 0 | 0 | 8 | 32 | 40 | 40 | 16 | 32 | 30 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 16 | 40 | 40
[11 empty] | Price List €/h | S47: 22
[11 empty] | FROM | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20
[11 empty] | TO | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24
[10 empty] | Software Tester 2 (apprenticeship) |  | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12
[10 empty] | Testbook Design | 0
[10 empty] | Execution | 334 |  |  | 8 | 32 | 40 | 40 | 8 | 32 | 32 | 42 | 36 |  |  |  | 8 | 8 | 24 | 8 | 16
[10 empty] | Retest | 162 | S5: 40; S6: 44; S7: 40; S8: 5; S9: 12; S10: 5; S12: 16
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0
[11 empty] | 496 | 0 | 0 | 8 | 32 | 40 | 40 | 8 | 32 | 32 | 42 | 36 | 40 | 44 | 40 | 13 | 20 | 29 | 8 | 32
[11 empty] | Price List €/h | S47: 30
[11 empty] | FROM | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20
[11 empty] | TO | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24
[10 empty] | Test Analyst 1 |  | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12
[10 empty] | Testbook Design | 112 | S47: 40; S48: 32; S49: 40
[10 empty] | Execution | 333 |  |  |  | 32 | 32 | 32 | 16 | 16 | 32 | 32 | 32 | 15 | 24 | 14 |  |  | 16 | 24 | 16
[10 empty] | Retest | 40 | S8: 16; S9: 24
[10 empty] | Management | 0
[10 empty] | Reporting activities | 174 |  |  |  |  | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 20 | 20 | 20 | 12 | 16 | 12 | 4 | 6
[11 empty] | 659 | 40 | 32 | 40 | 32 | 48 | 40 | 24 | 24 | 40 | 40 | 40 | 35 | 44 | 34 | 28 | 40 | 28 | 28 | 22
[11 empty] | Price List €/h | S47: 44
[11 empty] | FROM | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20
[11 empty] | TO | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24
[10 empty] | Test Manager |  | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12
[10 empty] | Testbook Design | 52 | S47: 20; S48: 20; S49: 12
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 207 | 16 | 16 | 16 | 12 | 12 | 12 | 12 |  |  |  | 8 | 8 | 8 | 2 | 6 | 15 | 24 | 32 | 8
[10 empty] | Reporting activities | 0
[11 empty] | 259 | 36 | 36 | 28 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 8 | 8 | 8 | 2 | 6 | 15 | 24 | 32 | 8
[11 empty] | Price List €/h | S47: 25
[11 empty] | FROM | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20
[11 empty] | TO | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24
[10 empty] | PMO |  | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12
[10 empty] | Testbook Design | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 102 | 5 | 4 | 8 | 16 | 16 | 2 | 8 |  | 2 | 2 | 3 |  | 4 |  | 4 |  | 12 |  | 16
[10 empty] | Reporting activities | 0
[11 empty] | 102 | 5 | 4 | 8 | 16 | 16 | 2 | 8 | 0 | 2 | 2 | 3 | 0 | 4 | 0 | 4 | 0 | 12 | 0 | 16
[11 empty] | FROM | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20
[11 empty] | TO | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24
[10 empty] | Actual Total Costs | 57240 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12
[10 empty] | Testbook Design | 5648 | 2080 | 1840 | 1728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Execution | 28322 | 0 | 0 | 400 | 2560 | 2960 | 2960 | 1104 | 2080 | 2504 | 3004 | 2872 | 1346 | 1168 | 644 | 848 | 624 | 1232 | 2016 | 1728
[10 empty] | Retest | 7324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1104 | 1640 | 1776 | 814 | 1656 | 334 | 0 | 576
[10 empty] | Management | 10906 | 829 | 804 | 904 | 928 | 928 | 578 | 728 | 0 | 50 | 50 | 427 | 352 | 452 | 88 | 364 | 660 | 1356 | 1408 | 752
[10 empty] | Reporting activities | 5040 | 0 | 0 | 0 | 0 | 480 | 240 | 240 | 240 | 240 | 240 | 240 | 600 | 600 | 600 | 360 | 480 | 360 | 120 | 180
[12 empty] | 2909 | 2644 | 3032 | 3488 | 4368 | 3778 | 2072 | 2320 | 2794 | 3294 | 3539 | 3402 | 3860 | 3108 | 2386 | 3420 | 3282 | 3544 | 3236
EARNED VALUE
[11 empty] | FROM | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20
[11 empty] | TO | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24
[10 empty] | %Progress | 100% | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12
[10 empty] | Testbook Design | 100% | 20% | 55% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Execution | 100% | 0% | 0% | 0% | 10% | 15% | 22% | 22% | 30% | 35% | 42% | 55% | 63% | 69% | 74% | 86% | 86% | 92% | 95% | 100%
[10 empty] | Retest | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 23% | 27% | 35% | 40% | 70% | 83% | 100%
[10 empty] | Management | 100% | 5.5% | 11% | 16.5% | 22% | 27.5% | 33% | 38.5% | 38.5% | 40% | 45% | 52% | 57.5% | 63% | 68.5% | 74% | 79.5% | 85% | 90.5% | 100%
[10 empty] | Reporting activities | 100% | 0% | 0% | 0% | 5% | 7% | 30% | 35% | 40% | 45% | 51% | 56% | 60% | 65% | 70% | 76% | 82% | 88% | 92% | 100%
[12 empty] | 2.555% | 6.35% | 10.97% | 17.29% | 20.81% | 29.44% | 31.36% | 35.89% | 39.36% | 44.48% | 52.37% | 58.71% | 64.7% | 69.26% | 77.55% | 80.21% | 88.28% | 92.75% | 100%
[11 empty] | FROM | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20
[11 empty] | TO | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24
[10 empty] | EV | 50463.55 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12
[10 empty] | Testbook Design | 4500 | 900 | 2475 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500
[10 empty] | Execution | 22800 | 0 | 0 | 0 | 2400 | 3600 | 5280 | 5280 | 7200 | 8400 | 10080 | 13200 | 15120 | 16560 | 17760 | 20640 | 20640 | 22080 | 22800 | 24000
[10 empty] | Retest | 4980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 1380 | 1620 | 2100 | 2400 | 4200 | 4980 | 6000
[10 empty] | Management | 8063.55 | 490.05 | 980.1 | 1470.15 | 1960.2 | 2450.25 | 2940.3 | 3430.35 | 3430.35 | 3564 | 4009.5 | 4633.2 | 5123.25 | 5613.3 | 6103.35 | 6593.4 | 7083.45 | 7573.5 | 8063.55 | 8910
[10 empty] | Reporting activities | 10120 | 0 | 0 | 0 | 550 | 770 | 3300 | 3850 | 4400 | 4950 | 5610 | 6160 | 6600 | 7150 | 7700 | 8360 | 9020 | 9680 | 10120 | 11000
[12 empty] | 1390.05 | 3455.1 | 5970.15 | 9410.2 | 11320.25 | 16020.3 | 17060.35 | 19530.35 | 21414 | 24199.5 | 28493.2 | 31943.25 | 35203.3 | 37683.35 | 42193.4 | 43643.45 | 48033.5 | 50463.55 | 54410
Formulas:
Bank 1 = MIN([Bank 1, row below]:C26)

## Project_5
PROJECT OVERVIEW
| Project Name | Project 5 |  | Estimation | yes
| Responsible | Test Manager Green Team |  | Sceduling | yes |  |  |  |  | Assumptions | [44 empty] | AC(AD) | AC(29) | 132351 |  | 1.3384
| Client | Bank 1 | [5 empty] | Business Unit | Financial Services | Client charge | Test Manager | 330
| Area | Crediti | [5 empty] | Prectice | Testing | €/gg | Tester | 200
| Resource number | 7 | [5 empty] | Sub-practice level 1 | Area Operations | [45 empty] | ADn | 1.1154
| Starting date | 2022-06-06 | [5 empty] | Sub-practice level 2 | Credit Management
| Release (Go live) | 2022-12-02 | [5 empty] | Sub-practice level 3 | Credit Monitoring | [33 empty] | Project Planned Elapsed time
| Main Activities | Desing, Execution, Management and UAT | [5 empty] | Activity Description | Controlling activities on the credit actors to be able to anticipate issues and to potentially report them to the top management. Correct accouting of the registered anomalies. Credit management in case the debtor is not going to respect his/her obligations. | [33 empty] | 26 | weeks
| %completion | 100%
| Next Milestone | N/A
| TM Estimate Name | Estimate 5: Project_4_.xls
| Estimate Budget | 100190
BASELINE | [42 empty] | Week | Time Unit | TPn | BASELINE | BCWS | EV | ES | Actual Costs | ACWP | CPI | SPI | SPIt | CV | SV | RFI | RV | CEACn=BACn | CEACn=BACn-CVn | CEACn=BCAn/CPI | CEACn=BACn/(CPI*SPI) | CEACn=BACn/ ( .8 CPI + .2 SPI) | CEACn=BACn/(CPI*SPIt) | CEACn=BACn/ ( .8 CPI + .2 SPIt) |  | WS | WP | ACn | BACn | Esn | CVn | SVn | RVn
[44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[41 empty] | 2022-06-06 | 2022-06-10 | S24 | 1 | 0.038462 | 2830 | 2830 | 1257.4 | 0.44431 | 3828 | 3828 | 0.32847 | 0.44431 | 0.44431 | -2570.6 | -1572.6 | 0.73929 | -998 | 1 | 1.026 | 3.0444 | 6.8519 | 2.8438 | 6.8519 | 2.8438 |  | 0.028618 | 0.012715 | 0.03871 | 1 | 0.017089 | -0.025995 | -0.015903 | -0.010092
[41 empty] | 2022-06-13 | 2022-06-17 | S25 | 2 | 0.076923 | 2830 | 5660 | 2186.4 | 0.77258 | 4424 | 8252 | 0.26495 | 0.38629 | 0.38629 | -6065.6 | -3473.6 | 0.68589 | -2592 | 1 | 1.0613 | 3.7742 | 9.7705 | 3.4576 | 9.7705 | 3.4576 |  | 0.057235 | 0.022109 | 0.083446 | 1 | 0.029715 | -0.061337 | -0.035126 | -0.026211
|  | Project Activities | [8 empty] | FROM | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 |  |  |  | 2022-06-20 | 2022-06-24 | S26 | 3 | 0.11538 | 2830 | 8490 | 3529.6 | 1.2472 | 3432 | 11684 | 0.30209 | 0.41574 | 0.41574 | -8154.4 | -4960.4 | 0.72663 | -3194 | 1 | 1.0825 | 3.3103 | 7.9625 | 3.0786 | 7.9625 | 3.0786 |  | 0.085853 | 0.035692 | 0.11815 | 1 | 0.04797 | -0.082459 | -0.050161 | -0.032299
|  | Start Date | End Date | Starting week number | Ending week number | FTEs | FTE figure | Weight | Budget x activity |  | TO | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 |  |  |  | 2022-06-27 | 2022-07-01 | S27 | 4 | 0.15385 | 2830 | 11320 | 5087 | 1.7975 | 4400 | 16084 | 0.31628 | 0.44938 | 0.44938 | -10997 | -6233 | 0.70381 | -4764 | 1 | 1.1112 | 3.1618 | 7.0359 | 2.9163 | 7.0359 | 2.9163 |  | 0.11447 | 0.051441 | 0.16265 | 1 | 0.069136 | -0.1112 | -0.06303 | -0.048175
| Project 5 | 2022-06-06 | 2022-12-01 | 24 | 49 |  |  | 100% | overall budget - allocation plan | Scheduling | € | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | DELAY | DELAY | DELAY | 2022-07-04 | 2022-07-08 | S28 | 5 | 0.19231 | 2330 | 13650 | 6687 | 2.3629 | 1559 | 17643 | 0.37902 | 0.48989 | 0.47258 | -10956 | -6963 | 0.77368 | -3993 | 1 | 1.1108 | 2.6384 | 5.3857 | 2.4926 | 5.583 | 2.5143 |  | 0.13803 | 0.067621 | 0.17841 | 1 | 0.090881 | -0.11079 | -0.070412 | -0.040378
| Testbook Design | 2022-06-06 | 2022-07-01 | 24 | 27 | 2,5/day | Test Analyts | 10.11% | 10000 | Testbook Design | 10000 | 2500 | 2500 | 2500 | 2500 | [25 empty] | 2022-07-11 | 2022-07-15 | S29 | 6 | 0.23077 | 2330 | 15980 | 9787 | 3.4583 | 2133 | 19776 | 0.49489 | 0.61245 | 0.57638 | -9989 | -6193 | 0.80805 | -3796 | 1 | 1.101 | 2.0206 | 3.2993 | 1.929 | 3.5057 | 1.9562 |  | 0.16159 | 0.098969 | 0.19998 | 1 | 0.13301 | -0.10101 | -0.062625 | -0.038386
| Integration | 2022-07-04 | 2022-07-15 | 28 | 29 | 2/day | Software tester | 4.045% | 4000 | Integration | 4000 |  |  |  |  | 2000 | 2000 | [23 empty] | 2022-07-18 |  | S30 | 7 | 0.26923 | 5660 | 21640 | 11716 | 4.17 | 3914 | 23690 | 0.49455 | 0.5414 | 0.59571 | -11974 | -9924 | 0.91347 | -2050 | 1 | 1.1211 | 2.022 | 3.7348 | 1.9844 | 3.3943 | 1.9426 |  | 0.21883 | 0.11848 | 0.23956 | 1 | 0.16038 | -0.12108 | -0.10035 | -0.02073
| Execution | 2022-07-18 | 2022-09-02 | 30 | 36 | 4/day+0,5/week | Software tester; Test Analyst; Test Manager | 30.65% | 30310 | Execution | 30310 | [6 empty] | 4330 | 4330 | 4330 | 4330 | 4330 | 4330 | 4330 | [16 empty] | 2022-07-25 | 2022-07-29 | S31 | 8 | 0.30769 | 5660 | 27300 | 14836 | 5.509 | 1512 | 25202 | 0.58868 | 0.54344 | 0.68863 | -10366 | -12464 | 1.0832 | 2098 | 1 | 1.1048 | 1.6987 | 3.1258 | 1.7252 | 2.4668 | 1.6429 |  | 0.27606 | 0.15003 | 0.25485 | 1 | 0.21189 | -0.10482 | -0.12604 | 0.021215
| Retest | 2022-09-05 | 2022-09-30 | 37 | 40 | 2/day | Software tester | 8.09% | 8000 | Retest | 8000 | [13 empty] | 2000 | 2000 | 2000 | 2000 | [12 empty] | 2022-08-01 |  | S32 | 9 | 0.34615 | 5660 | 32960 | 16105 | 6.0221 | 3146 | 28348 | 0.56812 | 0.48862 | 0.66912 | -12243 | -16855 | 1.1627 | 4612 | 1 | 1.1238 | 1.7602 | 3.6024 | 1.8109 | 2.6306 | 1.6998 |  | 0.3333 | 0.16286 | 0.28666 | 1 | 0.23162 | -0.1238 | -0.17044 | 0.046638
| Management | 2022-06-06 | 2022-12-01 | 24 | 49 | 1/week | Test Manager | 8.676% | 8580 | Management | 8580 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 |  |  |  | 2022-08-08 | 2022-08-12 | S33 | 10 | 0.38462 | 5660 | 38620 | 20399.2 | 6.7808 | 4848 | 33196 | 0.61451 | 0.5282 | 0.67808 | -12796.8 | -18220.8 | 1.1634 | 5424 | 1 | 1.1294 | 1.6273 | 3.0809 | 1.6743 | 2.3999 | 1.5943 |  | 0.39053 | 0.20628 | 0.33569 | 1 | 0.2608 | -0.1294 | -0.18425 | 0.054849
| Reporting activities | 2022-07-18 | 2022-09-30 | 30 | 40 | 1/day | Test Analyts | 11.12% | 11000 | Reporting activities | 11000 | [6 empty] | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | [12 empty] | 2022-08-15 | 2022-08-19 | S34 | 11 | 0.42308 | 5660 | 44280 | 23290.9 | 7.2917 | 4342 | 37538 | 0.62046 | 0.52599 | 0.66288 | -14247.1 | -20989.1 | 1.1796 | 6742 | 1 | 1.1441 | 1.6117 | 3.0641 | 1.6623 | 2.4314 | 1.59 |  | 0.44777 | 0.23552 | 0.37959 | 1 | 0.28045 | -0.14407 | -0.21225 | 0.068177
| UAT Support | 2022-10-03 | 2022-12-01 | 41 | 49 | 3/day | Software tester; Test Analyst | 27.3% | 27000 | UAT Support | 27000 | [17 empty] | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 |  |  |  | 2022-08-22 | 2022-08-26 | S35 | 12 | 0.46154 | 5660 | 49940 | 35372.2 | 9.4262 | 3998 | 41536 | 0.8516 | 0.70829 | 0.78552 | -6163.8 | -14567.8 | 1.2023 | 8404 | 1 | 1.0623 | 1.1743 | 1.6579 | 1.2152 | 1.4949 | 1.1928 |  | 0.50501 | 0.35769 | 0.42002 | 1 | 0.36255 | -0.06233 | -0.14731 | 0.084983
[11 empty] | 98890 | 2830 | 2830 | 2830 | 2830 | 2330 | 2330 | 5660 | 5660 | 5660 | 5660 | 5660 | 5660 | 5660 | 3330 | 3330 | 3330 | 3330 | 3330 | 3330 | 3330 | 3330 | 3330 | 3330 | 3330 | 3330 | 3330 |  |  |  | 2022-08-29 | 2022-09-02 | S36 | 13 | 0.5 | 5660 | 55600 | 37866.7 | 9.8669 | 5326 | 46862 | 0.80805 | 0.68106 | 0.75899 | -8995.3 | -17733.3 | 1.1865 | 8738 | 1 | 1.091 | 1.2376 | 1.8171 | 1.2777 | 1.6305 | 1.2528 |  | 0.56224 | 0.38292 | 0.47388 | 1 | 0.3795 | -0.090963 | -0.17932 | 0.088361
[10 empty] | Contingency up to the project type | 1300 | [29 empty] | 2022-09-05 | 2022-09-09 | S37 | 14 | 0.53846 | 3330 | 58930 | 41766.7 | 10.556 | 6965 | 53827 | 0.77594 | 0.70875 | 0.754 | -12060.3 | -17163.3 | 1.0948 | 5103 | 1 | 1.122 | 1.2888 | 1.8183 | 1.3115 | 1.7092 | 1.2961 |  | 0.59591 | 0.42236 | 0.54431 | 1 | 0.406 | -0.12196 | -0.17356 | 0.051603
[10 empty] | >10%--> highly risk project | [30 empty] | 2022-09-12 | 2022-09-16 | S38 | 15 | 0.57692 | 3330 | 62260 | 44915.6 | 11.1123 | 6003 | 59830 | 0.75072 | 0.72142 | 0.74082 | -14914.4 | -17344.4 | 1.0406 | 2430 | 1 | 1.1508 | 1.3321 | 1.8464 | 1.3425 | 1.7981 | 1.3356 |  | 0.62959 | 0.4542 | 0.60502 | 1 | 0.4274 | -0.15082 | -0.17539 | 0.024573
[10 empty] | btw 5% and 10% --> medium risk project | [30 empty] | 2022-09-19 | 2022-09-23 | S39 | 16 | 0.61538 | 3330 | 65590 | 48475.1 | 11.7412 | 6244 | 66074 | 0.73365 | 0.73906 | 0.73382 | -17598.9 | -17114.9 | 0.99267 | -484 | 1 | 1.178 | 1.3631 | 1.8443 | 1.361 | 1.8575 | 1.363 |  | 0.66326 | 0.49019 | 0.66816 | 1 | 0.45158 | -0.17796 | -0.17307 | -0.0048943
[10 empty] | <5% --> low risk project | [30 empty] | 2022-09-26 | 2022-09-30 | S40 | 17 | 0.65385 | 3330 | 68920 | 50216 | 12.0488 | 5962 | 72036 | 0.6971 | 0.72861 | 0.70875 | -21820 | -18704 | 0.95674 | -3116 | 1 | 1.2206 | 1.4345 | 1.9688 | 1.4217 | 2.024 | 1.4297 |  | 0.69694 | 0.5078 | 0.72845 | 1 | 0.46341 | -0.22065 | -0.18914 | -0.03151
ACTUAL COSTS | [40 empty] | 2022-10-03 | 2022-10-07 | S41 | 18 | 0.69231 | 3330 | 72250 | 51316 | 12.2431 | 5396 | 77432 | 0.66272 | 0.71026 | 0.68017 | -26116 | -20934 | 0.93308 | -5182 | 1 | 1.2641 | 1.5089 | 2.1245 | 1.4876 | 2.2184 | 1.501 |  | 0.73061 | 0.51892 | 0.78301 | 1 | 0.47089 | -0.26409 | -0.21169 | -0.052402
[41 empty] | 2022-10-10 | 2022-10-14 | S42 | 19 | 0.73077 | 3330 | 75580 | 55626.4 | 13.0079 | 7014 | 84446 | 0.65872 | 0.73599 | 0.68463 | -28819.6 | -19953.6 | 0.89501 | -8866 | 1 | 1.2914 | 1.5181 | 2.0626 | 1.4833 | 2.2174 | 1.5062 |  | 0.76428 | 0.56251 | 0.85394 | 1 | 0.5003 | -0.29143 | -0.20178 | -0.089655
[41 empty] | 2022-10-17 | 2022-10-21 | S43 | 20 | 0.76923 | 3330 | 78910 | 63731.2 | 15.4418 | 5670 | 90116 | 0.70721 | 0.80764 | 0.77209 | -26384.8 | -15178.8 | 0.87565 | -11206 | 1 | 1.2668 | 1.414 | 1.7508 | 1.375 | 1.8314 | 1.3885 |  | 0.79796 | 0.64447 | 0.91128 | 1 | 0.59392 | -0.26681 | -0.15349 | -0.11332
[41 empty] | 2022-10-24 | 2022-10-28 | S44 | 21 | 0.80769 | 3330 | 82240 | 69485 | 17.1697 | 4852 | 94968 | 0.73167 | 0.84491 | 0.8176 | -25483 | -12755 | 0.86598 | -12728 | 1 | 1.2577 | 1.3667 | 1.6176 | 1.3257 | 1.6716 | 1.3354 |  | 0.83163 | 0.70265 | 0.96034 | 1 | 0.66037 | -0.25769 | -0.12898 | -0.12871
[11 empty] | Price List €/h | 11 | [28 empty] | 2022-10-31 | 2022-11-04 | S45 | 22 | 0.84615 | 3330 | 85570 | 75065.6 | 18.8455 | 3744 | 98712 | 0.76045 | 0.87724 | 0.85661 | -23646.4 | -10504.4 | 0.86687 | -13142 | 1 | 1.2391 | 1.315 | 1.499 | 1.2758 | 1.5351 | 1.2826 |  | 0.8653 | 0.75908 | 0.9982 | 1 | 0.72483 | -0.23912 | -0.10622 | -0.1329
[11 empty] | FROM | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-11-07 | 2022-11-11 | S46 | 23 | 0.88462 | 3330 | 88900 | 79013 | 20.0309 | 5188 | 103900 | 0.76047 | 0.88879 | 0.87091 | -24887 | -9887 | 0.85563 | -15000 | 1 | 1.2517 | 1.315 | 1.4795 | 1.272 | 1.5099 | 1.2779 |  | 0.89898 | 0.799 | 1.0507 | 1 | 0.77042 | -0.25166 | -0.09998 | -0.15168
[11 empty] | TO | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-11-14 | 2022-11-18 | S47 | 24 | 0.92308 | 3330 | 92230 | 82520.4 | 21.0842 | 5174 | 109074 | 0.75655 | 0.89472 | 0.87851 | -26553.6 | -9709.6 | 0.84557 | -16844 | 1 | 1.2685 | 1.3218 | 1.4773 | 1.2752 | 1.5046 | 1.2805 |  | 0.93265 | 0.83447 | 1.103 | 1 | 0.81093 | -0.26852 | -0.098186 | -0.17033
[10 empty] | Software Tester 1 (stage) |  | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | 2022-11-21 | 2022-11-25 | S48 | 25 | 0.96154 | 3330 | 95560 | 84703.6 | 21.7398 | 3976 | 113050 | 0.74926 | 0.88639 | 0.86959 | -28346.4 | -10856.4 | 0.84529 | -17490 | 1 | 1.2866 | 1.3347 | 1.5057 | 1.2875 | 1.5348 | 1.2931 |  | 0.96633 | 0.85654 | 1.1432 | 1 | 0.83615 | -0.28665 | -0.10978 | -0.17686
[10 empty] | Testbook Design | 0 | [29 empty] | 2022-11-28 | 2022-12-02 | S49 | 26 | 1 | 3330 | 98890 | 87661 | 22.6279 | 5140 | 118190 | 0.7417 | 0.88645 | 0.8703 | -30529 | -11229 | 0.8367 | -19300 | 1 | 1.3087 | 1.3483 | 1.521 | 1.2976 | 1.5492 | 1.3031 |  | 1 | 0.88645 | 1.1952 | 1 | 0.8703 | -0.30872 | -0.11355 | -0.19517
[10 empty] | Integration | 177 | S28: 40; S29: 21; S30: 44; S31: 32; S32: 40 | 2022-12-05 | 2022-12-09 | S50 | 27 | 1.0385 | 0 | 98890 | 90532.6 | 23.4903 | 3960 | 122150 | 0.74116 | 0.91549 | 0.87001 | -31617.4 | -8357.4 | 0.80958 | -23260 | 1 | 1.3197 | 1.3492 | 1.4738 | 1.2886 | 1.5508 | 1.3039 | dw | 1 | 0.91549 | 1.2352 | 1 | 0.90347 | -0.31972 | -0.084512 | -0.23521
[10 empty] | Execution | 358 | S33: 40; S34: 12; S35: 40; S36: 32; S37: 40; S38: 40; S39: 40; S40: 40; S41: 34; S42: 40 | 2022-12-12 | 2022-12-16 | S51 | 28 | 1.0769 | 0 | 98890 | 96644.2 | 25.3256 | 5590 | 127740 | 0.75657 | 0.97729 | 0.90449 | -31095.8 | -2245.8 | 0.77415 | -28850 | 1 | 1.3144 | 1.3218 | 1.3525 | 1.2489 | 1.4613 | 1.272 | dw | 1 | 0.97729 | 1.2917 | 1 | 0.97406 | -0.31445 | -0.02271 | -0.29174
[10 empty] | Retest | 162 | S43: 40; S44: 40; S45: 32; S46: 40; S47: 5; S48: 5 | 2022-12-19 | 2022-12-23 | S52 | 29 | 1.1154 | 0 | 98890 | 98890 | 29 | 4611 | 132351 | 0.74718 | 1 | 1 | -33461 | 0 | 0.74718 | -33461 | FINE | FINE | FINE | FINE | FINE | FINE | FINE | dw | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0 | [39 empty] | 33461
[10 empty] | UAT Support | 219 | S47: 35; S48: 32; S49: 40; S50: 32; S51: 40; S52: 40
[11 empty] | 916 | 0 | 0 | 0 | 0 | 40 | 21 | 44 | 32 | 40 | 40 | 12 | 40 | 32 | 40 | 40 | 40 | 40 | 34 | 40 | 40 | 40 | 32 | 40 | 40 | 37 | 40 | 32 | 40 | 40
[11 empty] | Price List €/h | S24: 29
[11 empty] | FROM | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Software Tester 2 |  | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 0
[10 empty] | Integration | 149 | S28: 15; S29: 32; S30: 22; S31: 40; S32: 40
[10 empty] | Execution | 354 | S33: 32; S34: 32; S35: 16; S36: 40; S37: 40; S38: 41; S39: 40; S40: 38; S41: 32; S42: 39; S43: 4
[10 empty] | Retest | 147 | S43: 23; S44: 40; S45: 24; S46: 40; S47: 12; S48: 8
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT Support | 240 | S42: 1; S43: 17; S45: 8; S47: 32; S48: 30; S49: 40; S50: 32; S51: 40; S52: 40
[11 empty] | 890 | 0 | 0 | 0 | 0 | 15 | 32 | 22 | 40 | 40 | 32 | 32 | 16 | 40 | 40 | 41 | 40 | 38 | 32 | 40 | 44 | 40 | 32 | 40 | 44 | 38 | 40 | 32 | 40 | 40
[11 empty] | Price List €/h | S24: 30
[11 empty] | FROM | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Test Analyst 1 |  | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 212 | S24: 40; S25: 40; S26: 40; S27: 40; S28: 12; S29: 16; S30: 24
[10 empty] | Integration | 0
[10 empty] | Execution | 314 | S33: 22; S34: 12; S36: 40; S37: 40; S38: 40; S39: 40; S40: 40; S41: 40; S42: 40
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | Reporting activities | 148 | S33: 18; S34: 28; S35: 6; S43: 15; S44: 32; S45: 8; S46: 22; S47: 13; S48: 6
[10 empty] | UAT Support | 141 | S43: 15; S44: 8; S45: 24; S46: 18; S47: 16; S49: 12; S50: 16; S51: 24; S52: 8
[11 empty] | 815 | 40 | 40 | 40 | 40 | 12 | 16 | 24 | 0 | 0 | 40 | 40 | 6 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 30 | 40 | 32 | 40 | 29 | 6 | 12 | 16 | 24 | 8
[11 empty] | Price List €/h | S24: 32
[11 empty] | FROM | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Test Analyst 2 |  | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 153 | S24: 24; S25: 40; S26: 16; S27: 41; S28: 8; S29: 8; S30: 16
[10 empty] | Integration | 0
[10 empty] | Execution | 392 | S33: 40; S34: 40; S35: 24; S36: 40; S37: 40; S38: 40; S39: 40; S40: 40; S41: 40; S42: 40; S43: 8
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT Support | 344 | S43: 32; S44: 24; S45: 16; S46: 40; S47: 40; S48: 40; S49: 40; S50: 32; S51: 40; S52: 40
[11 empty] | 889 | 24 | 40 | 16 | 41 | 8 | 8 | 16 | 0 | 0 | 40 | 40 | 24 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 24 | 16 | 40 | 40 | 40 | 40 | 32 | 40 | 40
[11 empty] | Price List €/h | S24: 34
[11 empty] | FROM | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Test Analyst 3 |  | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 199 | S24: 40; S25: 40; S26: 40; S27: 40; S28: 2; S29: 7; S30: 30
[10 empty] | Integration | 0
[10 empty] | Execution | 118 | S34: 2; S35: 16; S36: 2; S37: 2; S38: 16; S39: 16; S40: 16; S41: 16; S42: 16; S43: 16
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | Reporting activities | 291 | S33: 20; S34: 11; S35: 26; S36: 24; S37: 30; S38: 24; S39: 24; S40: 5; S41: 5; S42: 24; S43: 15; S44: 10; S45: 16; S46: 22; S47: 12; S48: 23
[10 empty] | UAT Support | 128 | S49: 40; S50: 24; S51: 40; S52: 24
[11 empty] | 736 | 40 | 40 | 40 | 40 | 2 | 7 | 30 | 0 | 0 | 20 | 13 | 42 | 26 | 32 | 40 | 40 | 21 | 21 | 40 | 31 | 10 | 16 | 22 | 12 | 23 | 40 | 24 | 40 | 24
[11 empty] | Price List €/h | S24: 45
[11 empty] | FROM | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Test Manager |  | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 150 | S33: 4; S34: 8; S35: 4; S36: 10; S37: 10; S38: 10; S39: 16; S40: 24; S41: 20; S42: 28; S43: 16
[10 empty] | Retest | 0
[10 empty] | Management | 193 | 8 | 8 | 8 | 8 |  |  | 12 |  | 30 |  |  | 2 |  | 15 |  |  | 2 |  | 2 |  | 16 |  | 8 | 20 | 5 | 12 | 8 | 14 | 15
[10 empty] | Reporting activities | 0
[10 empty] | UAT Support | 0
[11 empty] | 343 | 8 | 8 | 8 | 8 | 0 | 0 | 12 | 0 | 30 | 4 | 8 | 6 | 10 | 25 | 10 | 16 | 26 | 20 | 30 | 16 | 16 | 0 | 8 | 20 | 5 | 12 | 8 | 14 | 15
[11 empty] | Price List €/h | S24: 28
[11 empty] | FROM | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | PMO |  | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 111 | S24: 5; S25: 8; S27: 6; S32: 7; S33: 5; S35: 16; S37: 24; S38: 3; S39: 3; S40: 2; S42: 8; S44: 8; S45: 16
[10 empty] | Reporting activities | 0
[10 empty] | UAT Support | 0
[11 empty] | 111 | 5 | 8 | 0 | 6 | 0 | 0 | 0 | 0 | 7 | 5 | 0 | 16 | 0 | 24 | 3 | 3 | 2 | 0 | 8 | 0 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | FROM | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | Actual Total Costs | 132351 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 18022 | 3328 | 3840 | 3072 | 3872 | 684 | 974 | 2252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Integration | 6268 | 0 | 0 | 0 | 0 | 875 | 1159 | 1122 | 1512 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Execution | 46930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3488 | 3128 | 2396 | 4510 | 4598 | 5103 | 5344 | 5646 | 5226 | 5855 | 1636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Retest | 6045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1107 | 1600 | 1048 | 1600 | 403 | 287 | 0 | 0 | 0 | 0
[10 empty] | Management | 11793 | 500 | 584 | 360 | 528 | 0 | 0 | 540 | 0 | 1546 | 140 | 0 | 538 | 0 | 1347 | 84 | 84 | 146 | 0 | 314 | 0 | 944 | 448 | 360 | 900 | 225 | 540 | 360 | 630 | 675
[10 empty] | Reporting activities | 14334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220 | 1214 | 1064 | 816 | 1020 | 816 | 816 | 170 | 170 | 816 | 960 | 1300 | 784 | 1408 | 798 | 962 | 0 | 0 | 0 | 0
[10 empty] | UAT Support | 28959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1967 | 1008 | 1464 | 1820 | 3073 | 2502 | 4600 | 3600 | 4960 | 3936
[12 empty] | 3828 | 4424 | 3432 | 4400 | 1559 | 2133 | 3914 | 1512 | 3146 | 4848 | 4342 | 3998 | 5326 | 6965 | 6003 | 6244 | 5962 | 5396 | 7014 | 5670 | 4852 | 3744 | 5188 | 5174 | 3976 | 5140 | 3960 | 5590 | 4611
EARNED VALUE
[11 empty] | FROM | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | %Progress | 100% | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 100% | 10% | 15% | 25% | 38% | 48% | 65% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Integration | 100% | 0% | 0% | 0% | 0% | 15% | 50% | 50% | 78% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Execution | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 17% | 50% | 55% | 65% | 68% | 77% | 80% | 80% | 92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Retest | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 33% | 62% | 77% | 98% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Management | 100% | 3% | 8% | 12% | 15% | 15% | 15% | 20% | 20% | 25% | 29% | 29% | 34% | 39% | 44% | 56% | 58% | 60% | 60% | 64% | 64% | 75% | 82% | 85% | 88% | 92% | 95% | 97% | 99% | 100%
[10 empty] | Reporting activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 15% | 30% | 35% | 39% | 50% | 56% | 62% | 72% | 75% | 79% | 85% | 92% | 95% | 97% | 100% | 100% | 100% | 100% | 100%
[10 empty] | UAT Support | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 25% | 32% | 40% | 45% | 50% | 60% | 70% | 92% | 100%
[12 empty] | 1.272% | 2.211% | 3.569% | 5.144% | 6.762% | 9.897% | 11.85% | 15% | 16.29% | 20.63% | 23.55% | 35.77% | 38.29% | 42.24% | 45.42% | 49.02% | 50.78% | 51.89% | 56.25% | 64.45% | 70.26% | 75.91% | 79.9% | 83.45% | 85.65% | 88.64% | 91.55% | 97.73% | 100%
[11 empty] | FROM | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
[11 empty] | TO | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23
[10 empty] | EV | 98890 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
[10 empty] | Testbook Design | 10000 | 1000 | 1500 | 2500 | 3800 | 4800 | 6500 | 8000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
[10 empty] | Integration | 4000 | 0 | 0 | 0 | 0 | 600 | 2000 | 2000 | 3120 | 3960 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
[10 empty] | Execution | 30310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3031 | 5152.7 | 15155 | 16670.5 | 19701.5 | 20610.8 | 23338.7 | 24248 | 24248 | 27885.2 | 30310 | 30310 | 30310 | 30310 | 30310 | 30310 | 30310 | 30310 | 30310 | 30310
[10 empty] | Retest | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2640 | 4960 | 6160 | 7840 | 8000 | 8000 | 8000 | 8000 | 8000
[10 empty] | Management | 8580 | 257.4 | 686.4 | 1029.6 | 1287 | 1287 | 1287 | 1716 | 1716 | 2145 | 2488.2 | 2488.2 | 2917.2 | 3346.2 | 3775.2 | 4804.8 | 4976.4 | 5148 | 5148 | 5491.2 | 5491.2 | 6435 | 7035.6 | 7293 | 7550.4 | 7893.6 | 8151 | 8322.6 | 8494.2 | 8580
[10 empty] | Reporting activities | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 1650 | 3300 | 3850 | 4290 | 5500 | 6160 | 6820 | 7920 | 8250 | 8690 | 9350 | 10120 | 10450 | 10670 | 11000 | 11000 | 11000 | 11000 | 11000
[10 empty] | UAT Support | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3240 | 6750 | 8640 | 10800 | 12150 | 13500 | 16200 | 18900 | 24840 | 27000
[12 empty] | 1257.4 | 2186.4 | 3529.6 | 5087 | 6687 | 9787 | 11716 | 14836 | 16105 | 20399.2 | 23290.9 | 35372.2 | 37866.7 | 41766.7 | 44915.6 | 48475.1 | 50216 | 51316 | 55626.4 | 63731.2 | 69485 | 75065.6 | 79013 | 82520.4 | 84703.6 | 87661 | 90532.6 | 96644.2 | 98890
Formulas:
Bank 1 = MIN([Bank 1, row below]:C28)

## Project_6
PROJECT OVERVIEW
| Project Name | Project 6 |  | Estimation | yes
| Responsible | Test Manager Green Team |  | Sceduling | yes | [35 empty] | AC(AD) | AC(15) | 29168 |  | Acn(ADn=1) | 0.59039
| Client | Bank 1 | [5 empty] | Business Unit | Financial Services |  | Assumptions
| Area | Crediti | [5 empty] | Prectice | Testing |  | Client charge | Test Manager | 330
| Resource number | 7 | [5 empty] | Sub-practice level 1 | Area Operations |  | €/gg | Tester | 200 | [27 empty] | ADn | 1
| Starting date | 2023-03-13 | [5 empty] | Sub-practice level 2 | Credit Management
| Release (Go live) | 2023-06-30 | [5 empty] | Sub-practice level 3 | Warranties Management
| Main Activities | Desing, DP, Execution, Management and UAT | [5 empty] | Activity Description | Revision, renewal and extincition of the warranties given by the bank to its clients. | [18 empty] | Project Planned Elapsed time
| %completion | 100% | [25 empty] | 15 | weeks
| Next Milestone | N/A
| TM Estimate Name | Estimate 6: Project_6_2022.xls
| Estimate Budget | 54839.55
BASELINE | [28 empty] | Week | Time Unit | TPn | BASELINE | BCWS | EV | ES | Actual Costs | ACWP | CPI | SPI | SPIt | CV | SV | RFI | RV | CEACn=BACn | CEACn=BACn-CVn | CEACn=BCAn/CPI | CEACn=BACn/(CPI*SPI) | CEACn=BACn/ ( .8 CPI + .2 SPI) | CEACn=BACn/(CPI*SPIt) | CEACn=BACn/ ( .8 CPI + .2 SPIt) | WS | WP | ACn | BACn | Esn | CVn | SVn | RVn
[30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[27 empty] | 2023-03-13 | 2023-03-17 | S11 | 1 | 0.066667 | 2495 | 2495 | 1282.625 | 0.51408 | 2731 | 2731 | 0.46965 | 0.51408 | 0.51408 | -1448.375 | -1212.375 | 0.91358 | -236 | 1 | 1.0293 | 2.1292 | 4.1418 | 2.0897 | 4.1418 | 2.0897 | 0.050501 | 0.025961 | 0.055278 | 1 | 0.034272 | -0.029316 | -0.02454 | -0.0047768
[27 empty] | 2023-03-20 | 2023-03-24 | S12 | 2 | 0.13333 | 2495 | 4990 | 4645.25 | 1.8618 | 2160 | 4891 | 0.94975 | 0.93091 | 0.93091 | -245.75 | -344.75 | 1.0202 | 99 | 1 | 1.005 | 1.0529 | 1.131 | 1.0571 | 1.131 | 1.0571 | 0.101 | 0.094024 | 0.098998 | 1 | 0.12412 | -0.0049742 | -0.006978 | 0.0020038
|  | Project Activities | [8 empty] | FROM | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-03-27 | 2023-03-31 | S13 | 3 | 0.2 | 3495 | 8485 | 6347.875 | 2.3885 | 2075 | 6966 | 0.91127 | 0.74813 | 0.79617 | -618.125 | -2137.125 | 1.2181 | 1519 | 1 | 1.0125 | 1.0974 | 1.4668 | 1.1381 | 1.3783 | 1.1258 | 0.17174 | 0.12849 | 0.141 | 1 | 0.15923 | -0.012511 | -0.043257 | 0.030746
|  | Start Date | End Date | Starting week number | Ending week number | FTEs | FTE figure | Weight | Budget x activity |  | TO | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-04-03 | 2023-04-07 | S14 | 4 | 0.26667 | 3495 | 11980 | 12680.5 | 4.2004 | 1736 | 8702 | 1.4572 | 1.0585 | 1.0501 | 3978.5 | 700.5 | 1.3767 | 3278 | 1 | 0.91947 | 0.68625 | 0.64834 | 0.72598 | 0.65351 | 0.72686 | 0.24249 | 0.25666 | 0.17614 | 1 | 0.28003 | 0.080528 | 0.014179 | 0.06635
| Project 6 | 2023-03-13 | 2023-06-23 | 11 | 25 |  |  | 100% | overall budget - allocation plan | Scheduling | € | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | 2023-04-10 | 2023-04-14 | S15 | 5 | 0.33333 | 3495 | 15475 | 15413.125 | 4.9823 | 1356 | 10058 | 1.5324 | 0.996 | 0.99646 | 5355.125 | -61.875 | 1.5386 | 5417 | 1 | 0.89161 | 0.65256 | 0.65518 | 0.70169 | 0.65488 | 0.70164 | 0.31323 | 0.31198 | 0.20358 | 1 | 0.33215 | 0.10839 | -0.0012524 | 0.10964
| Testbook Design | 2023-03-13 | 2023-03-24 | 11 | 12 | 2/day | Test Analyst | 8.096% | 4000 | Testbook Design | 4000 | 2000 | 2000 | [13 empty] | 2023-04-17 | 2023-04-21 | S16 | 6 | 0.4 | 1495 | 16970 | 16445.75 | 5.6493 | 900 | 10958 | 1.5008 | 0.96911 | 0.94156 | 5487.75 | -524.25 | 1.5486 | 6012 | 1 | 0.88892 | 0.66631 | 0.68755 | 0.71712 | 0.70767 | 0.71997 | 0.34349 | 0.33288 | 0.2218 | 1 | 0.37662 | 0.11108 | -0.010611 | 0.12169
| Data preparation | 2023-03-27 | 2023-04-14 | 13 | 15 | 3/day | Test Analyst; Software Tester | 18.22% | 9000 | Data preparation | 9000 |  |  | 3000 | 3000 | 3000 | [10 empty] | 2023-04-24 | 2023-04-28 | S17 | 7 | 0.46667 | 4990 | 21960 | 21843.775 | 6.9767 | 3451 | 14409 | 1.516 | 0.99471 | 0.99667 | 7434.775 | -116.225 | 1.524 | 7551 | 1 | 0.84951 | 0.65964 | 0.66315 | 0.70835 | 0.66184 | 0.70816 | 0.44449 | 0.44214 | 0.29165 | 1 | 0.46511 | 0.15049 | -0.0023525 | 0.15284
| Integration | 2023-04-18 | 2023-04-21 | 16 | 16 | 1/day | Software Tester | 2.024% | 1000 | Integration | 1000 | [5 empty] | 1000 | [9 empty] | 2023-05-01 | 2023-05-05 | S18 | 8 | 0.53333 | 4990 | 26950 | 27211.2 | 8.0523 | 2604 | 17013 | 1.5994 | 1.0097 | 1.0065 | 10198.2 | 261.2 | 1.5841 | 9937 | 1 | 0.79358 | 0.62522 | 0.61922 | 0.675 | 0.62116 | 0.67528 | 0.54549 | 0.55078 | 0.34436 | 1 | 0.53682 | 0.20642 | 0.0052869 | 0.20113
| Execution | 2023-04-24 | 2023-05-19 | 17 | 20 | 3/day+1,5 week | Test Analyst; Software Tester; Test Manager | 28.3% | 13980 | Execution | 13980 | [6 empty] | 3495 | 3495 | 3495 | 3495 | [5 empty] | 2023-05-08 | 2023-05-12 | S19 | 9 | 0.6 | 4990 | 31940 | 29532.625 | 8.5176 | 2288 | 19301 | 1.5301 | 0.92463 | 0.9464 | 10231.625 | -2407.375 | 1.6548 | 12639 | 1 | 0.7929 | 0.65355 | 0.70682 | 0.70972 | 0.69057 | 0.70753 | 0.64649 | 0.59777 | 0.39067 | 1 | 0.56784 | 0.2071 | -0.048727 | 0.25582
| Retest | 2023-05-22 | 2023-05-26 | 21 | 21 | 1/day | Software Tester | 2.024% | 1000 | Retest | 1000 | [10 empty] | 1000 |  |  |  |  | 2023-05-15 | 2023-05-19 | S20 | 10 | 0.66667 | 4990 | 36930 | 33980.65 | 9.4089 | 2350 | 21651 | 1.5695 | 0.92014 | 0.94089 | 12329.65 | -2949.35 | 1.7057 | 15279 | 1 | 0.75044 | 0.63716 | 0.69246 | 0.69463 | 0.67718 | 0.69264 | 0.7475 | 0.6878 | 0.43823 | 1 | 0.62726 | 0.24956 | -0.059697 | 0.30926
| Management | 2023-03-13 | 2023-06-23 | 11 | 25 | 1,5/week | Test Manager | 15.03% | 7425 | Management | 7425 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 2023-05-22 | 2023-05-26 | S21 | 11 | 0.73333 | 2495 | 39425 | 39126 | 10.8802 | 1579 | 23230 | 1.6843 | 0.99242 | 0.98911 | 15896 | -299 | 1.6972 | 16195 | 1 | 0.67825 | 0.59372 | 0.59826 | 0.64687 | 0.60026 | 0.64714 | 0.798 | 0.79194 | 0.4702 | 1 | 0.72534 | 0.32175 | -0.006052 | 0.3278
| ALM maintenance | 2023-05-29 | 2023-06-09 | 22 | 23 | 1,5/day | Software Tester | 6.072% | 3000 | ALM maintenance | 3000 | [11 empty] | 1500 | 1500 |  |  | 2023-05-29 | 2023-06-02 | S22 | 12 | 0.8 | 1995 | 41420 | 41345.75 | 11.9628 | 984 | 24214 | 1.7075 | 0.99821 | 0.9969 | 17131.75 | -74.25 | 1.7106 | 17206 | 1 | 0.65324 | 0.58565 | 0.5867 | 0.63871 | 0.58747 | 0.63882 | 0.83838 | 0.83687 | 0.49011 | 1 | 0.79752 | 0.34676 | -0.0015029 | 0.34826
| Reporting activities | 2023-04-24 | 2023-05-26 | 17 | 21 | 1/day | Test Analyst | 10.12% | 5000 | Reporting activities | 5000 | [6 empty] | 1000 | 1000 | 1000 | 1000 | 1000 |  |  |  |  | 2023-06-05 | 2023-06-09 | S23 | 13 | 0.86667 | 1995 | 43415 | 43365.5 | 12.9752 | 701 | 24915 | 1.7405 | 0.99886 | 0.99809 | 18450.5 | -49.5 | 1.7425 | 18500 | 1 | 0.62655 | 0.57454 | 0.57519 | 0.62806 | 0.57563 | 0.62812 | 0.87876 | 0.87776 | 0.5043 | 1 | 0.86501 | 0.37345 | -0.0010019 | 0.37446
| UAT support | 2023-06-12 | 2023-06-23 | 24 | 25 | 2,5/day | Test Analyst; Software Tester | 10.12% | 5000 | UAT support | 5000 | [13 empty] | 2500 | 2500 | 2023-06-12 | 2023-06-16 | S24 | 14 | 0.93333 | 2995 | 46410 | 46885.25 | 14.1587 | 1952 | 26867 | 1.7451 | 1.0102 | 1.0113 | 20018.25 | 475.25 | 1.7274 | 19543 | 1 | 0.59481 | 0.57304 | 0.56723 | 0.62574 | 0.56662 | 0.62565 | 0.93938 | 0.949 | 0.54381 | 1 | 0.94391 | 0.40519 | 0.0096195 | 0.39557
[11 empty] | 49405 | 2495 | 2495 | 3495 | 3495 | 3495 | 1495 | 4990 | 4990 | 4990 | 4990 | 2495 | 1995 | 1995 | 2995 | 2995 | 2023-06-19 | 2023-06-23 | S25 | 15 | 1 | 2995 | 49405 | 49405 | 15 | 2301 | 29168 | 1.6938 | 1 | 1 | 20237 | 0 | 1.6938 | 20237 | 1 | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE
[10 empty] | Contingency up to the project type | 5434.55
>10%--> highly risk project
btw 5% and 10% --> medium risk project
<5% --> low risk project
ACTUAL COSTS
[11 empty] | Price List €/h | 11
[11 empty] | FROM | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
[11 empty] | TO | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23
[10 empty] | Software Tester 1 (stage) |  | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 112 | S13: 40; S14: 40; S15: 32
[10 empty] | Integration | 0
[10 empty] | Execution | 152 | S17: 40; S18: 32; S19: 40; S20: 40
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 64 | S22: 32; S23: 32
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 80 | S24: 40; S25: 40
[11 empty] | 408 | 0 | 0 | 40 | 40 | 32 | 0 | 40 | 32 | 40 |  | 0 | 32 | 32 | 40 | 40
[11 empty] | Price List €/h | S11: 11
[11 empty] | FROM | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
[11 empty] | TO | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23
[10 empty] | Software Tester 2 (stage) |  | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 92 | S13: 32; S14: 40; S15: 20
[10 empty] | Integration | 60 | S16: 44; S17: 16
[10 empty] | Execution | 0
[10 empty] | Retest | 37 | S21: 29; S22: 8
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 23 | S22: 8; S23: 15
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 212 | 0 | 0 | 32 | 40 | 20 | 44 | 16 | 0 | 0 |  | 29 | 16 | 15 | 0 | 0
[11 empty] | Price List €/h | S11: 28
[11 empty] | FROM | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
[11 empty] | TO | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23
[10 empty] | Test Analyst 1 |  | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25
[10 empty] | Testbook Design | 64 | S11: 32; S12: 32
[10 empty] | Data preparation | 76 | S13: 24; S14: 24; S15: 28
[10 empty] | Integration | 0
[10 empty] | Execution | 104 | S17: 35; S18: 32; S19: 16; S20: 16; S21: 5
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 66 | S24: 34; S25: 32
[11 empty] | 310 | 32 | 32 | 24 | 24 | 28 | 0 | 35 | 32 | 16 |  | 5 | 0 | 0 | 34 | 32
[11 empty] | Price List €/h | S11: 28
[11 empty] | FROM | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
[11 empty] | TO | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23
[10 empty] | Test Analyst 2 |  | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25
[10 empty] | Testbook Design | 88 | S11: 40; S12: 32; S13: 16
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 112 | S17: 24; S18: 24; S19: 25; S20: 39
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 83 | S17: 16; S18: 8; S19: 14; S20: 5; S21: 40
[10 empty] | UAT support | 40 | S24: 20; S25: 20
[11 empty] | 323 | 40 | 32 | 16 | 0 | 0 | 0 | 40 | 32 | 39 | 44 | 40 | 0 | 0 | 20 | 20
[11 empty] | Price List €/h | S11: 46
[11 empty] | FROM | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
[11 empty] | TO | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23
[10 empty] | Test Manager |  | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 27 | S17: 10; S18: 10; S19: 2; S20: 5
[10 empty] | Retest | 0
[10 empty] | Management | 34 | S11: 12; S12: 8; S14: 4; S16: 2; S22: 4; S23: 4
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 61 | 12 | 8 | 0 | 4 | 0 | 2 | 10 | 10 | 2 |  | 0 | 4 | 4 | 0 | 0
[11 empty] | Price List €/h | S11: 55
[11 empty] | FROM | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
[11 empty] | TO | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23
[10 empty] | Service Manager |  | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 9 | S11: 1; S13: 1; S17: 5; S22: 2
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 9 | 1 | 0 | 1 | 0 | 0 | 0 | 5 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0
[11 empty] | Price List €/h | S11: 27
[11 empty] | FROM | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
[11 empty] | TO | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23
[10 empty] | PMO |  | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 49 | S11: 4; S13: 4; S16: 12; S19: 8; S22: 6; S25: 15
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 49 | 4 | 0 | 4 | 0 | 0 | 12 | 0 | 0 | 8 | 0 | 0 | 6 | 0 | 0 | 15
[11 empty] | FROM | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
[11 empty] | TO | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23
[10 empty] | Actual Total Costs | 29168 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25
[10 empty] | Testbook Design | 4256 | 2016 | 1792 | 448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Data preparation | 4372 | 0 | 0 | 1464 | 1552 | 1356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Integration | 660 | 0 | 0 | 0 | 0 | 0 | 484 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Execution | 8962 | 0 | 0 | 0 | 0 | 0 | 0 | 2552 | 2380 | 1680 | 2210 | 140 | 0 | 0 | 0 | 0
[10 empty] | Retest | 407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319 | 88 | 0 | 0 | 0
[10 empty] | Management | 3382 | 715 | 368 | 163 | 184 | 0 | 416 | 275 | 0 | 216 | 0 | 0 | 456 | 184 | 0 | 405
[10 empty] | ALM maintenance | 957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 517 | 0 | 0
[10 empty] | Reporting activities | 2324 | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 224 | 392 | 140 | 1120 | 0 | 0 | 0 | 0
[10 empty] | UAT support | 3848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1952 | 1896
[12 empty] | 2731 | 2160 | 2075 | 1736 | 1356 | 900 | 3451 | 2604 | 2288 | 2350 | 1579 | 984 | 701 | 1952 | 2301
EARNED VALUE
[11 empty] | FROM | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
[11 empty] | TO | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23
[10 empty] | %Progress | 100% | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25
[10 empty] | Testbook Design | 100% | 20% | 92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Data preparation | 100% | 0% | 0% | 10% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Integration | 100% | 0% | 0% | 0% | 0% | 0% | 55% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Execution | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 23% | 49% | 55% | 78% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Retest | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80% | 100% | 100% | 100% | 100%
[10 empty] | Management | 100% | 6.5% | 13% | 19.5% | 26% | 32.5% | 39% | 45.5% | 52% | 58.5% | 65% | 72% | 79% | 86% | 93% | 100%
[10 empty] | ALM maintenance | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%
[10 empty] | Reporting activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 70% | 85% | 100% | 100% | 100% | 100% | 100%
[10 empty] | UAT support | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 60% | 100%
[12 empty] | 2.596% | 9.402% | 12.85% | 25.67% | 31.2% | 33.29% | 44.21% | 55.08% | 59.78% | 68.78% | 79.19% | 83.69% | 87.78% | 94.9% | 100%
[11 empty] | FROM | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
[11 empty] | TO | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23
[10 empty] | EV | 49405 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25
[10 empty] | Testbook Design | 4000 | 800 | 3680 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
[10 empty] | Data preparation | 9000 | 0 | 0 | 900 | 6750 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000
[10 empty] | Integration | 1000 | 0 | 0 | 0 | 0 | 0 | 550 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
[10 empty] | Execution | 13980 | 0 | 0 | 0 | 0 | 0 | 0 | 3215.4 | 6850.2 | 7689 | 10904.4 | 13980 | 13980 | 13980 | 13980 | 13980
[10 empty] | Retest | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 1000 | 1000 | 1000 | 1000
[10 empty] | Management | 7425 | 482.625 | 965.25 | 1447.875 | 1930.5 | 2413.125 | 2895.75 | 3378.375 | 3861 | 4343.625 | 4826.25 | 5346 | 5865.75 | 6385.5 | 6905.25 | 7425
[10 empty] | ALM maintenance | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 3000 | 3000 | 3000
[10 empty] | Reporting activities | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 2500 | 3500 | 4250 | 5000 | 5000 | 5000 | 5000 | 5000
[10 empty] | UAT support | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 5000
[12 empty] | 1282.625 | 4645.25 | 6347.875 | 12680.5 | 15413.125 | 16445.75 | 21843.775 | 27211.2 | 29532.625 | 33980.65 | 39126 | 41345.75 | 43365.5 | 46885.25 | 49405
Formulas:
Test Manager = [Test Manager, row above]+4
Bank 1 = MIN([Bank 1, row below]:C30)

## Project_7
PROJECT OVERVIEW
| Project Name | Project 7 |  | Estimation | yes
| Responsible | Test Manager Blue Team |  | Sceduling | yes | [48 empty] | AC(AD) | AC(28) | 75290 |  | Acn(ADn=1,08) | 0.91963
| Client | Bank 1 | [5 empty] | Business Unit | Financial Services |  | Assumptions
| Area | Crediti | [5 empty] | Prectice | Testing |  | Client charge | Test Manager | 330
| Resource number | 6 | [5 empty] | Sub-practice level 1 | Area Operations |  | €/gg | Tester | 200 | [40 empty] | ADn | 1.0769
| Starting date | 2023-01-04 | [5 empty] | Sub-practice level 2 | Credit Management
| Release (Go live) | 2023-06-30 | [5 empty] | Sub-practice level 3 | Post Granting activities
| Main Activities | Desing, Execution, Management and UAT | [5 empty] | Activity Description | Subrogation, rate variations, partial extinctions, management of credit variations during the credit elapsed time. | [31 empty] | Project Planned Elapsed time
| %completion | 100% | [38 empty] | 26 | weeks
| Next Milestone | N/A
| TM Estimate Name | Estimate 7: Project_7_.xls
| Estimate Budget | 87600.9
BASELINE | [41 empty] | Week | Time Unit | TPn | BASELINE | BCWS | EV | ES | Actual Costs | ACWP | CPI | SPI | SPIt | CV | SV | RFI | RV | CEACn=BACn | CEACn=BACn-CVn | CEACn=BCAn/CPI | CEACn=BACn/(CPI*SPI) | CEACn=BACn/ ( .8 CPI + .2 SPI) | CEACn=BACn/(CPI*SPIt) | CEACn=BACn/ ( .8 CPI + .2 SPIt) |  | WS | WP | ACn | BACn | Esn | CVn | SVn | RVn
[43 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[40 empty] | 2023-01-02 | 2023-01-06 | S1 | 1 | 0.038462 | 1365 | 1365 | 1380 | 1.0069 | 2582 | 2582 | 0.53447 | 1.011 | 1.0069 | -1202 | 15 | 0.52866 | -1217 | 1 | 1.0147 | 1.871 | 1.8507 | 1.5879 | 1.8581 | 1.5899 |  | 0.016673 | 0.016856 | 0.031538 | 1 | 0.038728 | -0.014682 | 0.00018322 | -0.014865
[40 empty] | 2023-01-09 | 2023-01-13 | S2 | 2 | 0.076923 | 2165 | 3530 | 2287.6 | 1.4261 | 2294 | 4876 | 0.46916 | 0.64805 | 0.71307 | -2588.4 | -1242.4 | 0.72395 | -1346 | 1 | 1.0316 | 2.1315 | 3.2891 | 1.9805 | 2.9892 | 1.9307 |  | 0.043117 | 0.027942 | 0.059558 | 1 | 0.054852 | -0.031616 | -0.015175 | -0.016441
|  | Project Activities | [8 empty] | FROM | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 |  |  | 2023-01-16 | 2023-01-20 | S3 | 3 | 0.11538 | 2165 | 5695 | 5403.2 | 2.8652 | 2522 | 7398 | 0.73036 | 0.94876 | 0.95507 | -1994.8 | -291.8 | 0.7698 | -1703 | 1 | 1.0244 | 1.3692 | 1.4431 | 1.2919 | 1.4336 | 1.2898 |  | 0.069561 | 0.065997 | 0.090363 | 1 | 0.1102 | -0.024365 | -0.0035642 | -0.020801
|  | Start Date | End Date | Starting week number | Ending week number | FTEs | FTE figure | Weight | Budget x activity |  | TO | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 |  |  | 2023-01-23 | 2023-01-27 | S4 | 4 | 0.15385 | 2165 | 7860 | 6034.8 | 3.157 | 2182 | 9580 | 0.62994 | 0.76779 | 0.78924 | -3545.2 | -1825.2 | 0.82046 | -1720 | 1 | 1.0433 | 1.5875 | 2.0676 | 1.5209 | 2.0114 | 1.511 |  | 0.096006 | 0.073712 | 0.11701 | 1 | 0.12142 | -0.043303 | -0.022294 | -0.021009
| Project 7 | 2023-01-04 | 2023-06-29 | 1 | 26 |  |  | 100% | overall budget - allocation plan | Scheduling | € | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | DELAY | DELAY | 2023-01-30 | 2023-02-03 | S5 | 5 | 0.19231 | 2165 | 10025 | 8046.4 | 4.0861 | 2642 | 12222 | 0.65835 | 0.80263 | 0.81722 | -4175.6 | -1978.6 | 0.82024 | -2197 | 1 | 1.051 | 1.5189 | 1.8924 | 1.4552 | 1.8587 | 1.449 |  | 0.12245 | 0.098283 | 0.14929 | 1 | 0.15716 | -0.051003 | -0.024168 | -0.026835
| Testbook Design | 2023-01-04 | 2023-02-03 | 1 | 5 | 2/day | Test Analyst | 11.24% | 9200 | Testbook Design | 9200 | 1200 | 2000 | 2000 | 2000 | 2000 | [23 empty] | 2023-02-06 | 2023-02-10 | S6 | 6 | 0.23077 | 4330 | 14355 | 11122 | 5.2533 | 3184 | 15406 | 0.72193 | 0.77478 | 0.87556 | -4284 | -3233 | 0.93178 | -1051 | 1 | 1.0523 | 1.3852 | 1.7878 | 1.3652 | 1.5821 | 1.3286 |  | 0.17534 | 0.13585 | 0.18818 | 1 | 0.20205 | -0.052327 | -0.039489 | -0.012837
| Execution | 2023-02-08 | 2023-04-27 | 6 | 17 | 3/day+0,5/week | Software Tester; Test Analyst; Test Manager | 45.66% | 37380 | Execution | 37380 | [5 empty] | 3165 | 3165 | 3165 | 3165 | 3165 | 3165 | 3165 | 3165 | 3165 | 3165 | 3165 | 2565 | [11 empty] | 2023-02-13 | 2023-02-17 | S7 | 7 | 0.26923 | 4330 | 18685 | 14648.6 | 6.0678 | 3672 | 19078 | 0.76783 | 0.78398 | 0.86683 | -4429.4 | -4036.4 | 0.9794 | -393 | 1 | 1.0541 | 1.3024 | 1.6612 | 1.2969 | 1.5025 | 1.2696 |  | 0.22823 | 0.17893 | 0.23303 | 1 | 0.23338 | -0.054103 | -0.049303 | -0.0048003
| Retest | 2023-05-03 | 2023-05-19 | 18 | 20 | 2/day | Software Tester | 7.329% | 6000 | Retest | 6000 | [17 empty] | 2000 | 2000 | 2000 | [8 empty] | 2023-02-20 | 2023-02-24 | S8 | 8 | 0.30769 | 4330 | 23015 | 23046.2 | 8.0072 | 3566 | 22644 | 1.0178 | 1.0014 | 1.0009 | 402.2 | 31.2 | 1.0164 | 371 | 1 | 0.99509 | 0.98255 | 0.98122 | 0.98573 | 0.98166 | 0.98581 |  | 0.28112 | 0.2815 | 0.27658 | 1 | 0.30797 | 0.0049127 | 0.00038109 | 0.0045316
| Management | 2023-01-04 | 2023-06-29 | 1 | 26 | 0,5/week | Test Manager | 5.24% | 4290 | Management | 4290 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 |  |  | 2023-02-27 | 2023-03-03 | S9 | 9 | 0.34615 | 4330 | 27345 | 28453.4 | 9.256 | 3112 | 25756 | 1.1047 | 1.0405 | 1.0284 | 2697.4 | 1108.4 | 1.0617 | 1589 | 1 | 0.96705 | 0.9052 | 0.86994 | 0.91584 | 0.88017 | 0.91788 |  | 0.33401 | 0.34754 | 0.3146 | 1 | 0.356 | 0.032947 | 0.013539 | 0.019409
| Reporting activities | 2023-02-08 | 2023-05-19 | 6 | 20 | 1/day | Test Analyst | 18.32% | 15000 | Reporting activities | 15000 | [5 empty] | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | [8 empty] | 2023-03-06 | 2023-03-10 | S10 | 10 | 0.38462 | 4330 | 31675 | 30496.4 | 9.7278 | 3652 | 29408 | 1.037 | 0.96279 | 0.97278 | 1088.4 | -1178.6 | 1.0771 | 2267 | 1 | 0.98671 | 0.96431 | 1.0016 | 0.97831 | 0.99129 | 0.97641 |  | 0.38689 | 0.3725 | 0.3592 | 1 | 0.37415 | 0.013294 | -0.014396 | 0.02769
| UAT support | 2023-05-29 | 2023-06-29 | 22 | 26 | 2/day | Software Tester | 12.21% | 10000 | UAT support | 10000 | [21 empty] | 2000 | 2000 | 2000 | 2000 | 2000 |  |  | 2023-03-13 | 2023-03-17 | S11 | 11 | 0.42308 | 4330 | 36005 | 34408.4 | 10.6313 | 2742 | 32150 | 1.0702 | 0.95566 | 0.96648 | 2258.4 | -1596.6 | 1.1199 | 3855 | 1 | 0.97241 | 0.93436 | 0.97772 | 0.95481 | 0.96677 | 0.95284 |  | 0.43978 | 0.42028 | 0.3927 | 1 | 0.4089 | 0.027585 | -0.019502 | 0.047087
[11 empty] | 81870 | 1365 | 2165 | 2165 | 2165 | 2165 | 4330 | 4330 | 4330 | 4330 | 4330 | 4330 | 4330 | 4330 | 4330 | 4330 | 4330 | 3730 | 3165 | 3165 | 3165 | 165 | 2165 | 2165 | 2165 | 2165 | 2165 |  |  | 2023-03-20 | 2023-03-24 | S12 | 12 | 0.46154 | 4330 | 40335 | 36825.2 | 11.1894 | 2908 | 35058 | 1.0504 | 0.91298 | 0.93245 | 1767.2 | -3509.8 | 1.1505 | 5277 | 1 | 0.97841 | 0.95201 | 1.0427 | 0.97759 | 1.021 | 0.97388 |  | 0.49267 | 0.4498 | 0.42822 | 1 | 0.43036 | 0.021585 | -0.04287 | 0.064456
[10 empty] | Contingency up to the project type | 5730.9 | [28 empty] | 2023-03-27 | 2023-03-31 | S13 | 13 | 0.5 | 4330 | 44665 | 42606.2 | 12.5245 | 3560 | 38618 | 1.1033 | 0.95391 | 0.96343 | 3988.2 | -2058.8 | 1.1566 | 6047 | 1 | 0.95129 | 0.90639 | 0.95019 | 0.93162 | 0.9408 | 0.92997 |  | 0.54556 | 0.52041 | 0.4717 | 1 | 0.48171 | 0.048714 | -0.025147 | 0.073861
[10 empty] | >10%--> highly risk project | [29 empty] | 2023-04-03 | 2023-04-07 | S14 | 14 | 0.53846 | 4330 | 48995 | 49584.8 | 14.1362 | 3744 | 42362 | 1.1705 | 1.012 | 1.0097 | 7222.8 | 589.8 | 1.1566 | 6633 | 1 | 0.91178 | 0.85433 | 0.84417 | 0.87811 | 0.8461 | 0.87847 |  | 0.59845 | 0.60565 | 0.51743 | 1 | 0.5437 | 0.088223 | 0.0072041 | 0.081019
[10 empty] | btw 5% and 10% --> medium risk project | [29 empty] | 2023-04-10 | 2023-04-14 | S15 | 15 | 0.57692 | 4330 | 53325 | 54320.6 | 15.2299 | 3280 | 45642 | 1.1901 | 1.0187 | 1.0153 | 8678.6 | 995.6 | 1.1683 | 7683 | 1 | 0.894 | 0.84023 | 0.82483 | 0.86516 | 0.82755 | 0.86566 |  | 0.65134 | 0.6635 | 0.55749 | 1 | 0.58577 | 0.106 | 0.012161 | 0.093844
[10 empty] | <5% --> low risk project | [29 empty] | 2023-04-17 | 2023-04-21 | S16 | 16 | 0.61538 | 4330 | 57655 | 57935 | 16.0751 | 3560 | 49202 | 1.1775 | 1.0049 | 1.0047 | 8733 | 280 | 1.1718 | 8453 | 1 | 0.89333 | 0.84926 | 0.84516 | 0.87492 | 0.8453 | 0.87494 |  | 0.70423 | 0.70765 | 0.60098 | 1 | 0.61827 | 0.10667 | 0.0034201 | 0.10325
ACTUAL COSTS | [39 empty] | 2023-04-24 | 2023-04-28 | S17 | 17 | 0.65385 | 3730 | 61385 | 59306.6 | 16.4428 | 4026 | 53228 | 1.1142 | 0.96614 | 0.96722 | 6078.6 | -2078.4 | 1.1532 | 8157 | 1 | 0.92575 | 0.89751 | 0.92896 | 0.92201 | 0.92792 | 0.92183 |  | 0.74979 | 0.7244 | 0.65015 | 1 | 0.63241 | 0.074247 | -0.025387 | 0.099634
[40 empty] | 2023-05-01 | 2023-05-05 | S18 | 18 | 0.69231 | 3165 | 64550 | 62178.2 | 17.2506 | 2680 | 55908 | 1.1122 | 0.96326 | 0.95837 | 6270.2 | -2371.8 | 1.1546 | 8642 | 1 | 0.92341 | 0.89916 | 0.93346 | 0.9239 | 0.93822 | 0.92473 |  | 0.78845 | 0.75947 | 0.68289 | 1 | 0.66349 | 0.076587 | -0.02897 | 0.10556
[40 empty] | 2023-05-08 | 2023-05-12 | S19 | 19 | 0.73077 | 3165 | 67715 | 66291.2 | 18.5501 | 4210 | 60118 | 1.1027 | 0.97897 | 0.97632 | 6173.2 | -1423.8 | 1.1264 | 7597 | 1 | 0.9246 | 0.90688 | 0.92636 | 0.92769 | 0.92887 | 0.92815 |  | 0.8271 | 0.80971 | 0.73431 | 1 | 0.71347 | 0.075402 | -0.017391 | 0.092793
[11 empty] | Price List €/h | 11 | [27 empty] | 2023-05-15 | 2023-05-19 | S20 | 20 | 0.76923 | 3165 | 70880 | 68920.4 | 19.3809 | 2440 | 62558 | 1.1017 | 0.97235 | 0.96904 | 6362.4 | -1959.6 | 1.133 | 8322 | 1 | 0.92229 | 0.90768 | 0.93349 | 0.92951 | 0.93668 | 0.93008 |  | 0.86576 | 0.84183 | 0.76411 | 1 | 0.74542 | 0.077713 | -0.023936 | 0.10165
[11 empty] | FROM | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-05-22 | 2023-05-26 | S21 | 21 | 0.80769 | 165 | 71045 | 69632 | 19.6057 | 2064 | 64622 | 1.0775 | 0.98011 | 0.9336 | 5010 | -1413 | 1.0994 | 6423 | 1 | 0.93881 | 0.92805 | 0.94688 | 0.94514 | 0.99405 | 0.95352 |  | 0.86778 | 0.85052 | 0.78932 | 1 | 0.75406 | 0.061195 | -0.017259 | 0.078454
[11 empty] | TO | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-05-29 | 2023-06-02 | S22 | 22 | 0.84615 | 2165 | 73210 | 73683.6 | 22.2188 | 1458 | 66080 | 1.1151 | 1.0065 | 1.0099 | 7603.6 | 473.6 | 1.1079 | 7130 | 1 | 0.90713 | 0.89681 | 0.89104 | 0.91462 | 0.88798 | 0.91404 |  | 0.89422 | 0.90001 | 0.80713 | 1 | 0.85457 | 0.092874 | 0.0057848 | 0.087089
[10 empty] | Software Tester 1 (stage) |  | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | 2023-06-05 | 2023-06-09 | S23 | 23 | 0.88462 | 2165 | 75375 | 76855.2 | 23.6837 | 796 | 66876 | 1.1492 | 1.0196 | 1.0297 | 9979.2 | 1480.2 | 1.1271 | 8499 | 1 | 0.87811 | 0.87016 | 0.8534 | 0.89023 | 0.84504 | 0.88864 |  | 0.92067 | 0.93875 | 0.81686 | 1 | 0.91091 | 0.12189 | 0.01808 | 0.10381
[10 empty] | Testbook Design | 0 | [28 empty] | 2023-06-12 | 2023-06-16 | S24 | 24 | 0.92308 | 2165 | 77540 | 77526.8 | 23.9939 | 1618 | 68494 | 1.1319 | 0.99983 | 0.99975 | 9032.8 | -13.2 | 1.1321 | 9046 | 1 | 0.88967 | 0.88349 | 0.88364 | 0.90459 | 0.88371 | 0.90461 |  | 0.94711 | 0.94695 | 0.83662 | 1 | 0.92284 | 0.11033 | -0.00016123 | 0.11049
[10 empty] | Execution | 550 | S6: 40; S7: 40; S8: 40; S9: 40; S10: 32; S11: 40; S12: 24; S13: 40; S14: 40; S15: 32; S16: 40; S17: 40; S18: 24; S19: 38; S20: 40 | 2023-06-19 | 2023-06-23 | S25 | 25 | 0.96154 | 2165 | 79705 | 79198.4 | 24.766 | 1100 | 69594 | 1.138 | 0.99364 | 0.99064 | 9604.4 | -506.6 | 1.1453 | 10111 | 1 | 0.88269 | 0.87873 | 0.88435 | 0.9016 | 0.88703 | 0.90209 |  | 0.97356 | 0.96737 | 0.85005 | 1 | 0.95254 | 0.11731 | -0.0061879 | 0.1235
[10 empty] | Retest | 42 | S18: 8; S19: 6; S21: 20; S22: 8 | 2023-06-26 | 2023-06-30 | S26 | 26 | 1 | 2165 | 81870 | 79870 | 25.0762 | 1590 | 71184 | 1.122 | 0.97557 | 0.96447 | 8686 | -2000 | 1.1501 | 10686 | 1 | 0.8939 | 0.89125 | 0.91357 | 0.91514 | 0.92408 | 0.917 |  | 1 | 0.97557 | 0.86948 | 1 | 0.96447 | 0.1061 | -0.024429 | 0.13052
[10 empty] | Management | 0 | [28 empty] | 2023-07-03 | 2023-07-07 | S27 | 27 | 1.0385 | 0 | 81870 | 80570 | 25.3995 | 1959 | 73143 | 1.1015 | 0.98412 | 0.94072 | 7427 | -1300 | 1.1193 | 8727 | 1 | 0.90928 | 0.90782 | 0.92247 | 0.92759 | 0.96502 | 0.93512 | dw | 1 | 0.98412 | 0.8934 | 1 | 0.97691 | 0.090717 | -0.015879 | 0.1066
[10 empty] | Reporting activities | 0 | [28 empty] | 2023-07-10 | 2023-07-14 | S28 | 28 | 1.0769 | 0 | 81870 | 81870 | 28 | 2147 | 75290 | 1.0874 | 1 | 1 | 6580 | 0 | 1.0874 | 6580 | 1 | FINE | FINE | FINE | FINE | FINE | FINE | dw | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE
[10 empty] | UAT support | 248 | S22: 32; S23: 16; S24: 42; S25: 38; S26: 40; S27: 40; S28: 40
[11 empty] | 840 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 32 | 40 | 24 | 40 | 40 | 32 | 40 | 40 | 32 | 44 | 40 | 20 | 40 | 16 | 42 | 38 | 40 | 40 | 40
[11 empty] | Price List €/h | S1: 22
[11 empty] | FROM | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10
[11 empty] | TO | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14
[10 empty] | Software Tester 2 (apprenticeship) |  | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28
[10 empty] | Testbook Design | 0
[10 empty] | Execution | 487 | S6: 12; S7: 40; S8: 22; S9: 40; S10: 34; S11: 41; S12: 24; S13: 40; S14: 36; S15: 32; S16: 40; S17: 40; S18: 24; S19: 38; S20: 24
[10 empty] | Retest | 84 | S18: 8; S19: 2; S20: 16; S21: 50; S22: 8
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 247 | S22: 32; S23: 24; S24: 40; S25: 31; S26: 40; S27: 42; S28: 38
[11 empty] | 818 | 0 | 0 | 0 | 0 | 0 | 12 | 40 | 22 | 40 | 34 | 41 | 24 | 40 | 36 | 32 | 40 | 40 | 32 | 40 | 40 | 50 | 40 | 24 | 40 | 31 | 40
[11 empty] | Price List €/h | S1: 28
[11 empty] | FROM | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10
[11 empty] | TO | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14
[10 empty] | Test Analyst 1 |  | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28
[10 empty] | Testbook Design | 244 | S1: 32; S2: 40; S3: 40; S4: 38; S5: 38; S6: 24; S7: 32
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | Reporting activities | 528 | S6: 16; S7: 8; S8: 40; S9: 40; S10: 40; S11: 40; S12: 40; S13: 40; S14: 40; S15: 32; S16: 40; S17: 40; S18: 32; S19: 40; S20: 40
[10 empty] | UAT support | 0
[11 empty] | 772 | 32 | 40 | 40 | 38 | 38 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Price List €/h | S1: 28
[11 empty] | FROM | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10
[11 empty] | TO | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14
[10 empty] | Test Analyst 2 |  | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28
[10 empty] | Testbook Design | 229 | S1: 32; S2: 40; S3: 35; S4: 38; S5: 38; S6: 42; S7: 4
[10 empty] | Execution | 412 | S7: 40; S8: 42; S9: 24; S10: 38; S11: 10; S12: 18; S13: 40; S14: 30; S15: 32; S16: 40; S17: 32; S18: 26; S19: 40
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 641 | 32 | 40 | 35 | 38 | 38 | 42 | 44 | 42 | 24 | 38 | 10 | 18 | 40 | 30 | 32 | 40 | 32 | 26 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Price List €/h | S1: 46
[11 empty] | FROM | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10
[11 empty] | TO | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14
[10 empty] | Test Manager |  | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28
[10 empty] | Testbook Design | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 147 | S1: 16; S3: 8; S5: 10; S6: 4; S8: 4; S10: 8; S12: 6; S14: 12; S17: 15; S19: 12; S21: 15; S22: 3; S23: 2; S24: 6; S27: 10; S28: 16
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 147 | 16 | 0 | 8 | 0 | 10 | 4 | 0 | 4 | 0 | 8 | 0 | 6 | 0 | 12 | 0 | 0 | 15 | 0 | 12 | 0 | 15 | 3 | 2 | 6 | 0 | 0
[11 empty] | Price List €/h | S1: 27
[11 empty] | FROM | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10
[11 empty] | TO | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14
[10 empty] | PMO |  | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28
[10 empty] | Testbook Design | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 64 | S1: 2; S2: 2; S3: 2; S4: 2; S5: 2; S8: 6; S12: 8; S15: 16; S19: 2; S21: 2; S26: 10; S27: 5; S28: 5
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 64 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 6 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 10
[11 empty] | FROM | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10
[11 empty] | TO | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14
[10 empty] | Actual Total Costs | 75290 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28
[10 empty] | Testbook Design | 13244 | 1792 | 2240 | 2100 | 2128 | 2128 | 1848 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Execution | 28300 | 0 | 0 | 0 | 0 | 0 | 704 | 2440 | 2100 | 1992 | 2164 | 1622 | 1296 | 2440 | 2072 | 1952 | 2440 | 2216 | 1520 | 2374 | 968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Retest | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 110 | 352 | 1320 | 264 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Management | 8490 | 790 | 54 | 422 | 54 | 514 | 184 | 0 | 346 | 0 | 368 | 0 | 492 | 0 | 552 | 432 | 0 | 690 | 0 | 606 | 0 | 744 | 138 | 92 | 276 | 0 | 270 | 595 | 871
[10 empty] | Reporting activities | 14784 | 0 | 0 | 0 | 0 | 0 | 448 | 224 | 1120 | 1120 | 1120 | 1120 | 1120 | 1120 | 1120 | 896 | 1120 | 1120 | 896 | 1120 | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | UAT support | 8162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056 | 704 | 1342 | 1100 | 1320 | 1364 | 1276
[12 empty] | 2582 | 2294 | 2522 | 2182 | 2642 | 3184 | 3672 | 3566 | 3112 | 3652 | 2742 | 2908 | 3560 | 3744 | 3280 | 3560 | 4026 | 2680 | 4210 | 2440 | 2064 | 1458 | 796 | 1618 | 1100 | 1590 | 1959 | 2147
EARNED VALUE
[11 empty] | FROM | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10
[11 empty] | TO | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14
[10 empty] | %Progress | 100% | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28
[10 empty] | Testbook Design | 100% | 15% | 23% | 55% | 60% | 80% | 92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Execution | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 25% | 37% | 40% | 48% | 52% | 65% | 80% | 89% | 95% | 95% | 95% | 98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Retest | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 52% | 68% | 77% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Management | 100% | 0% | 4% | 8% | 12% | 16% | 20% | 24% | 28% | 32% | 36% | 40% | 44% | 48% | 52% | 56% | 60% | 64% | 68% | 72% | 76% | 80% | 84% | 88% | 92% | 96% | 100% | 100% | 100%
[10 empty] | Reporting activities | 100% | 0% | 0% | 0% | 0% | 0% | 12% | 17% | 22% | 27% | 32% | 37% | 42% | 47% | 55% | 63% | 71% | 79% | 87% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | UAT support | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 55% | 60% | 75% | 80% | 87% | 100%
[12 empty] | 1.686% | 2.794% | 6.6% | 7.371% | 9.828% | 13.58% | 17.89% | 28.15% | 34.75% | 37.25% | 42.03% | 44.98% | 52.04% | 60.57% | 66.35% | 70.76% | 72.44% | 75.95% | 80.97% | 84.18% | 85.05% | 90% | 93.87% | 94.7% | 96.74% | 97.56% | 98.41% | 100%
[11 empty] | FROM | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10
[11 empty] | TO | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14
[10 empty] | EV | 81870 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28
[10 empty] | Testbook Design | 9200 | 1380 | 2116 | 5060 | 5520 | 7360 | 8464 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200
[10 empty] | Execution | 37380 | 0 | 0 | 0 | 0 | 0 | 0 | 1869 | 9345 | 13830.6 | 14952 | 17942.4 | 19437.6 | 24297 | 29904 | 33268.2 | 35511 | 35511 | 35511 | 36632.4 | 37380 | 37380 | 37380 | 37380 | 37380 | 37380 | 37380 | 37380 | 37380
[10 empty] | Retest | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 3120 | 4080 | 4620 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
[10 empty] | Management | 4290 | 0 | 171.6 | 343.2 | 514.8 | 686.4 | 858 | 1029.6 | 1201.2 | 1372.8 | 1544.4 | 1716 | 1887.6 | 2059.2 | 2230.8 | 2402.4 | 2574 | 2745.6 | 2917.2 | 3088.8 | 3260.4 | 3432 | 3603.6 | 3775.2 | 3946.8 | 4118.4 | 4290 | 4290 | 4290
[10 empty] | Reporting activities | 15000 | 0 | 0 | 0 | 0 | 0 | 1800 | 2550 | 3300 | 4050 | 4800 | 5550 | 6300 | 7050 | 8250 | 9450 | 10650 | 11850 | 13050 | 14250 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
[10 empty] | UAT support | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 5500 | 6000 | 7500 | 8000 | 8700 | 10000
[12 empty] | 1380 | 2287.6 | 5403.2 | 6034.8 | 8046.4 | 11122 | 14648.6 | 23046.2 | 28453.4 | 30496.4 | 34408.4 | 36825.2 | 42606.2 | 49584.8 | 54320.6 | 57935 | 59306.6 | 62178.2 | 66291.2 | 68920.4 | 69632 | 73683.6 | 76855.2 | 77526.8 | 79198.4 | 79870 | 80570 | 81870
Formulas:
Test Manager = [Test Manager, row above]+4
Bank 1 = MIN([Bank 1, row below]:C27)

## Project_8
PROJECT OVERVIEW
| Project Name | Project 8 |  | Estimation | yes
| Responsible | Test Manager Blue Team |  | Sceduling | yes |  |  |  |  | Assumptions | [34 empty] | AC(AD) | AC(19) | 51378 |  | Acn(ADn=1,06) | 1.4099
| Client | Bank 1 | [5 empty] | Business Unit | Financial Services | Client charge | Test Manager | 330
| Area | Crediti | [5 empty] | Prectice | Testing | €/gg | Tester | 200
| Resource number | 5 | [5 empty] | Sub-practice level 1 | Area Operations | [35 empty] | ADn | 1.0556
| Starting date | 2023-02-20 | [5 empty] | Sub-practice level 2 | Credit Management | [21 empty] | Project Planned Elapsed time
| Release (Go live) | 2023-06-23 | [5 empty] | Sub-practice level 3 | Credit Extincition | [21 empty] | 18 | weeks
| Main Activities | Desing, Execution, and Management | [5 empty] | Activity Description | Activities with the aim of extinguish the credit and its relative warranties.
| %completion | 100%
| Next Milestone | N/A
| TM Estimate Name | Estimate 8: Project_8_.xls
| Estimate Budget | 30284.8
BASELINE | [32 empty] | Week | Time Unit | TPn | BASELINE | BCWS | EV | ES | Actual Costs | ACWP | CPI | SPI | SPIt | CV | SV | RFI | RV | CEACn=BACn | CEACn=BACn-CVn | CEACn=BCAn/CPI | CEACn=BACn/(CPI*SPI) | CEACn=BACn/ ( .8 CPI + .2 SPI) | CEACn=BACn/(CPI*SPIt) | CEACn=BACn/ ( .8 CPI + .2 SPIt) |  | WS | WP | ACn | BACn | Esn | CVn | SVn | RVn
[34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 2023-02-20 | 2023-02-24 | S8 | 1 | 0.055556 | 1330 | 1330 | 788.88 | 0.59314 | 1677 | 1677 | 0.47041 | 0.59314 | 0.59314 | -888.12 | -541.12 | 0.79308 | -347 | 1 | 1.0244 | 2.1258 | 3.584 | 2.0204 | 3.584 | 2.0204 |  | 0.036498 | 0.021649 | 0.046021 | 1 | 0.032952 | -0.024372 | -0.01485 | -0.0095225
[31 empty] | 2023-02-27 | 2023-03-03 | S9 | 2 | 0.11111 | 1330 | 2660 | 1497.76 | 1.1261 | 1200 | 2877 | 0.5206 | 0.56307 | 0.56307 | -1379.24 | -1162.24 | 0.92457 | -217 | 1 | 1.0378 | 1.9209 | 3.4114 | 1.89 | 3.4114 | 1.89 |  | 0.072997 | 0.041102 | 0.078952 | 1 | 0.062563 | -0.03785 | -0.031895 | -0.005955
|  | Project Activities | [8 empty] | FROM | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 |  | 2023-03-06 | 2023-03-10 | S10 | 3 | 0.16667 | 1330 | 3990 | 2926.64 | 2.2005 | 1696 | 4573 | 0.63998 | 0.73349 | 0.73349 | -1646.36 | -1063.36 | 0.87251 | -583 | 1 | 1.0452 | 1.5625 | 2.1303 | 1.5182 | 2.1303 | 1.5182 |  | 0.1095 | 0.080314 | 0.12549 | 1 | 0.12225 | -0.04518 | -0.029181 | -0.015999
|  | Start Date | End Date | Starting week number | Ending week number | FTEs | FTE figure | Weight | Budget x activity |  | TO | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 |  | 2023-03-13 | 2023-03-17 | S11 | 4 | 0.22222 | 1330 | 5320 | 3635.52 | 2.7335 | 1387 | 5960 | 0.60999 | 0.68337 | 0.68337 | -2324.48 | -1684.48 | 0.89262 | -640 | 1 | 1.0638 | 1.6394 | 2.399 | 1.6009 | 2.399 | 1.6009 |  | 0.14599 | 0.099767 | 0.16356 | 1 | 0.15186 | -0.063789 | -0.046226 | -0.017563
| Project 8 | 2023-02-20 | 2023-06-23 | 8 | 25 |  |  | 100% | overall budget - allocation plan | Scheduling | € | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | DELAY | 2023-03-20 | 2023-03-24 | S12 | 5 | 0.27778 | 330 | 5650 | 4544.4 | 3.4168 | 1250 | 7210 | 0.63029 | 0.80432 | 0.68337 | -2665.6 | -1105.6 | 0.78363 | -1560 | 1 | 1.0732 | 1.5866 | 1.9726 | 1.5035 | 2.3217 | 1.5603 |  | 0.15505 | 0.12471 | 0.19786 | 1 | 0.18982 | -0.07315 | -0.03034 | -0.04281
| Testbook Design | 2023-02-20 | 2023-03-17 | 8 | 11 | 1 | Test Analyst | 10.98% | 4000 | Testbook Design | 4000 | 1000 | 1000 | 1000 | 1000 | [15 empty] | 2023-03-27 | 2023-03-31 | S13 | 6 | 0.33333 | 2830 | 8480 | 6478.28 | 5.2927 | 3380 | 10590 | 0.61174 | 0.76395 | 0.88211 | -4111.72 | -2001.72 | 0.80076 | -2110 | 1 | 1.1128 | 1.6347 | 2.1398 | 1.5572 | 1.8532 | 1.5019 |  | 0.23271 | 0.17778 | 0.29061 | 1 | 0.29404 | -0.11284 | -0.054932 | -0.057903
| Execution | 2023-03-27 | 2023-05-12 | 13 | 19 | 2/day | Test Analyst; Software Tester | 38.42% | 14000 | Execution | 14000 | [5 empty] | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | [7 empty] | 2023-04-03 | 2023-04-07 | S14 | 7 | 0.38889 | 2830 | 11310 | 8342.16 | 5.9513 | 2733 | 13323 | 0.62615 | 0.73759 | 0.85018 | -4980.84 | -2967.84 | 0.84891 | -2013 | 1 | 1.1367 | 1.5971 | 2.1652 | 1.5422 | 1.8785 | 1.4904 |  | 0.31037 | 0.22893 | 0.36561 | 1 | 0.33063 | -0.13669 | -0.081445 | -0.055241
| Retest | 2023-05-15 | 2023-06-23 | 20 | 25 | 1/day | Software Tester | 16.47% | 6000 | Retest | 6000 | [12 empty] | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 2023-04-10 | 2023-04-14 | S15 | 8 | 0.44444 | 2830 | 14140 | 10151.04 | 6.5905 | 1888 | 15211 | 0.66735 | 0.7179 | 0.82381 | -5059.96 | -3988.96 | 0.92959 | -1071 | 1 | 1.1389 | 1.4985 | 2.0873 | 1.4761 | 1.8189 | 1.4314 |  | 0.38804 | 0.27857 | 0.41743 | 1 | 0.36614 | -0.13886 | -0.10947 | -0.029391
| Management | 2023-02-20 | 2023-06-23 | 8 | 25 | 1/week | Test Manager | 16.3% | 5940 | Management | 5940 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 |  | 2023-04-17 | 2023-04-21 | S16 | 9 | 0.5 | 2830 | 16970 | 11764.92 | 7.1607 | 3163 | 18374 | 0.6403 | 0.69328 | 0.79564 | -6609.08 | -5205.08 | 0.92359 | -1404 | 1 | 1.1814 | 1.5618 | 2.2527 | 1.5363 | 1.9629 | 1.4895 |  | 0.4657 | 0.32286 | 0.50423 | 1 | 0.39782 | -0.18137 | -0.14284 | -0.038529
| Reporting activities | 2023-03-27 | 2023-06-23 | 13 | 25 | 0,5/day | Test Analyst | 17.84% | 6500 | Reporting activities | 6500 | [5 empty] | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 |  | 2023-04-24 | 2023-04-28 | S17 | 10 | 0.55556 | 2830 | 19800 | 14213.8 | 8.0261 | 2254 | 20628 | 0.68905 | 0.71787 | 0.80261 | -6414.2 | -5586.2 | 0.95986 | -828 | 1 | 1.176 | 1.4513 | 2.0216 | 1.4392 | 1.8082 | 1.405 |  | 0.54336 | 0.39006 | 0.56608 | 1 | 0.44589 | -0.17602 | -0.1533 | -0.022722
[11 empty] | 36440 | 1330 | 1330 | 1330 | 1330 | 330 | 2830 | 2830 | 2830 | 2830 | 2830 | 2830 | 2830 | 1830 | 1830 | 1830 | 1830 | 1830 | 1830 |  | 2023-05-01 | 2023-05-05 | S18 | 11 | 0.61111 | 2830 | 22630 | 15937.68 | 8.6352 | 2688 | 23316 | 0.68355 | 0.70427 | 0.78502 | -7378.32 | -6692.32 | 0.97058 | -686 | 1 | 1.2025 | 1.4629 | 2.0772 | 1.4541 | 1.8636 | 1.4208 |  | 0.62102 | 0.43737 | 0.63985 | 1 | 0.47973 | -0.20248 | -0.18365 | -0.018825
[10 empty] | Contingency up to the project type | -6155.2 | [19 empty] | 2023-05-08 | 2023-05-12 | S19 | 12 | 0.66667 | 2830 | 25460 | 18866.56 | 9.6702 | 2706 | 26022 | 0.72502 | 0.74103 | 0.80585 | -7155.44 | -6593.44 | 0.9784 | -562 | 1 | 1.1964 | 1.3793 | 1.8613 | 1.3732 | 1.7116 | 1.3492 |  | 0.69868 | 0.51774 | 0.71411 | 1 | 0.53723 | -0.19636 | -0.18094 | -0.015423
[10 empty] | >10%--> highly risk project | [20 empty] | 2023-05-15 | 2023-05-19 | S20 | 13 | 0.72222 | 1830 | 27290 | 21930.44 | 10.7528 | 2848 | 28870 | 0.75963 | 0.80361 | 0.82714 | -6939.56 | -5359.56 | 0.94527 | -1580 | 1 | 1.1904 | 1.3164 | 1.6382 | 1.3014 | 1.5916 | 1.2934 |  | 0.7489 | 0.60182 | 0.79226 | 1 | 0.59738 | -0.19044 | -0.14708 | -0.043359
[10 empty] | btw 5% and 10% --> medium risk project | [20 empty] | 2023-05-22 | 2023-05-26 | S21 | 14 | 0.77778 | 1830 | 29120 | 25224.32 | 11.9167 | 3928 | 32798 | 0.76908 | 0.86622 | 0.85119 | -7573.68 | -3895.68 | 0.88786 | -3678 | 1 | 1.2078 | 1.3003 | 1.5011 | 1.2682 | 1.5276 | 1.2731 |  | 0.79912 | 0.69222 | 0.90005 | 1 | 0.66204 | -0.20784 | -0.10691 | -0.10093
[10 empty] | <5% --> low risk project | [20 empty] | 2023-05-29 | 2023-06-02 | S22 | 15 | 0.83333 | 1830 | 30950 | 27138.2 | 12.917 | 3288 | 36086 | 0.75204 | 0.87684 | 0.86114 | -8947.8 | -3811.8 | 0.85767 | -5136 | 1 | 1.2455 | 1.3297 | 1.5165 | 1.287 | 1.5441 | 1.2922 |  | 0.84934 | 0.74474 | 0.99029 | 1 | 0.71761 | -0.24555 | -0.1046 | -0.14094
ACTUAL COSTS | [30 empty] | 2023-06-05 | 2023-06-09 | S23 | 16 | 0.88889 | 1830 | 32780 | 29702.08 | 14.3181 | 4124 | 40210 | 0.73867 | 0.9061 | 0.89488 | -10507.92 | -3077.92 | 0.81522 | -7430 | 1 | 1.2884 | 1.3538 | 1.4941 | 1.2951 | 1.5128 | 1.2988 |  | 0.89956 | 0.8151 | 1.1035 | 1 | 0.79545 | -0.28836 | -0.084465 | -0.2039
[31 empty] | 2023-06-12 | 2023-06-16 | S24 | 17 | 0.94444 | 1830 | 34610 | 31605.96 | 15.3584 | 3752 | 43962 | 0.71894 | 0.9132 | 0.90344 | -12356.04 | -3004.04 | 0.78727 | -9352 | 1 | 1.3391 | 1.3909 | 1.5231 | 1.3196 | 1.5396 | 1.323 |  | 0.94978 | 0.86734 | 1.2064 | 1 | 0.85325 | -0.33908 | -0.082438 | -0.25664
[31 empty] | 2023-06-19 | 2023-06-23 | S25 | 18 | 1 | 1830 | 36440 | 34629.84 | 17.0108 | 3488 | 47450 | 0.72982 | 0.95032 | 0.94505 | -12820.16 | -1810.16 | 0.76797 | -11010 | 1 | 1.3518 | 1.3702 | 1.4418 | 1.2921 | 1.4499 | 1.2939 |  | 1 | 0.95032 | 1.3021 | 1 | 0.94505 | -0.35182 | -0.049675 | -0.30214
[31 empty] | 2023-06-26 | 2023-06-30 | S26 | 19 | 1.0556 | 0 | 36440 | 36440 | 19 | 3928 | 51378 | 0.70925 | 1 | 1 | -14938 | 0 | 0.70925 | -14938 | FINE | FINE | FINE | FINE | FINE | FINE | FINE | dw | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE
[11 empty] | Price List €/h | 28
[11 empty] | FROM | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | Software Tester 1 |  | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 0
[10 empty] | Execution | 41 | S21: 8; S22: 16; S23: 12; S24: 5
[10 empty] | Retest | 238 | S20: 40; S21: 32; S22: 16; S23: 35; S24: 35; S25: 40; S26: 40
[10 empty] | Management | 0
[10 empty] | Reporting activities | 90 | S13: 16; S14: 24; S15: 8; S16: 8; S17: 2; S18: 24; S19: 8
[11 empty] | 369 | 0 | 0 | 0 | 0 | 0 | 16 | 24 | 8 | 8 | 2 | 24 | 8 | 40 | 40 | 32 | 47 | 40 | 40 | 40
[11 empty] | Price List €/h | S8: 22
[11 empty] | FROM | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | Software Tester 2 (apprenticeship) |  | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 0
[10 empty] | Execution | 394 | [5 empty] | 40 | 38 | 32 | 32 | 44 | 32 | 40 | 24 | 24 | 24 | 32 | 32
[10 empty] | Retest | 28 | S25: 12; S26: 16
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0
[11 empty] | 422 | 0 | 0 | 0 | 0 | 0 | 40 | 38 | 32 | 32 | 44 | 32 | 40 | 24 | 24 | 24 | 32 | 32 | 12 | 16
[11 empty] | Price List €/h | S8: 30
[11 empty] | FROM | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | Test Analyst 1 |  | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 252 | S8: 40; S9: 40; S10: 40; S11: 32; S12: 40; S13: 28; S14: 32
[10 empty] | Execution | 323 | [5 empty] | 10 | 8 | 32 | 40 | 41 | 24 | 40 | 32 | 24 | 16 | 16 | 40
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | Reporting activities | 156 | S13: 4; S18: 8; S20: 8; S21: 16; S22: 16; S23: 24; S25: 40; S26: 40
[11 empty] | 731 | 40 | 40 | 40 | 32 | 40 | 42 | 40 | 32 | 40 | 41 | 32 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40
[11 empty] | Price List €/h | S8: 44
[11 empty] | FROM | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | Test Manager |  | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 178 | 8 |  | 9 | 8 |  | 18 |  |  | 15 |  | 8 | 8 |  | 20 | 16 | 16 | 12 | 16 | 24
[10 empty] | Reporting activities | 0
[11 empty] | 178 | 8 | 0 | 9 | 8 | 0 | 18 | 0 | 0 | 15 | 0 | 8 | 8 | 0 | 20 | 16 | 16 | 12 | 16 | 24
[11 empty] | Price List €/h | S8: 25
[11 empty] | FROM | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | PMO |  | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 80 | 5 |  | 4 | 3 | 2 |  | 1 |  | 15 |  |  | 2 |  | 8 | 8 | 8 | 8 | 8 | 8
[10 empty] | Reporting activities | 0
[11 empty] | 80 | 5 | 0 | 4 | 3 | 2 | 0 | 1 | 0 | 15 | 0 | 0 | 2 | 0 | 8 | 8 | 8 | 8 | 8 | 8
[11 empty] | FROM | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | Actual Total Costs | 51378 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 7560 | 1200 | 1200 | 1200 | 960 | 1200 | 840 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Execution | 19506 | 0 | 0 | 0 | 0 | 0 | 1180 | 1076 | 1664 | 1904 | 2198 | 1424 | 2080 | 1488 | 1472 | 1456 | 1520 | 2044 | 0 | 0
[10 empty] | Retest | 7280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120 | 896 | 448 | 980 | 980 | 1384 | 1472
[10 empty] | Management | 9832 | 477 | 0 | 496 | 427 | 50 | 792 | 25 | 0 | 1035 | 0 | 352 | 402 | 0 | 1080 | 904 | 904 | 728 | 904 | 1256
[10 empty] | Reporting activities | 7200 | 0 | 0 | 0 | 0 | 0 | 568 | 672 | 224 | 224 | 56 | 912 | 224 | 240 | 480 | 480 | 720 | 0 | 1200 | 1200
[12 empty] | 1677 | 1200 | 1696 | 1387 | 1250 | 3380 | 2733 | 1888 | 3163 | 2254 | 2688 | 2706 | 2848 | 3928 | 3288 | 4124 | 3752 | 3488 | 3928
EARNED VALUE
[11 empty] | FROM | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | %Progress | 100% | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 100% | 12% | 22% | 50% | 60% | 75% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Execution | 100% | 0% | 0% | 0% | 0% | 0% | 5% | 10% | 17% | 24% | 30% | 35% | 50% | 60% | 75% | 82% | 82% | 89% | 95% | 100%
[10 empty] | Retest | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 20% | 25% | 55% | 62% | 90% | 100%
[10 empty] | Management | 100% | 5.2% | 10.4% | 15.6% | 20.8% | 26% | 31.2% | 36.4% | 41.6% | 46.8% | 52% | 57.2% | 62.4% | 67.6% | 72.8% | 78% | 83.2% | 88.4% | 93.6% | 100%
[10 empty] | Reporting activities | 100% | 0% | 0% | 0% | 0% | 0% | 5% | 12% | 20% | 25% | 45% | 56% | 64% | 71% | 80% | 85% | 92% | 95% | 98% | 100%
[12 empty] | 2.165% | 4.11% | 8.031% | 9.977% | 12.47% | 17.78% | 22.89% | 27.86% | 32.29% | 39.01% | 43.74% | 51.77% | 60.18% | 69.22% | 74.47% | 81.51% | 86.73% | 95.03% | 100%
[11 empty] | FROM | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | EV | 36440 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 4000 | 480 | 880 | 2000 | 2400 | 3000 | 3600 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
[10 empty] | Execution | 14000 | 0 | 0 | 0 | 0 | 0 | 700 | 1400 | 2380 | 3360 | 4200 | 4900 | 7000 | 8400 | 10500 | 11480 | 11480 | 12460 | 13300 | 14000
[10 empty] | Retest | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 1200 | 1500 | 3300 | 3720 | 5400 | 6000
[10 empty] | Management | 5940 | 308.88 | 617.76 | 926.64 | 1235.52 | 1544.4 | 1853.28 | 2162.16 | 2471.04 | 2779.92 | 3088.8 | 3397.68 | 3706.56 | 4015.44 | 4324.32 | 4633.2 | 4942.08 | 5250.96 | 5559.84 | 5940
[10 empty] | Reporting activities | 6500 | 0 | 0 | 0 | 0 | 0 | 325 | 780 | 1300 | 1625 | 2925 | 3640 | 4160 | 4615 | 5200 | 5525 | 5980 | 6175 | 6370 | 6500
[12 empty] | 788.88 | 1497.76 | 2926.64 | 3635.52 | 4544.4 | 6478.28 | 8342.16 | 10151.04 | 11764.92 | 14213.8 | 15937.68 | 18866.56 | 21930.44 | 25224.32 | 27138.2 | 29702.08 | 31605.96 | 34629.84 | 36440
Formulas:
Project Planned Elapsed time = [Project Planned Elapsed time, row above]+7
Week = CONCATENATE("S",WEEKNUM([Project Planned Elapsed time]))
Bank 1 = MIN([Bank 1, row below]:C26)

## Project_9
PROJECT OVERVIEW
| Project Name | Project 9 |  | Estimation | yes
| Responsible | Test Manager Blue Team |  | Sceduling | yes | [17 empty] | Assumptions | [24 empty] | AC(AD) | AC(21) | 84704.5 |  | Acn(ADn=1,17) | 1.0186
| Client | Bank 1 | [5 empty] | Business Unit | Financial Services | [13 empty] | Client charge | Test Manager | 330
| Area | Crediti | [5 empty] | Prectice | Testing | [13 empty] | €/gg | Tester | 200
| Resource number | 9 | [5 empty] | Sub-practice level 1 | Area Operations | [38 empty] | ADn | 1.1667
| Starting date | 2023-03-01 | [5 empty] | Sub-practice level 2 | Credit Management
| Release (Go live) | 2023-06-30 | [5 empty] | Sub-practice level 3 | Credit Revision
| Main Activities | Desing, DP, Execution, Management and UAT | [5 empty] | Activity Description | Activities with the aim of reviewing the lending/mortages. In particular the persistence of conditions that had determined the credit concessions to the client have to be reverified and confirmed. The guarantor presence continuity is one of the main. | [23 empty] | Project Planned Elapsed time
| %completion | 100% | [30 empty] | 18 | weeks
| Next Milestone | N/A
| TM Estimate Name | Estimate : Project_9_.xls
| Estimate Budget | 85654.8
BASELINE | [34 empty] | Week | Time Unit | TPn | BASELINE | BCWS | EV | ES | Actual Costs | ACWP | CPI | SPI | SPIt | CV | SV | RFI | RV | CEACn=BACn | CEACn=BACn-CVn | CEACn=BCAn/CPI | CEACn=BACn/(CPI*SPI) | CEACn=BACn/ ( .8 CPI + .2 SPI) | CEACn=BACn/(CPI*SPIt) | CEACn=BACn/ ( .8 CPI + .2 SPIt) |  | WS | WP | ACn | BACn | Esn | CVn | SVn | RVn
[36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[33 empty] | 2023-02-27 | 2023-03-03 | S9 | 1 | 0.055556 | 2295 | 2295 | 1597.68 | 0.69616 | 4261 | 4261 | 0.37495 | 0.69616 | 0.69616 | -2663.32 | -697.32 | 0.53861 | -1966 | 1 | 1.032 | 2.667 | 3.831 | 2.2769 | 3.831 | 2.2769 |  | 0.027597 | 0.019212 | 0.051239 | 1 | 0.038675 | -0.032026 | -0.0083853 | -0.023641
[33 empty] | 2023-03-06 | 2023-03-10 | S10 | 2 | 0.11111 | 5495 | 7790 | 5965.36 | 1.6679 | 4163 | 8424 | 0.70814 | 0.76577 | 0.83397 | -2458.64 | -1824.64 | 0.92474 | -634 | 1 | 1.0296 | 1.4122 | 1.8441 | 1.3895 | 1.6933 | 1.3637 |  | 0.093675 | 0.071734 | 0.1013 | 1 | 0.092664 | -0.029565 | -0.021941 | -0.0076239
|  | Project Activities | [8 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 |  |  |  | 2023-03-13 | 2023-03-17 | S11 | 3 | 0.16667 | 5495 | 13285 | 12603.04 | 2.8759 | 4614 | 13038 | 0.96664 | 0.94867 | 0.95863 | -434.96 | -681.96 | 1.0189 | 247 | 1 | 1.0052 | 1.0345 | 1.0905 | 1.0384 | 1.0792 | 1.0362 |  | 0.15975 | 0.15155 | 0.15678 | 1 | 0.15977 | -0.0052304 | -0.0082006 | 0.0029702
|  | Start Date | End Date | Starting week number | Ending week number | FTEs | FTE figure | Weight | Budget x activity |  | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 |  |  |  | 2023-03-20 | 2023-03-24 | S12 | 4 | 0.22222 | 2495 | 15780 | 14710.72 | 3.5714 | 3068 | 16106 | 0.91337 | 0.93224 | 0.89286 | -1395.28 | -1069.28 | 0.97976 | -326 | 1 | 1.0168 | 1.0948 | 1.1744 | 1.0903 | 1.2262 | 1.0998 |  | 0.18975 | 0.1769 | 0.19367 | 1 | 0.19841 | -0.016778 | -0.012858 | -0.0039202
| Project 9 | 2023-03-01 | 2023-06-30 | 9 | 26 |  |  | 100% | overall budget - allocation plan | Scheduling | € | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | DELAY | DELAY | DELAY | 2023-03-27 | 2023-03-31 | S13 | 5 | 0.27778 | 2495 | 18275 | 17938.4 | 4.8651 | 832 | 16938 | 1.0591 | 0.98158 | 0.97302 | 1000.4 | -336.6 | 1.0789 | 1337 | 1 | 0.98797 | 0.94423 | 0.96195 | 0.95825 | 0.97042 | 0.95983 |  | 0.21976 | 0.21571 | 0.20368 | 1 | 0.27028 | 0.01203 | -0.0040476 | 0.016077
| Testbook Design | 2023-03-01 | 2023-03-17 | 9 | 11 | 3/day | Test Analyst | 9.38% | 7800 | Testbook Design | 7800 | 1800 | 3000 | 3000 | [18 empty] | 2023-04-03 | 2023-04-07 | S14 | 6 | 0.33333 | 2495 | 20770 | 20366.08 | 5.8381 | 2152 | 19090 | 1.0668 | 0.98055 | 0.97302 | 1276.08 | -403.92 | 1.088 | 1680 | 1 | 0.98466 | 0.93734 | 0.95593 | 0.95276 | 0.96334 | 0.95413 |  | 0.24976 | 0.2449 | 0.22956 | 1 | 0.32434 | 0.015345 | -0.0048571 | 0.020202
| Data preparation | 2023-03-06 | 2023-03-31 | 10 | 13 | 2/day | Test Analyst; Software Tester | 9.62% | 8000 | Data preparation | 8000 |  | 2000 | 2000 | 2000 | 2000 | [16 empty] | 2023-04-10 | 2023-04-14 | S15 | 7 | 0.38889 | 2495 | 23265 | 22793.76 | 6.8111 | 1494 | 20584 | 1.1074 | 0.97974 | 0.97302 | 2209.76 | -471.24 | 1.1302 | 2681 | 1 | 0.97343 | 0.90305 | 0.92172 | 0.92436 | 0.9281 | 0.92551 |  | 0.27976 | 0.2741 | 0.24752 | 1 | 0.3784 | 0.026572 | -0.0056667 | 0.032239
| Integration | 2023-04-03 | 2023-04-14 | 14 | 15 | 2/day | Software Tester | 4.81% | 4000 | Integration | 4000 | [5 empty] | 2000 | 2000 | [14 empty] | 2023-04-17 | 2023-04-21 | S16 | 8 | 0.44444 | 6495 | 29760 | 31381.44 | 8.2496 | 4664 | 25248 | 1.2429 | 1.0545 | 1.0312 | 6133.44 | 1621.44 | 1.1787 | 4512 | 1 | 0.92625 | 0.80455 | 0.76298 | 0.82971 | 0.78021 | 0.83293 |  | 0.35786 | 0.37736 | 0.30361 | 1 | 0.45831 | 0.073755 | 0.019498 | 0.054257
| Execution | 2023-04-17 | 2023-05-19 | 16 | 20 | 5/day | Test Analyst; Software Tester | 30.06% | 25000 | Execution | 25000 | [7 empty] | 5000 | 5000 | 5000 | 5000 | 5000 | [9 empty] | 2023-04-24 | 2023-04-28 | S17 | 9 | 0.5 | 6495 | 36255 | 34049.12 | 8.6604 | 5325 | 30573 | 1.1137 | 0.93916 | 0.96226 | 3476.12 | -2205.88 | 1.1859 | 5682 | 1 | 0.9582 | 0.89791 | 0.95608 | 0.92696 | 0.93312 | 0.92301 |  | 0.43597 | 0.40944 | 0.36764 | 1 | 0.48113 | 0.0418 | -0.026526 | 0.068326
| Retest | 2023-05-22 | 2023-05-31 | 21 | 22 | 2/day | Software Tester | 3.848% | 3200 | Retest | 3200 | [12 empty] | 2000 | 1200 | [7 empty] | 2023-05-01 | 2023-05-05 | S18 | 10 | 0.55556 | 6495 | 42750 | 38886.8 | 9.4052 | 4638 | 35211 | 1.1044 | 0.90963 | 0.94052 | 3675.8 | -3863.2 | 1.2141 | 7539 | 1 | 0.9558 | 0.90547 | 0.99543 | 0.93858 | 0.96274 | 0.93317 |  | 0.51407 | 0.46761 | 0.42341 | 1 | 0.52251 | 0.044202 | -0.046455 | 0.090657
| Management | 2023-03-01 | 2023-06-30 | 9 | 26 | 1,5/week | Test Manager | 10.71% | 8910 | Management | 8910 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 |  |  |  | 2023-05-08 | 2023-05-12 | S19 | 11 | 0.61111 | 6495 | 49245 | 43790.48 | 10.1602 | 5190 | 40401 | 1.0839 | 0.88924 | 0.92365 | 3389.48 | -5454.52 | 1.2189 | 8844 | 1 | 0.95924 | 0.9226 | 1.0375 | 0.95697 | 0.99886 | 0.95071 |  | 0.59217 | 0.52658 | 0.48582 | 1 | 0.56446 | 0.040759 | -0.065591 | 0.10635
| ALM maintenance | 2023-05-22 | 2023-05-31 | 21 | 22 | 1,5/day | Software Tester | 2.886% | 2400 | ALM maintenance | 2400 | [12 empty] | 1500 | 900 | [7 empty] | 2023-05-15 | 2023-05-19 | S20 | 12 | 0.66667 | 6495 | 55740 | 46982.16 | 10.6516 | 5928 | 46329 | 1.0141 | 0.84288 | 0.88763 | 653.16 | -8757.84 | 1.2031 | 9411 | 1 | 0.99215 | 0.9861 | 1.1699 | 1.0206 | 1.1109 | 1.0113 |  | 0.67027 | 0.56496 | 0.55711 | 1 | 0.59176 | 0.0078543 | -0.10531 | 0.11317
| Reporting activities | 2023-04-17 | 2023-05-31 | 16 | 22 | 1/day | Test Analyst | 7.937% | 6600 | Reporting activities | 6600 | [7 empty] | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 600 | [7 empty] | 2023-05-22 | 2023-05-26 | S21 | 13 | 0.72222 | 4995 | 60735 | 49219.84 | 10.9961 | 7270.5 | 53599.5 | 0.91829 | 0.8104 | 0.84586 | -4379.66 | -11515.16 | 1.1331 | 7135.5 | 1 | 1.0527 | 1.089 | 1.3438 | 1.1152 | 1.2874 | 1.1064 |  | 0.73034 | 0.59187 | 0.64453 | 1 | 0.6109 | -0.052665 | -0.13847 | 0.085804
| UAT support | 2023-06-01 | 2023-06-30 | 22 | 26 | 2,5/day | Test Analyst; Software Tester | 20.74% | 17250 | UAT support | 17250 | [13 empty] | 2250 | 3750 | 3750 | 3750 | 3750 |  |  |  | 2023-05-29 | 2023-06-02 | S22 | 14 | 0.77778 | 5445 | 66180 | 52297.52 | 11.47 | 5592 | 59191.5 | 0.88353 | 0.79023 | 0.81928 | -6893.98 | -13882.48 | 1.1181 | 6988.5 | 1 | 1.0829 | 1.1318 | 1.4323 | 1.1562 | 1.3815 | 1.1485 |  | 0.79582 | 0.62888 | 0.71178 | 1 | 0.63722 | -0.0829 | -0.16694 | 0.084037
[11 empty] | 83160 | 2295 | 5495 | 5495 | 2495 | 2495 | 2495 | 2495 | 6495 | 6495 | 6495 | 6495 | 6495 | 4995 | 5445 | 4245 | 4245 | 4245 | 4245 |  |  |  | 2023-06-05 | 2023-06-09 | S23 | 15 | 0.83333 | 4245 | 70425 | 58960.2 | 12.6447 | 6352 | 65543.5 | 0.89956 | 0.83721 | 0.84298 | -6583.3 | -11464.8 | 1.0745 | 4881.5 | 1 | 1.0792 | 1.1117 | 1.3278 | 1.1273 | 1.3187 | 1.1258 |  | 0.84686 | 0.709 | 0.78816 | 1 | 0.70248 | -0.079164 | -0.13786 | 0.0587
[10 empty] | Contingency up to the project type | 2494.8 | [21 empty] | 2023-06-12 | 2023-06-16 | S24 | 16 | 0.88889 | 4245 | 74670 | 61686.38 | 13.1747 | 3312 | 68855.5 | 0.89588 | 0.82612 | 0.82342 | -7169.12 | -12983.62 | 1.0844 | 5814.5 | 1 | 1.0862 | 1.1162 | 1.3512 | 1.1339 | 1.3556 | 1.1346 |  | 0.89791 | 0.74178 | 0.82799 | 1 | 0.73193 | -0.086209 | -0.15613 | 0.069919
[10 empty] | >10%--> highly risk project | [22 empty] | 2023-06-19 | 2023-06-23 | S25 | 17 | 0.94444 | 4245 | 78915 | 70105.56 | 14.9247 | 3202 | 72057.5 | 0.97291 | 0.88837 | 0.87793 | -1951.94 | -8809.44 | 1.0952 | 6857.5 | 1 | 1.0235 | 1.0278 | 1.157 | 1.046 | 1.1708 | 1.0483 |  | 0.94895 | 0.84302 | 0.86649 | 1 | 0.82915 | -0.023472 | -0.10593 | 0.082462
[10 empty] | btw 5% and 10% --> medium risk project | [22 empty] | 2023-06-26 | 2023-06-30 | S26 | 18 | 1 | 4245 | 83160 | 71541.24 | 15.263 | 2080 | 74137.5 | 0.96498 | 0.86028 | 0.84794 | -2596.26 | -11618.76 | 1.1217 | 9022.5 | 1 | 1.0312 | 1.0363 | 1.2046 | 1.0593 | 1.2221 | 1.0621 |  | 1 | 0.86028 | 0.8915 | 1 | 0.84794 | -0.03122 | -0.13972 | 0.1085
[10 empty] | <5% --> low risk project | [22 empty] | 2023-07-03 | 2023-07-07 | S27 | 19 | 1.0556 | 0 | 83160 | 75546.42 | 16.2065 | 3912 | 78049.5 | 0.96793 | 0.90845 | 0.85297 | -2503.08 | -7613.58 | 1.0655 | 5110.5 | 1 | 1.0301 | 1.0331 | 1.1373 | 1.046 | 1.2112 | 1.0583 | dw | 1 | 0.90845 | 0.93855 | 1 | 0.90036 | -0.0301 | -0.091553 | 0.061454
ACTUAL COSTS | [32 empty] | 2023-07-10 | 2023-07-14 | S28 | 20 | 1.1111 | 0 | 83160 | 80616.6 | 17.4008 | 3172 | 81221.5 | 0.99255 | 0.96942 | 0.87004 | -604.9 | -2543.4 | 1.0239 | 1938.5 | 1 | 1.0073 | 1.0075 | 1.0393 | 1.0122 | 1.158 | 1.033 | dw | 1 | 0.96942 | 0.97669 | 1 | 0.96671 | -0.0072739 | -0.030584 | 0.02331
[33 empty] | 2023-07-17 | 2023-07-21 | S29 | 21 | 1.1667 | 0 | 83160 | 83160 | 21 | 3483 | 84704.5 | 0.98177 | 1 | 1 | -1544.5 | 0 | 0.98177 | -1544.5 | FINE | FINE | FINE | FINE | FINE | FINE | FINE | dw | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE
[11 empty] | Price List €/h | 11
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | Software Tester 1 (stage) |  | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 60 | S14: 32; S15: 8; S17: 16; S20: 4
[10 empty] | Execution | 288 | S16: 40; S17: 24; S18: 32; S19: 40; S20: 32; S21: 38; S22: 40; S23: 42
[10 empty] | Retest | 80 | S21: 4; S23: 6; S24: 32; S25: 38
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 160 | S26: 40; S27: 40; S28: 40; S29: 40
[11 empty] | 588 | 0 | 0 | 0 | 0 | 0 | 32 | 8 | 40 | 40 | 32 | 40 | 36 | 42 | 40 | 48 | 32 | 38 | 40 | 40 | 40 | 40
[11 empty] | Price List €/h | S9: 22
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | Software Tester 2 (apprenticeship) |  | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 120 | S10: 24; S11: 40; S12: 40; S13: 16
[10 empty] | Integration | 0
[10 empty] | Execution | 240 | S14: 32; S15: 12; S16: 40; S17: 40; S18: 32; S19: 40; S20: 44
[10 empty] | Retest | 112 | S21: 16; S22: 32; S23: 40; S24: 24
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 71 | S21: 24; S24: 16; S25: 8; S26: 8; S27: 15
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 128 | S25: 32; S26: 8; S27: 16; S28: 32; S29: 40
[11 empty] | 671 | 0 | 24 | 40 | 40 | 16 | 32 | 12 | 40 | 40 | 32 | 40 | 44 | 40 | 32 | 40 | 40 | 40 | 16 | 31 | 32 | 40
[11 empty] | Price List €/h | S9: 22
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | Software Tester 3 (apprenticeship) |  | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 72 | S14: 40; S15: 32
[10 empty] | Execution | 316 | S16: 40; S17: 40; S18: 32; S19: 40; S20: 44; S21: 40; S22: 40; S23: 40
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 76 | S24: 40; S25: 32; S26: 4
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 464 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 40 | 40 | 32 | 40 | 44 | 40 | 40 | 40 | 40 | 32 | 4 | 0 | 0 | 0
[11 empty] | Price List €/h | S9: 32
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | Test Analyst 1 |  | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 120 | S9: 40; S10: 40; S11: 40
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 308 | S16: 32; S17: 40; S18: 32; S19: 40; S20: 40; S21: 40; S22: 44; S23: 40
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 428 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 32 | 40 | 32 | 40 | 40 | 40 | 44 | 40 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Price List €/h | S9: 30
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | Test Analyst 2 |  | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 96 | S9: 32; S10: 24; S11: 40
[10 empty] | Data preparation | 74 | S10: 18; S12: 40; S13: 16
[10 empty] | Integration | 0
[10 empty] | Execution | 208 | S15: 8; S16: 16; S17: 16; S18: 16; S19: 16; S20: 24; S21: 32; S22: 40; S23: 40
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 378 | 32 | 42 | 40 | 40 | 16 | 0 | 8 | 16 | 16 | 16 | 16 | 24 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Price List €/h | S9: 30
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | Test Analyst 3 |  | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 64 | S9: 40; S10: 16; S11: 8
[10 empty] | Data preparation | 32 | S11: 32
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 307 | S16: 32; S17: 40; S18: 32; S19: 25; S20: 18; S21: 32; S22: 32; S26: 32; S27: 24; S28: 8; S29: 32
[10 empty] | UAT support | 168 | S23: 40; S24: 40; S25: 40; S26: 8; S27: 16; S28: 24
[11 empty] | 571 | 40 | 16 | 40 | 0 | 0 | 0 | 0 | 32 | 40 | 32 | 25 | 18 | 32 | 32 | 40 | 40 | 40 | 40 | 40 | 32 | 32
[11 empty] | Price List €/h | S9: 48
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | Test Manager |  | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 147 | S9: 12; S10: 10; S12: 16; S15: 3; S18: 3; S19: 10; S20: 13; S21: 24; S23: 8; S27: 16; S28: 16; S29: 16
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 147 | 12 | 10 | 0 | 16 | 0 | 0 | 3 | 0 | 0 | 3 | 10 | 13 | 24 | 0 | 8 | 0 | 0 | 0 | 16 | 16 | 16
[11 empty] | Price List €/h | S9: 27
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | PMO |  | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 78.5 | S9: 5; S10: 5; S11: 2; S14: 8; S15: 2; S18: 10; S20: 16; S21: 9.5; S27: 6; S28: 5; S29: 10
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 78.5 | 5 | 5 | 2 | 0 | 0 | 8 | 2 | 0 | 0 | 10 | 0 | 16 | 9.5 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 10
[11 empty] | Price List €/h | S9: 55
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | Service Manager |  | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 0
[10 empty] | Data preparation | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 35 | S9: 2; S12: 4; S17: 3; S21: 8; S27: 12; S28: 3; S29: 3
[10 empty] | ALM maintenance | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT support | 0
[11 empty] | 35 | 2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 12 | 3 | 3
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | Actual Total Costs | 84704.5 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 8640 | 3440 | 2480 | 2720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Data preparation | 5820 | 0 | 1068 | 1840 | 2080 | 832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Integration | 2244 | 0 | 0 | 0 | 0 | 0 | 1232 | 792 | 0 | 176 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Execution | 31496 | 0 | 0 | 0 | 0 | 0 | 704 | 504 | 3704 | 3784 | 3264 | 3960 | 4288 | 3538 | 3928 | 3822 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Retest | 3344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396 | 704 | 946 | 880 | 418 | 0 | 0 | 0 | 0
[10 empty] | Management | 11100.5 | 821 | 615 | 54 | 988 | 0 | 216 | 198 | 0 | 165 | 414 | 480 | 1056 | 1848.5 | 0 | 384 | 0 | 0 | 0 | 1590 | 1068 | 1203
[10 empty] | ALM maintenance | 3234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528 | 0 | 0 | 1232 | 880 | 264 | 330 | 0 | 0
[10 empty] | Reporting activities | 9210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 1200 | 960 | 750 | 540 | 960 | 960 | 0 | 0 | 0 | 960 | 720 | 240 | 960
[10 empty] | UAT support | 9616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1904 | 856 | 1272 | 1864 | 1320
[12 empty] | 4261 | 4163 | 4614 | 3068 | 832 | 2152 | 1494 | 4664 | 5325 | 4638 | 5190 | 5928 | 7270.5 | 5592 | 6352 | 3312 | 3202 | 2080 | 3912 | 3172 | 3483
EARNED VALUE
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | %Progress | 100% | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 100% | 15% | 45% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Data preparation | 100% | 0% | 20% | 44% | 65% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Integration | 100% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Execution | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 35% | 50% | 65% | 75% | 80% | 89% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Retest | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 15% | 55% | 68% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Management | 100% | 4.8% | 9.6% | 14.4% | 19.2% | 24% | 28.8% | 33.6% | 38.4% | 43.2% | 48% | 52.8% | 57.6% | 62.4% | 67.2% | 72% | 76.8% | 81.6% | 86.4% | 91.2% | 96% | 100%
[10 empty] | ALM maintenance | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 40% | 55% | 80% | 100% | 100% | 100% | 100%
[10 empty] | Reporting activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 25% | 35% | 46% | 50% | 50% | 50% | 50% | 60% | 65% | 73% | 88% | 93% | 100%
[10 empty] | UAT support | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 15% | 50% | 50% | 65% | 90% | 100%
[12 empty] | 1.921% | 7.173% | 15.16% | 17.69% | 21.57% | 24.49% | 27.41% | 37.74% | 40.94% | 46.76% | 52.66% | 56.5% | 59.19% | 62.89% | 70.9% | 74.18% | 84.3% | 86.03% | 90.84% | 96.94% | 100%
[11 empty] | FROM | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17
[11 empty] | TO | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
[10 empty] | EV | 83160 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29
[10 empty] | Testbook Design | 7800 | 1170 | 3510 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800
[10 empty] | Data preparation | 8000 | 0 | 1600 | 3520 | 5200 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
[10 empty] | Integration | 4000 | 0 | 0 | 0 | 0 | 0 | 2000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
[10 empty] | Execution | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8750 | 12500 | 16250 | 18750 | 20000 | 22250 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
[10 empty] | Retest | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 480 | 1760 | 2176 | 3200 | 3200 | 3200 | 3200 | 3200
[10 empty] | Management | 8910 | 427.68 | 855.36 | 1283.04 | 1710.72 | 2138.4 | 2566.08 | 2993.76 | 3421.44 | 3849.12 | 4276.8 | 4704.48 | 5132.16 | 5559.84 | 5987.52 | 6415.2 | 6842.88 | 7270.56 | 7698.24 | 8125.92 | 8553.6 | 8910
[10 empty] | ALM maintenance | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 480 | 960 | 1320 | 1920 | 2400 | 2400 | 2400 | 2400
[10 empty] | Reporting activities | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 1650 | 2310 | 3036 | 3300 | 3300 | 3300 | 3300 | 3960 | 4290 | 4818 | 5808 | 6138 | 6600
[10 empty] | UAT support | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1725 | 2587.5 | 8625 | 8625 | 11212.5 | 15525 | 17250
[12 empty] | 1597.68 | 5965.36 | 12603.04 | 14710.72 | 17938.4 | 20366.08 | 22793.76 | 31381.44 | 34049.12 | 38886.8 | 43790.48 | 46982.16 | 49219.84 | 52297.52 | 58960.2 | 61686.38 | 70105.56 | 71541.24 | 75546.42 | 80616.6 | 83160
Formulas:
Bank 1 = MIN([Bank 1, row below]:C30)

## Project_10
PROJECT OVERVIEW
| Project Name | Project 10 |  | Estimation | yes
| Responsible | Test Manager Green Team |  | Sceduling | yes |  |  |  |  | Assumptions | [47 empty] | AC(AD) | AC(29) | 104130 |  | Acn(ADn=1,07) | 1.1988
| Client | Bank 1 | [5 empty] | Business Unit | Financial Services | Client charge | Test Manager | 330
| Area | Crediti | [5 empty] | Prectice | Testing | €/gg | Tester | 200
| Resource number | 7 | [5 empty] | Sub-practice level 1 | Area Operations | [48 empty] | ADn | 1.0741
| Starting date | 2022-12-12 | [5 empty] | Sub-practice level 2 | Credit Management
| Release (Go live) | 2023-06-16 | [5 empty] | Sub-practice level 3 | Pre-dispute Credit Recovery
| Main Activities | Desing, Execution, Management and UAT | [5 empty] | Activity Description | The aim is to manage debtors and their compliances as good as possible thanks to the information coming from the monitoring of their positions. The process involves many steps, from the soft collection till the problematic report. | [31 empty] | Project Planned Elapsed time
| %completion | 100% | [38 empty] | 27 | weeks
| Next Milestone | N/A
| TM Estimate Name | Estimate 10: Project_10_.xls
| Estimate Budget | 93814.2
BASELINE | [42 empty] | Week | Time Unit | TPn | BASELINE | BCWS | EV | ES | Actual Costs | ACWP | CPI | SPI | SPIt | CV | SV | RFI | RV | CEACn=BACn | CEACn=BACn-CVn | CEACn=BCAn/CPI | CEACn=BACn/(CPI*SPI) | CEACn=BACn/ ( .8 CPI + .2 SPI) | CEACn=BACn/(CPI*SPIt) | CEACn=BACn/ ( .8 CPI + .2 SPIt) |  | WS | WP | ACn | BACn | Esn | CVn | SVn | RVn
[44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[41 empty] | 2022-12-12 | 2022-12-16 | S51 | 1 | 0.037037 | 2995 | 2995 | 2354.41 | 0.78611 | 4264 | 4264 | 0.55216 | 0.78611 | 0.78611 | -1909.59 | -640.59 | 0.70239 | -1269 | 1 | 1.022 | 1.8111 | 2.3038 | 1.6696 | 2.3038 | 1.6696 |  | 0.034479 | 0.027104 | 0.049088 | 1 | 0.029115 | -0.021983 | -0.0073745 | -0.014609
[41 empty] | 2022-12-19 | 2022-12-23 | S52 | 2 | 0.074074 | 2995 | 5990 | 3663.82 | 1.2233 | 2916 | 7180 | 0.51028 | 0.61166 | 0.61166 | -3516.18 | -2326.18 | 0.83426 | -1190 | 1 | 1.0405 | 1.9597 | 3.2039 | 1.8848 | 3.2039 | 1.8848 |  | 0.068958 | 0.042178 | 0.082657 | 1 | 0.045308 | -0.040479 | -0.026779 | -0.013699
|  | Project Activities | [8 empty] | FROM | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 |  |  | 2022-12-26 | 2022-12-30 | S53 | 3 | 0.11111 | 2995 | 8985 | 4688.23 | 1.5654 | 3792 | 10972 | 0.42729 | 0.52178 | 0.52178 | -6283.77 | -4296.77 | 0.8189 | -1987 | 1 | 1.0723 | 2.3403 | 4.4852 | 2.2412 | 4.4852 | 2.2412 |  | 0.10344 | 0.053971 | 0.12631 | 1 | 0.057976 | -0.072339 | -0.049465 | -0.022875
|  | Start Date | End Date | Starting week number | Ending week number | FTEs | FTE figure | Weight | Budget x activity |  | TO | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 |  |  | 2023-01-02 | 2023-01-06 | S1 | 4 | 0.14815 | 2495 | 11480 | 7137.64 | 2.3832 | 4480 | 15452 | 0.46192 | 0.62175 | 0.5958 | -8314.36 | -4342.36 | 0.74295 | -3972 | 1 | 1.0957 | 2.1649 | 3.4819 | 2.0248 | 3.6336 | 2.0463 |  | 0.13216 | 0.082169 | 0.17789 | 1 | 0.088266 | -0.095716 | -0.04999 | -0.045726
| Project 10 | 2022-12-12 | 2023-06-16 | 51 | 24 |  |  | 100% | overall budget - allocation plan | Scheduling | € | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | DELAY | DELAY | 2023-01-09 | 2023-01-13 | S2 | 5 | 0.18519 | 495 | 11975 | 11772.05 | 4.59 | 1672 | 17124 | 0.68746 | 0.98305 | 0.918 | -5351.95 | -202.95 | 0.69931 | -5149 | 1 | 1.0616 | 1.4546 | 1.4797 | 1.3394 | 1.5846 | 1.3632 |  | 0.13786 | 0.13552 | 0.19713 | 1 | 0.17 | -0.061612 | -0.0023364 | -0.059276
| Testbook Design | 2022-12-12 | 2023-01-05 | 51 | 1 | 2,5/day | Test Analyst | 10.94% | 9500 | Testbook Design | 9500 | 2500 | 2500 | 2500 | 2000 | [25 empty] | 2023-01-16 | 2023-01-20 | S3 | 6 | 0.22222 | 1995 | 13970 | 13426.46 | 5.7275 | 1185 | 18309 | 0.73333 | 0.96109 | 0.95459 | -4882.54 | -543.54 | 0.76301 | -4339 | 1 | 1.0562 | 1.3637 | 1.4189 | 1.2839 | 1.4285 | 1.286 |  | 0.16082 | 0.15457 | 0.21078 | 1 | 0.21213 | -0.056208 | -0.0062573 | -0.049951
| Integration | 2023-01-16 | 2023-02-10 | 3 | 6 | 1,5/day | Software Tester | 6.907% | 6000 | Integration | 6000 | [5 empty] | 1500 | 1500 | 1500 | 1500 | [20 empty] | 2023-01-23 | 2023-01-27 | S4 | 7 | 0.25926 | 1995 | 15965 | 14480.87 | 6.2561 | 1568 | 19877 | 0.72852 | 0.90704 | 0.89373 | -5396.13 | -1484.13 | 0.80319 | -3912 | 1 | 1.0621 | 1.3726 | 1.5133 | 1.3085 | 1.5359 | 1.3131 |  | 0.18379 | 0.16671 | 0.22883 | 1 | 0.23171 | -0.062121 | -0.017085 | -0.045035
| Execution | 2023-02-22 | 2023-04-21 | 8 | 16 | 4/day | Test Analyst; Software Tester | 39.6% | 34400 | Execution | 34400 | [10 empty] | 2400 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | [10 empty] | 2023-01-30 | 2023-02-03 | S5 | 8 | 0.2963 | 1995 | 17960 | 15535.28 | 3.7846 | 2331 | 22208 | 0.69954 | 0.86499 | 0.47308 | -6672.72 | -2424.72 | 0.80872 | -4248 | 1 | 1.0768 | 1.4295 | 1.6526 | 1.365 | 3.0218 | 1.5285 |  | 0.20676 | 0.17884 | 0.25566 | 1 | 0.14017 | -0.076817 | -0.027914 | -0.048903
| Retest | 2023-04-26 | 2023-05-12 | 17 | 19 | 1/day | Software Tester | 2.993% | 2600 | Retest | 2600 | [19 empty] | 600 | 1000 | 1000 | [7 empty] | 2023-02-06 | 2023-02-10 | S6 | 9 | 0.33333 | 1995 | 19955 | 17189.69 | 7.6139 | 1622 | 23830 | 0.72135 | 0.86142 | 0.84599 | -6640.31 | -2765.31 | 0.83739 | -3875 | 1 | 1.0764 | 1.3863 | 1.6093 | 1.3345 | 1.6387 | 1.34 |  | 0.22972 | 0.19789 | 0.27433 | 1 | 0.282 | -0.076444 | -0.031835 | -0.044609
| Management | 2022-12-12 | 2023-06-16 | 51 | 24 | 1,5/week | Test Manager | 15.39% | 13365 | Management | 13365 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 |  |  | 2023-02-13 | 2023-02-17 | S7 | 10 | 0.37037 | 495 | 20450 | 20044.1 | 9.18 | 696 | 24526 | 0.81726 | 0.98015 | 0.918 | -4481.9 | -405.9 | 0.83381 | -4076 | 1 | 1.0516 | 1.2236 | 1.2484 | 1.1767 | 1.3329 | 1.1942 |  | 0.23542 | 0.23075 | 0.28235 | 1 | 0.34 | -0.051596 | -0.0046728 | -0.046923
| Reporting activities | 2023-02-22 | 2023-05-12 | 8 | 19 | 1/day | Test Analyst | 12.66% | 11000 | Reporting activities | 11000 | [10 empty] | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | [8 empty] | 2023-02-20 | 2023-02-24 | S8 | 11 | 0.40741 | 3895 | 24345 | 23938.51 | 10.8956 | 3622 | 28148 | 0.85045 | 0.9833 | 0.99051 | -4209.49 | -406.49 | 0.86489 | -3803 | 1 | 1.0485 | 1.1758 | 1.1958 | 1.1402 | 1.1871 | 1.1384 |  | 0.28026 | 0.27558 | 0.32404 | 1 | 0.40354 | -0.04846 | -0.0046796 | -0.043781
| UAT Support | 2023-05-15 | 2023-06-16 | 20 | 24 | 2/day | Software Tester; Test Analyst | 11.51% | 10000 | UAT Support | 10000 | [22 empty] | 2000 | 2000 | 2000 | 2000 | 2000 |  |  | 2023-02-27 | 2023-03-03 | S9 | 12 | 0.44444 | 5495 | 29840 | 28932.92 | 11.8349 | 5246 | 33394 | 0.86641 | 0.9696 | 0.98624 | -4461.08 | -907.08 | 0.89357 | -3554 | 1 | 1.0514 | 1.1542 | 1.1904 | 1.1273 | 1.1703 | 1.1231 |  | 0.34352 | 0.33308 | 0.38444 | 1 | 0.43833 | -0.051356 | -0.010442 | -0.040914
[11 empty] | 86865 | 2995 | 2995 | 2995 | 2495 | 495 | 1995 | 1995 | 1995 | 1995 | 495 | 3895 | 5495 | 5495 | 5495 | 5495 | 5495 | 5495 | 5495 | 5495 | 2095 | 2495 | 1495 | 2495 | 2495 | 2495 | 2495 | 2495 |  |  | 2023-03-06 | 2023-03-10 | S10 | 13 | 0.48148 | 5495 | 35335 | 34065.33 | 12.7689 | 4095 | 37489 | 0.90868 | 0.96407 | 0.98223 | -3423.67 | -1269.67 | 0.94254 | -2154 | 1 | 1.0394 | 1.1005 | 1.1415 | 1.0872 | 1.1204 | 1.083 |  | 0.40678 | 0.39216 | 0.43158 | 1 | 0.47292 | -0.039414 | -0.014617 | -0.024797
[10 empty] | Contingency up to the project type | 6949.2 | [29 empty] | 2023-03-13 | 2023-03-17 | S11 | 14 | 0.51852 | 5495 | 40830 | 39885.74 | 13.8282 | 3844 | 41333 | 0.96499 | 0.97687 | 0.98773 | -1447.26 | -944.26 | 0.98783 | -503 | 1 | 1.0167 | 1.0363 | 1.0608 | 1.0337 | 1.0492 | 1.0314 |  | 0.47004 | 0.45917 | 0.47583 | 1 | 0.51215 | -0.016661 | -0.01087 | -0.0057906
[10 empty] | >10%--> highly risk project | [30 empty] | 2023-03-20 | 2023-03-24 | S12 | 15 | 0.55556 | 5495 | 46325 | 43986.15 | 14.5744 | 5108 | 46441 | 0.94714 | 0.94951 | 0.97162 | -2454.85 | -2338.85 | 0.9975 | -116 | 1 | 1.0283 | 1.0558 | 1.1119 | 1.0553 | 1.0866 | 1.0504 |  | 0.5333 | 0.50637 | 0.53463 | 1 | 0.53979 | -0.028261 | -0.026925 | -0.0013354
[10 empty] | btw 5% and 10% --> medium risk project | [30 empty] | 2023-03-27 | 2023-03-31 | S13 | 16 | 0.59259 | 5495 | 51820 | 48430.56 | 15.3832 | 5544 | 51985 | 0.93163 | 0.93459 | 0.96145 | -3554.44 | -3389.44 | 0.99683 | -165 | 1 | 1.0409 | 1.0734 | 1.1485 | 1.0727 | 1.1164 | 1.0666 |  | 0.59656 | 0.55754 | 0.59846 | 1 | 0.56975 | -0.040919 | -0.03902 | -0.0018995
[10 empty] | <5% --> low risk project | [30 empty] | 2023-04-03 | 2023-04-07 | S14 | 17 | 0.62963 | 5495 | 57315 | 51622.97 | 15.9641 | 5049 | 57034 | 0.90513 | 0.90069 | 0.93907 | -5411.03 | -5692.03 | 1.0049 | 281 | 1 | 1.0623 | 1.1048 | 1.2266 | 1.1059 | 1.1765 | 1.0966 |  | 0.65982 | 0.59429 | 0.65658 | 1 | 0.59126 | -0.062292 | -0.065527 | 0.0032349
ACTUAL COSTS | [40 empty] | 2023-04-10 | 2023-04-14 | S15 | 18 | 0.66667 | 5495 | 62810 | 56149.38 | 16.7879 | 4352 | 61386 | 0.91469 | 0.89396 | 0.93266 | -5236.62 | -6660.62 | 1.0232 | 1424 | 1 | 1.0603 | 1.0933 | 1.2229 | 1.0982 | 1.1722 | 1.089 |  | 0.72308 | 0.6464 | 0.70668 | 1 | 0.62177 | -0.060285 | -0.076678 | 0.016393
[41 empty] | 2023-04-17 | 2023-04-21 | S16 | 19 | 0.7037 | 5495 | 68305 | 58873.79 | 17.2837 | 5412 | 66798 | 0.88137 | 0.86193 | 0.90967 | -7924.21 | -9431.21 | 1.0226 | 1507 | 1 | 1.0912 | 1.1346 | 1.3164 | 1.1396 | 1.2473 | 1.1274 |  | 0.78634 | 0.67776 | 0.76899 | 1 | 0.64014 | -0.091224 | -0.10857 | 0.017349
[41 empty] | 2023-04-24 | 2023-04-28 | S17 | 20 | 0.74074 | 2095 | 70400 | 62066.2 | 17.8646 | 3617 | 70415 | 0.88143 | 0.88162 | 0.89323 | -8348.8 | -8333.8 | 0.99979 | -15 | 1 | 1.0961 | 1.1345 | 1.2868 | 1.1345 | 1.2701 | 1.1315 |  | 0.81045 | 0.71451 | 0.81063 | 1 | 0.66165 | -0.096112 | -0.09594 | -0.00017268
[41 empty] | 2023-05-01 | 2023-05-05 | S18 | 21 | 0.77778 | 2495 | 72895 | 65010.61 | 18.4005 | 4154 | 74569 | 0.87182 | 0.89184 | 0.87621 | -9558.39 | -7884.39 | 0.97755 | -1674 | 1 | 1.11 | 1.147 | 1.2861 | 1.1418 | 1.3091 | 1.1459 |  | 0.83918 | 0.74841 | 0.85845 | 1 | 0.6815 | -0.11004 | -0.090766 | -0.019271
[11 empty] | Price List €/h | 11 | [28 empty] | 2023-05-08 | 2023-05-12 | S19 | 22 | 0.81481 | 1495 | 74390 | 68007.02 | 18.9458 | 3224 | 77793 | 0.8742 | 0.9142 | 0.86117 | -9785.98 | -6382.98 | 0.95626 | -3403 | 1 | 1.1127 | 1.1439 | 1.2513 | 1.1335 | 1.3283 | 1.1473 |  | 0.85639 | 0.7829 | 0.89556 | 1 | 0.7017 | -0.11266 | -0.073482 | -0.039176
[11 empty] | FROM | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-05-15 | 2023-05-19 | S20 | 23 | 0.85185 | 2495 | 76885 | 72271.43 | 20.7501 | 3704 | 81497 | 0.8868 | 0.93999 | 0.90218 | -9225.57 | -4613.57 | 0.94341 | -4612 | 1 | 1.1062 | 1.1277 | 1.1996 | 1.1143 | 1.2499 | 1.1238 |  | 0.88511 | 0.832 | 0.9382 | 1 | 0.76852 | -0.10621 | -0.053112 | -0.053094
[11 empty] | TO | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-05-22 | 2023-05-26 | S21 | 24 | 0.88889 | 2495 | 79380 | 75233.84 | 22.3382 | 3604 | 85101 | 0.88405 | 0.94777 | 0.93076 | -9867.16 | -4146.16 | 0.93277 | -5721 | 1 | 1.1136 | 1.1312 | 1.1935 | 1.1151 | 1.2153 | 1.1193 |  | 0.91383 | 0.8661 | 0.97969 | 1 | 0.82734 | -0.11359 | -0.047731 | -0.065861
[10 empty] | Software Tester 1 (stage) |  | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | 2023-05-29 | 2023-06-02 | S22 | 25 | 0.92593 | 2495 | 81875 | 78460.25 | 23.6314 | 3080 | 88181 | 0.88976 | 0.95829 | 0.94525 | -9720.75 | -3414.75 | 0.92849 | -6306 | 1 | 1.1119 | 1.1239 | 1.1728 | 1.1068 | 1.189 | 1.11 |  | 0.94255 | 0.90324 | 1.0151 | 1 | 0.87524 | -0.11191 | -0.039311 | -0.072595
[10 empty] | Testbook Design | 0 | [29 empty] | 2023-06-05 | 2023-06-09 | S23 | 26 | 0.96296 | 2495 | 84370 | 80044.66 | 24.2664 | 3092 | 91273 | 0.87698 | 0.94873 | 0.93332 | -11228.34 | -4325.34 | 0.92437 | -6903 | 1 | 1.1293 | 1.1403 | 1.2019 | 1.1219 | 1.2217 | 1.1258 |  | 0.97128 | 0.92148 | 1.0507 | 1 | 0.89876 | -0.12926 | -0.049794 | -0.079468
[10 empty] | Integration | 154 | S3: 40; S4: 32; S5: 40; S6: 42 | 2023-06-12 | 2023-06-16 | S24 | 27 | 1 | 2495 | 86865 | 83219.07 | 25.5387 | 4112 | 95385 | 0.87245 | 0.95803 | 0.94588 | -12165.93 | -3645.93 | 0.91068 | -8520 | 1 | 1.1401 | 1.1462 | 1.1964 | 1.1241 | 1.2118 | 1.1272 |  | 1 | 0.95803 | 1.0981 | 1 | 0.94588 | -0.14006 | -0.041972 | -0.098083
[10 empty] | Execution | 358 | S8: 24; S9: 40; S10: 40; S11: 32; S12: 16; S13: 40; S14: 25; S15: 32; S16: 40; S17: 29; S18: 32; S20: 8 | 2023-06-19 | 2023-06-23 | S25 | 28 | 1.037 | 0 | 86865 | 85203.48 | 26.3341 | 4562 | 99947 | 0.85249 | 0.98087 | 0.9405 | -14743.52 | -1661.52 | 0.86911 | -13082 | 1 | 1.1697 | 1.173 | 1.1959 | 1.1387 | 1.2472 | 1.1493 | Delay Week | 1 | 0.98087 | 1.1506 | 1 | 0.97534 | -0.16973 | -0.019128 | -0.1506
[10 empty] | Retest | 120 | S19: 40; S20: 32; S21: 32; S22: 16 | 2023-06-26 | 2023-06-30 | S26 | 29 | 1.0741 | 0 | 86865 | 86865 | 29 | 4183 | 104130 | 0.8342 | 1 | 1 | -17265 | 1.4552e-11 | 0.8342 | -17265 | FINE | FINE | FINE | FINE | FINE | FINE | FINE | Delay Week | FINE | FINE | FINE | FINE | FINE | FINE | FINE | FINE
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0 | [39 empty] | 17265
[10 empty] | UAT Support | 184 | S20: 8; S21: 8; S22: 16; S23: 32; S24: 40; S25: 40; S26: 40
[11 empty] | 816 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 40 | 42 | 0 | 24 | 40 | 40 | 32 | 16 | 40 | 25 | 32 | 40 | 29 | 32 | 40 | 48 | 40 | 32 | 32 | 40 | 40 | 40
[11 empty] | Price List €/h | S51: 29
[11 empty] | FROM | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | Software Tester 2 |  | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 0
[10 empty] | Integration | 160 | S3: 16; S4: 40; S5: 40; S6: 40; S7: 24
[10 empty] | Execution | 377 | S8: 32; S9: 32; S10: 15; S11: 32; S12: 26; S13: 32; S14: 30; S15: 32; S16: 42; S17: 40; S18: 32; S19: 16; S20: 16
[10 empty] | Retest | 88 | S20: 24; S21: 24; S22: 40
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT Support | 88 | S23: 24; S24: 24; S25: 24; S26: 16
[11 empty] | 713 | 0 | 0 | 0 | 0 | 0 | 16 | 40 | 40 | 40 | 24 | 32 | 32 | 15 | 32 | 26 | 32 | 30 | 32 | 42 | 40 | 32 | 16 | 40 | 24 | 40 | 24 | 24 | 24 | 16
[11 empty] | Price List €/h | S51: 30
[11 empty] | FROM | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | Test Analyst 1 |  | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 144 | S51: 40; S52: 40; S53: 32; S1: 32
[10 empty] | Integration | 0
[10 empty] | Execution | 374 | S8: 40; S9: 32; S10: 40; S11: 40; S12: 32; S13: 40; S14: 22; S15: 32; S16: 40; S17: 24; S18: 32
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT Support | 240 | S20: 40; S21: 40; S22: 16; S23: 32; S24: 32; S25: 40; S26: 40
[11 empty] | 758 | 40 | 40 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 40 | 40 | 32 | 40 | 22 | 32 | 40 | 24 | 32 | 0 | 40 | 40 | 16 | 32 | 32 | 40 | 40
[11 empty] | Price List €/h | S51: 32
[11 empty] | FROM | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | Test Analyst 2 |  | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 128 | S51: 32; S52: 24; S53: 32; S1: 32; S2: 8
[10 empty] | Integration | 0
[10 empty] | Execution | 370 | S8: 30; S9: 40; S10: 32; S11: 32; S12: 44; S13: 40; S14: 40; S15: 32; S16: 32; S17: 16; S18: 16; S19: 16
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | Reporting activities | 0
[10 empty] | UAT Support | 0
[11 empty] | 498 | 32 | 24 | 32 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 30 | 40 | 32 | 32 | 44 | 40 | 40 | 32 | 32 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Price List €/h | S51: 34
[11 empty] | FROM | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | Test Analyst 3 |  | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 168 | S51: 40; S52: 16; S53: 32; S1: 40; S2: 40
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 0
[10 empty] | Reporting activities | 531 | [11 empty] | 32 | 24 | 10 | 40 | 40 | 32 | 32 | 25 | 24 | 32 | 40 | 24 | 32 | 32 | 16 | 16 | 40 | 40
[10 empty] | UAT Support | 0
[11 empty] | 699 | 40 | 16 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 24 | 10 | 40 | 40 | 32 | 32 | 25 | 24 | 32 | 40 | 24 | 32 | 32 | 16 | 16 | 40 | 40
[11 empty] | Price List €/h | S51: 45
[11 empty] | FROM | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | Test Manager |  | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 199 | 12 | 4 | 16 | 24 |  | 5 |  | 15 |  |  | 6 | 6 | 4 |  | 10 |  | 12 |  | 12 | 2 | 2 |  |  | 4 |  | 12 | 24 | 18 | 11
[10 empty] | Reporting activities | 0
[10 empty] | UAT Support | 0
[11 empty] | 199 | 12 | 4 | 16 | 24 | 0 | 5 | 0 | 15 | 0 | 0 | 6 | 6 | 4 | 0 | 10 | 0 | 12 | 0 | 12 | 2 | 2 | 0 | 0 | 4 | 0 | 12 | 24 | 18 | 11
[11 empty] | Price List €/h | S51: 28
[11 empty] | FROM | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | PMO |  | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 0
[10 empty] | Integration | 0
[10 empty] | Execution | 0
[10 empty] | Retest | 0
[10 empty] | Management | 110 | S51: 5; S52: 8; S1: 2; S2: 2; S3: 2; S4: 2; S5: 2; S9: 10; S13: 12; S14: 12; S16: 5; S18: 8; S19: 16; S24: 14; S25: 2; S26: 8
[10 empty] | Reporting activities | 0
[10 empty] | UAT Support | 0
[11 empty] | 110 | 5 | 8 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 12 | 12 | 0 | 5 | 0 | 8 | 16 | 0 | 0 | 0 | 0 | 14 | 2 | 8
[11 empty] | FROM | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | Actual Total Costs | 104130 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 14128 | 3584 | 2512 | 3072 | 3344 | 1616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Integration | 6334 | 0 | 0 | 0 | 0 | 0 | 904 | 1512 | 1600 | 1622 | 696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Execution | 37931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3352 | 3608 | 3099 | 3504 | 3298 | 3848 | 3085 | 3264 | 3882 | 2711 | 2752 | 976 | 552 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Retest | 3872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1048 | 1048 | 1336 | 0 | 0 | 0 | 0
[10 empty] | Management | 12035 | 680 | 404 | 720 | 1136 | 56 | 281 | 56 | 731 | 0 | 0 | 270 | 550 | 180 | 0 | 450 | 336 | 876 | 0 | 680 | 90 | 314 | 448 | 0 | 180 | 0 | 540 | 1472 | 866 | 719
[10 empty] | Reporting activities | 18054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088 | 816 | 340 | 1360 | 1360 | 1088 | 1088 | 850 | 816 | 1088 | 1360 | 816 | 1088 | 1088 | 544 | 544 | 1360 | 1360
[10 empty] | UAT Support | 11776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288 | 1288 | 656 | 2008 | 2096 | 2336 | 2104
[12 empty] | 4264 | 2916 | 3792 | 4480 | 1672 | 1185 | 1568 | 2331 | 1622 | 696 | 3622 | 5246 | 4095 | 3844 | 5108 | 5544 | 5049 | 4352 | 5412 | 3617 | 4154 | 3224 | 3704 | 3604 | 3080 | 3092 | 4112 | 4562 | 4183
EARNED VALUE
[11 empty] | FROM | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | %Progress | 67.78% | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 100% | 20% | 29% | 35% | 56% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Integration | 100% | 0% | 0% | 0% | 0% | 0% | 20% | 30% | 40% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Execution | 85% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 32% | 46% | 55% | 65% | 72% | 80% | 85% | 92% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Retest | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 45% | 78% | 100% | 100% | 100% | 100% | 100%
[10 empty] | Management | 64.6% | 3.4% | 6.8% | 10.2% | 13.6% | 17% | 20.4% | 23.8% | 27.2% | 30.6% | 34% | 37.4% | 40.8% | 44.2% | 47.6% | 51% | 54.4% | 57.8% | 61.2% | 64.6% | 68% | 71.4% | 74.8% | 78.2% | 81.6% | 85% | 88.4% | 91.8% | 95.2% | 100%
[10 empty] | Reporting activities | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 15% | 20% | 25% | 30% | 33% | 45% | 50% | 53% | 60% | 69% | 75% | 80% | 90% | 93% | 95% | 98% | 100%
[10 empty] | UAT Support | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 36% | 47% | 55% | 80% | 92% | 100%
[12 empty] | 2.71% | 4.218% | 5.397% | 8.217% | 13.55% | 15.46% | 16.67% | 17.88% | 19.79% | 23.08% | 27.56% | 33.31% | 39.22% | 45.92% | 50.64% | 55.75% | 59.43% | 64.64% | 67.78% | 71.45% | 74.84% | 78.29% | 83.2% | 86.61% | 90.32% | 92.15% | 95.8% | 98.09% | 100%
[11 empty] | FROM | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26
[11 empty] | TO | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30
[10 empty] | EV | 86865 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26
[10 empty] | Testbook Design | 9500 | 1900 | 2755 | 3325 | 5320 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500
[10 empty] | Integration | 6000 | 0 | 0 | 0 | 0 | 0 | 1200 | 1800 | 2400 | 3600 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
[10 empty] | Execution | 34400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3440 | 6880 | 11008 | 15824 | 18920 | 22360 | 24768 | 27520 | 29240 | 31648 | 33368 | 34400 | 34400 | 34400 | 34400 | 34400 | 34400 | 34400 | 34400
[10 empty] | Retest | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | 1170 | 2028 | 2600 | 2600 | 2600 | 2600 | 2600
[10 empty] | Management | 13365 | 454.41 | 908.82 | 1363.23 | 1817.64 | 2272.05 | 2726.46 | 3180.87 | 3635.28 | 4089.69 | 4544.1 | 4998.51 | 5452.92 | 5907.33 | 6361.74 | 6816.15 | 7270.56 | 7724.97 | 8179.38 | 8633.79 | 9088.2 | 9542.61 | 9997.02 | 10451.43 | 10905.84 | 11360.25 | 11814.66 | 12269.07 | 12723.48 | 13365
[10 empty] | Reporting activities | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 1650 | 2200 | 2750 | 3300 | 3630 | 4950 | 5500 | 5830 | 6600 | 7590 | 8250 | 8800 | 9900 | 10230 | 10450 | 10780 | 11000
[10 empty] | UAT Support | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 3600 | 4700 | 5500 | 8000 | 9200 | 10000
[12 empty] | 2354.41 | 3663.82 | 4688.23 | 7137.64 | 11772.05 | 13426.46 | 14480.87 | 15535.28 | 17189.69 | 20044.1 | 23938.51 | 28932.92 | 34065.33 | 39885.74 | 43986.15 | 48430.56 | 51622.97 | 56149.38 | 58873.79 | 62066.2 | 65010.61 | 68007.02 | 72271.43 | 75233.84 | 78460.25 | 80044.66 | 83219.07 | 85203.48 | 86865
Formulas:
Project Planned Elapsed time = [Project Planned Elapsed time, row above]+7
Week = CONCATENATE("S",WEEKNUM([Project Planned Elapsed time]))
Bank 1 = MIN([Bank 1, row below]:C28)

## Gannt Chart
 | time axis 2022-06-06 to 2023-07-17
 | time axis 2022-06-10 to 2023-07-21
 | time axis 2022-06-10 to 2023-07-21
[11 empty] | Project 1 | [28 empty] | ok
Project 2
|  |  | Project 3 | [34 empty] | ok
Project 4
Project 5 | bar: 2022-06-10 to 2022-12-23
[39 empty] | Project 6 |  | ok
Project 7
Project 8
[37 empty] | Project 9 |  | ok
Project 10
[6 empty] | Team 1 | [8 empty] | Team 1 |  |  |  |  | Team 2
[6 empty] | Team 2+ | [8 empty] | Project 1 |  |  |  |  | Project 3
[15 empty] | Project 2 |  |  |  |  | Project 4
[15 empty] | Project 5 |  |  |  |  | Project 7
[15 empty] | Project 6 |  |  |  |  | Project 8
[15 empty] | Project 10 |  |  |  |  | Project 9

## References
Sei un consulente? Come fissare la propria tariffa oraria? :: Spunti(ni) economici (spuntinieconomici.com)
costoorario.XLS (live.com)
Si è cercato stipendio consulenza - Benvenuto a lavoro
Le 12 professionalità IT più pagate nel 2023 (hightekers.com)
3 Modi per Stabilire Tariffe di Consulenza - wikiHow
Costo orario e Consulenza - Dario Banfi
Costo aziendale per dipendente: calcolo e voci di costo (danea.it)
Ma quanto costa la consulenza? - Chiarini Blog

## CJ unico R5 Integration Pal (2) (hidden)
| Nome Progetto | CJ unico R5 Integration Paland.
| Responsabile | Malacrida Alessandro | [81 empty] | Note | BM | Referente | Workorder | Status | Text WO | Data Inizio | Data Fine | Fatturazione | OFFERTA | Residuo da Maturato | M% | Residuo da RevTab | RT% | Text Ressource | Time Code |  | PriceList | Hours 202003 | Hours 202004 | Hours 202005 | Hours 202006 | Hours 202007 | Hours 202008 | Hours 202009 | Hours 202010 | Hours 202011 | Hours 202012 | Hours 202101 | Hours 202102 | Hours 202103 | Hours 202104 | Hours 202105 | Hours 202106 | Hours 202107 | Hours 202108 | Hours 202109 | Maturato al 29/02 | Maturato 202003 | Maturato 202004 | Maturato 202005 | Maturato 202006 | Maturato 202007 | Maturato 202008 | Maturato 202009 | Maturato 202010 | Maturato 202011 | Maturato 202012 | Maturato 202101 | Maturato 202102 | Maturato 202103 | Maturato 202104 | Maturato 202105 | Maturato 202106 | Maturato 202107 | Maturato 202108 | Maturato 202109 | Totale Maturato | RevTab al 29/02 | RevTab 202003 | RevTab 202004 | RevTab 202005 | RevTab 202006 | RevTab 202007 | RevTab 202008 | RevTab 202009 | RevTab 202010 | RevTab 202011 | RevTab 202012 | RevTab 202101 | RevTab 202102 | RevTab 202103 | RevTab 202104 | RevTab 202105 | RevTab 202106 | RevTab 202107 | RevTab 202108 | RevTab 202109 | Totale RevTab
| Richiedente | Palandrani | [6 empty] | Stima | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Addante, Davide | NSW |  | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Ambito | - | [6 empty] | Pianificazione | NO | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Mercuri, Emanuela | NSW |  | 36 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Risorse | Malacrida Alessandro | Arcari Gabriella | Cutrullà Domenico | Montalbano Emanuele | Pastore Maria | Brescia Gennaro |  | Go A partire | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Iovieno, Salvatore | NSW | P1716976.10Iovieno, SalvatoreNSW | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Release | [7 empty] | Creazione Offerta | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Brescia, Gennaro | NSW | P1716976.10Brescia, GennaroNSW | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Data Avvio lavori | 2021-12-17 | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Capodici, Paolo | NSW |  | 25 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Bucket | Design |  |  |  | Descrizione | riferimento Alten Montalbano Rivedere GG e Budget | [77 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Djimeli Tchinda, Yolande Alida | NSW |  | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| %completamento | 100% | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Malacrida, Alessandro | NSW |  | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Prossima MIlestone | 2022-01-10 | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Malorgio, Gloria | NSW | P1716976.10Malorgio, GloriaNSW | 30 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Riferimenti Stima | ISP20220125_CJUnico_rel05_2022_integrazione_REV.xlsx (240) ISP20220216_price_optimization.xlsx (55) ISP20220219_CJPrestitiRLO_nuovoAccessoCQP.xlsx (36) Prestiti - ingaggio Alten per ulteriori attività - Rating (35) Metaconto - Lettere di rifiuto (53) | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Cutrullà, Domenico | NSW |  | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Stima | 452 | 3616 | 103960 | 230 | #REF! | [5 empty] | 44543 | 44669 | [71 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Montalbano, Emanuele | NSW | P1716976.10Montalbano, EmanueleNSW | 35 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Stato | Coerente | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Montalbano, Emanuele | STR | P1716976.10Montalbano, EmanueleSTR | 35 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
BASELINE | [65 empty] | FTE |  |  | Settimana | BASELINE | EFFETTIVO | BCWS | EV | ACWP | CPI | SPI | CV | SV | COMMESSA | REV TAB | BCWS-ACWP |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Pastore, Maria | NSW |  | 25 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[66 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Pastore, Maria | STR |  | 25 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[9 empty] | Andamento progetto |  |  | FTE | 452 | 0 | 0 | 0 | 21 | 26 | 19 | 37 | 41 | 43 | 46 | 35 | 35 | 33 | 24 | 26 | 24 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-01-03 | 2022-01-09 | S2 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Calò, Gaia | NSW |  | 12.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[12 empty] | ORE | 3616 | 0 | 0 | 0 | 168 | 208 | 152 | 296 | 328 | 344 | 368 | 280 | 280 | 264 | 192 | 208 | 192 | 112 | 112 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-01-10 | 2022-01-16 | S3 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Rubes, Federico | NSW |  | 27.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[66 empty] | 0 | 2022-01-17 | 2022-01-23 | S4 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Tuzio, Giuseppe | NSW | P1716976.10Tuzio, GiuseppeNSW | 36 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 3.45 | 2022-01-24 | 2022-01-30 | S5 | 4830 | 0 | 4830 | 1702 | 0 | - | 0.35238 | 1702 | -3128 | -4830 | 340.4 | 4830 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Leonardi, Angelo | NSW |  | 27.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
|  | Data Inizio | Data Fine | Durata | PESO | n sett INIZIO | n sett FINE | NOTE Pianificazione | FTE Allocati |  |  |  | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 4.2714 | 2022-01-31 | 2022-02-06 | S6 | 5980 | 0 | 10810 | 3404 | 0 | - | 0.31489 | 3404 | -7406 | -15640 | 680.8 | 10810 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Tento, Mattia | NSW |  | 12.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| CJ unico R5 Integration Paland. | 2021-12-17 | 2022-04-15 | 120 | 100% | 51 | 16 |  | 2.9 | 100% | allocazione budget "ideale" | Baseline | € | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | 3.1214 | 2022-02-07 | 2022-02-13 | S7 | 4370 | 0 | 15180 | 9706 | 0 | - | 0.63939 | 9706 | -5474 | -30820 | 1941.2 | 15180
| Design Rel 05 - Integrazione | 2022-01-24 | 2022-02-11 | 19 | 9% | 5 | 7 |  | 0 | 9% | 9356.4 | Design Rel 05 - Integrazione | 8510 |  |  |  | 2070 | 2070 | 2070 |  |  | 460 | 920 | 920 | [41 empty] | 6.0786 | 2022-02-14 | 2022-02-20 | S8 | 8510 | 0 | 23690 | 21677.5 | 0 | - | 0.91505 | 21677.5 | -2012.5 | -54510 | 4335.5 | 23690
| EXEC Rel 05 - Integrazione | 2022-02-14 | 2022-04-15 | 61 | 31% | 8 | 16 |  | 0.15 | 31% | 32227.6 | EXEC Rel 05 - Integrazione | 27830 | [6 empty] | 2070 | 2070 | 2070 | 4370 | 2300 | 2300 | 2990 | 1610 | 1610 | 1610 | 1610 | 1610 | 1610 | [33 empty] | 6.7357 | 2022-02-21 | 2022-02-27 | S9 | 9430 | 0 | 33120 | 27577 | 0 | - | 0.83264 | 27577 | -5543 | -87630 | 5515.4 | 33120
| RETEST Rel 05 - Integrazione | 2022-02-14 | 2022-04-15 | 61 | 7% | 8 | 16 | 11/04 UAT | 0.2 | 7% | 7277.2 | RETEST Rel 05 - Integrazione | 11270 | [11 empty] | 460 | 1150 | 1610 | 1610 | 1610 | 1610 | 1610 | 1610 | [33 empty] | 7.0643 | 2022-02-28 | 2022-03-06 | S10 | 9890 | 0 | 43010 | 36250.3 | 0 | - | 0.84283 | 36250.3 | -6759.7 | -130640 | 7250.06 | 43010
| MNG Rel 05 - Integrazione | 2022-01-24 | 2022-04-15 | 82 | 9% | 5 | 16 |  | 0.55 | 9% | 9356.4 | MNG Rel 05 - Integrazione | 8280 |  |  |  |  | 1150 |  |  | 1150 |  |  |  | 460 | 1610 | 1150 | 1610 | 1150 | [36 empty] | 7.5571 | 2022-03-07 | 2022-03-13 | S11 | 10580 | 0 | 53590 | 46586.5 | 0 | - | 0.86931 | 46586.5 | -7003.5 | -184230 | 9317.3 | 53590
| Data Preparation Rel 05 - Integrazione | 2021-12-17 | 2022-01-10 | 25 | 18% | 51 | 3 |  | 0 | 18% | 18712.8 | Data Preparation Rel 05 - Integrazione | 20470 |  |  |  | 2300 |  |  | 2300 | 2300 | 2300 | 2300 | 1840 | 1840 | 1840 | 1150 | 1150 | 1150 | [36 empty] | 5.75 | 2022-03-14 | 2022-03-20 | S12 | 8050 | 0 | 61640 | 48691 | 0 | - | 0.78993 | 48691 | -12949 | -245870 | 9738.2 | 61640
| DESIGN Price | 2022-02-21 | 2022-02-25 | 5 | 5% | 9 | 9 |  | 0 | 5% | 5198 | DESIGN Price | 4830 |  |  |  |  | 2300 | 2300 | 230 | [45 empty] | 5.75 | 2022-03-21 | 2022-03-27 | S13 | 8050 | 0 | 69690 | 51687.9 | 0 | - | 0.74168 | 51687.9 | -18002.1 | -315560 | 10337.58 | 69690
| DP sys + UAT Price | 2022-02-21 | 2022-02-25 | 5 | 7% | 9 | 9 |  | 0 | 7% | 7277.2 | DP sys + UAT Price | 9200 | [6 empty] | 3450 | 3450 | 2300 | [43 empty] | 5.4214 | 2022-03-28 | 2022-04-03 | S14 | 7590 | 0 | 77280 | 60881 | 0 | - | 0.7878 | 60881 | -16399 | -392840 | 12176.2 | 77280
| EXEC Price | 2022-02-28 | 2022-03-16 | 17 | 9% | 10 | 12 |  | 0 | 9% | 9356.4 | EXEC Price | 9200 | [8 empty] | 2300 | 2300 | 2300 | 2300 | [40 empty] | 3.9429 | 2022-04-04 | 2022-04-10 | S15 | 5520 | 0 | 82800 | 67401.5 | 0 | - | 0.81403 | 67401.5 | -15398.5 | -475640 | 13480.3 | 82800
| MNG Price | 2022-02-21 | 2022-03-16 | 24 | 5% | 9 | 12 |  | 0 | 5% | 5198 | MNG Price | 4370 |  |  |  | 460 | 460 |  | 460 | 460 | 460 | 690 | 690 | 690 | [40 empty] | 4.2714 | 2022-04-11 | 2022-04-17 | S16 | 5980 | 0 | 88780 | 72553.5 | 0 | - | 0.81723 | 72553.5 | -16226.5 | -564420 | 14510.7 | 88780
[13 empty] | 103960 | 0 | 0 | 0 | 4830 | 5980 | 4370 | 8510 | 9430 | 9890 | 10580 | 8050 | 8050 | 7590 | 5520 | 5980 | 5520 | 3220 | 3220 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9429 | 2022-04-18 | 2022-04-24 | S17 | 5520 | 0 | 94300 | 84299.6 | 0 | - | 0.89395 | 84299.6 | -10000.4 | -658720 | 16859.92 | 94300
|  |  |  | 103960 | [8 empty] | 0 | [52 empty] | 2.3 | 2022-04-25 | 2022-05-01 | S18 | 3220 | 0 | 97520 | 85698 | 0 | - | 0.87877 | 85698 | -11822 | -756240 | 17139.6 | 97520
| Offerta | ISP20220331452_CJUnico_rel05_2022 | 452 | 103960 | [61 empty] | 2.3 | 2022-05-02 | 2022-05-08 | S19 | 3220 | 0 | 100740 | 91277.8 | 0 | - | 0.90607 | 91277.8 | -9462.2 | -856980 | 18255.56 | 100740
|  |  |  | 0 | [5 empty] | % Compl | % Budget | Costo | Tempo | [52 empty] | 2.3 | 2022-05-09 | 2022-05-15 | S20 | 3220 | 0 | 103960 | 94541.5 | 0 | - | 0.9094 | 94541.5 | -9418.5 | -960940 | 18908.3 | 103960
|  |  |  | 0 | [5 empty] | 100% | #REF! | #REF! | #REF! | [52 empty] | 0 | 2022-05-16 | 2022-05-22 | S21 | 0 | 0 | 103960 | 96761 | 0 | - | 0.93075 | 96761 | -7199 | -1064900 | 19352.2 | 103960
[11 empty] | #REF! | #REF! | #REF! | [52 empty] | 0 | 2022-05-23 | 2022-05-29 | S22 | 0 | 0 | 103960 | 96761 | 0 | - | 0.93075 | 96761 | -7199 | -1168860 | 19352.2 | 103960
[66 empty] | 0 | 2022-05-30 | 2022-06-05 | S23 | 0 | 0 | 103960 | 100153.5 | 0 | - | 0.96338 | 100153.5 | -3806.5 | -1272820 | 20030.7 | 103960
[12 empty] | Barbano Angela | #REF! | [52 empty] | 0 | 2022-06-06 | 2022-06-12 | S24 | 0 | 0 | 103960 | 103960 | 0 | - | 1 | 103960 | 0 | -1376780 | 20792 | 103960
[12 empty] | Garreffa Francesco | #REF! | [52 empty] | 0 | 2022-06-13 | 2022-06-19 | S25 | 0 | 0 | 103960 | 103960 | 0 | - | 1 | 103960 | 0 | -1480740 | 20792 | 103960
[12 empty] | Yuliya Savostykova | #REF! | [52 empty] | 0 | 2022-06-20 | 2022-06-26 | S26 | 0 | 0 | 103960 | 103960 | 0 | - | 1 | 103960 | 0 | -1584700 | 20792 | 103960
[12 empty] | Cutrullà Domenico | #REF! | [52 empty] | 0 | 2022-06-27 | 2022-07-03 | S27 | 0 | 0 | 103960 | 103960 | 0 | - | 1 | 103960 | 0 | -1688660 | 20792 | 103960
[12 empty] | Montalbano Emanuele | #REF! | [52 empty] | 0 | 2022-07-04 | 2022-07-10 | S28 | 0 | 0 | 103960 | 103960 | 0 | - | 1 | 103960 | 0 | -1792620 | 20792 | 103960
[12 empty] | Stefan Andrada | #REF! | [52 empty] | 0 | 2022-07-11 | 2022-07-17 | S29 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Ratti Alessia | #REF! | [52 empty] | 0 | 2022-07-18 | 2022-07-24 | S30 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | gg/u | #REF! | [52 empty] | 0 | 2022-07-25 | 2022-07-31 | S31 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2022-08-01 | 2022-08-07 | S32 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-08-08 | 2022-08-14 | S33 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2022-08-15 | 2022-08-21 | S34 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | FTE | #REF! | [52 empty] | 0 | 2022-08-22 | 2022-08-28 | S35 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| Supporto UAT | 3 | [9 empty] | BCWS | #REF! | [13 empty] | NOTE RITARDI | [38 empty] | 0 | 2022-08-29 | 2022-09-04 | S36 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| Supporto Week end | 3.625 | [9 empty] | EV | #REF! | [13 empty] | 14/03 - Aggiunto stream 3 - a fine settimana si aggiungera lo stream 4 | [38 empty] | 0 | 2022-09-05 | 2022-09-11 | S37 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | ACWP | #REF! | [13 empty] | 28/03/2022: inserire CQP | [38 empty] | 0 | 2022-09-12 | 2022-09-18 | S38 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | CPI | #REF! | [13 empty] | 01/04: ritardo dovuto allo sviluppo, blocchi ambienti | [38 empty] | 0 | 2022-09-19 | 2022-09-25 | S39 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | SPI | #REF! | [13 empty] | 22/04/2022: Rilasci sviluppo in ritardo. Proseguimento attività di esecuzione per metaà maggio | [38 empty] | 0 | 2022-09-26 | 2022-10-02 | S40 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | CV | #REF! | [13 empty] | 20/05: system sospeto, fase di retest in corso, slittano alcune attività alle rel successive | [38 empty] | 0 | 2022-10-03 | 2022-10-09 | S41 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0 | 0 | 0
[12 empty] | SV | #REF! | [52 empty] | 0 | 2022-10-10 | 2022-10-16 | S42 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | REV_TAB | #REF! | [52 empty] | 0 | 2022-10-17 | 2022-10-23 | S43 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-10-24 | 2022-10-30 | S44 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-10-31 | 2022-11-06 | S45 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-11-07 | 2022-11-13 | S46 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-11-14 | 2022-11-20 | S47 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-11-21 | 2022-11-27 | S48 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-11-28 | 2022-12-04 | S49 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
EFFETTIVO | [65 empty] | 0 | 2022-12-05 | 2022-12-11 | S50 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-12-12 | 2022-12-18 | S51 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | FTE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2022-12-19 | 2022-12-25 | S52 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | ORE |  | 0 | 0 | 8 | 120 | 120 | 80 | 80 | 80 | 80 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-12-26 | 2023-01-01 | S53 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2023-01-02 | 2023-01-08 | S1 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 0 | 2023-01-09 | 2023-01-15 | S2 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
|  | 43290 | 43392 | Durata | % | n sett INIZIO | n sett FINE | NOTE Realizzazione |  |  |  |  | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 0 | 2023-01-16 | 2023-01-22 | S3 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| CJ unico R5 Integration Paland. | 0 |  | 1899-12-31 | 100% | 0 | 0 |  |  |  |  | Barbano Angela | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | 0 | 2023-01-23 | 2023-01-29 | S4 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| Analisi |  |  | 0 | 100% | 0 | 0 |  |  |  |  | Design Rel 05 - Integrazione | 80 |  |  |  | 40 | 40 | [47 empty] | 0 | 2023-01-30 | 2023-02-05 | S5 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| Sviluppo |  |  | 0 | 100% | 0 | 0 |  |  |  |  | EXEC Rel 05 - Integrazione | 0 | [52 empty] | 0 | 2023-02-06 | 2023-02-12 | S6 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| System test |  |  | 0 | 100% | 0 | 0 |  |  |  |  | RETEST Rel 05 - Integrazione | 0 | [52 empty] | 0 | 2023-02-13 | 2023-02-19 | S7 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| UAT |  |  | 0 | 100% | 0 | 0 |  |  |  |  | MNG Rel 05 - Integrazione | 0 | [52 empty] | 0 | 2023-02-20 | 2023-02-26 | S8 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| PRODUZIONE |  |  | 0 | 100% | 0 | 0 |  |  |  |  | Data Preparation Rel 05 - Integrazione | 0 | [52 empty] | 0 | 2023-02-27 | 2023-03-05 | S9 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| #REF! |  |  | 0 | 100% | 0 | 0 |  |  |  |  | DESIGN Price | 0 | [52 empty] | 0 | 2023-03-06 | 2023-03-12 | S10 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| #REF! |  |  | 0 | 100% | 0 | 0 |  |  |  |  | DP sys + UAT Price | 0 | [52 empty] | 0 | 2023-03-13 | 2023-03-19 | S11 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| #REF! |  |  | 0 | 100% | 0 | 0 |  |  |  |  | EXEC Price | 0 | [52 empty] | 0 | 2023-03-20 | 2023-03-26 | S12 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| #REF! |  |  | 0 | 100% | 0 | 0 |  |  |  |  | MNG Price | 0 | [52 empty] | 0 | 2023-03-27 | 2023-04-02 | S13 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | 80 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-04-03 | 2023-04-09 | S14 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2023-04-10 | 2023-04-16 | S15 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 0 | 2023-04-17 | 2023-04-23 | S16 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 0 | 2023-04-24 | 2023-04-30 | S17 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Garreffa Francesco | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | 0 | 2023-05-01 | 2023-05-07 | S18 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Design Rel 05 - Integrazione | 200 |  |  |  |  | 40 | 40 | 40 | 40 | 40 | [43 empty] | 0 | 2023-05-08 | 2023-05-14 | S19 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | si | invio Stima |  |  |  | EXEC Rel 05 - Integrazione | 0 | [52 empty] | 0 | 2023-05-15 | 2023-05-21 | S20 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | si | accettazione STIMA |  |  |  | RETEST Rel 05 - Integrazione | 0 | [52 empty] | 0 | 2023-05-22 | 2023-05-28 | S21 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[8 empty] | Pianificazione |  |  |  | MNG Rel 05 - Integrazione | 0 | [52 empty] | 0 | 2023-05-29 | 2023-06-04 | S22 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | si | GO a Partire |  |  |  | Data Preparation Rel 05 - Integrazione | 40 |  |  |  | 40 | [48 empty] | 0 | 2023-06-05 | 2023-06-11 | S23 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | si | Creazione offerta |  |  |  | DESIGN Price | 0 | [52 empty] | 0 | 2023-06-12 | 2023-06-18 | S24 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | no | invio proposta Formale |  |  |  | DP sys + UAT Price | 0 | [52 empty] | 0 | 2023-06-19 | 2023-06-25 | S25 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | no | Creazione work order |  |  |  | EXEC Price | 0 | [52 empty] | 0 | 2023-06-26 | 2023-07-02 | S26 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | MNG Price | 0 | [52 empty] | 0 | 2023-07-03 | 2023-07-09 | S27 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | 240 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-07-10 | 2023-07-16 | S28 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2023-07-17 | 2023-07-23 | S29 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 0 | 2023-07-24 | 2023-07-30 | S30 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 0 | 2023-07-31 | 2023-08-06 | S31 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Yuliya Savostykova | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 |  | 2023-08-07 | 2023-08-13 | S32 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Design Rel 05 - Integrazione | 160 |  |  |  |  | 40 | 40 | 40 | 40 | [45 empty] | 2023-08-14 | 2023-08-20 | S33 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | EXEC Rel 05 - Integrazione | 0 | [53 empty] | 2023-08-21 | 2023-08-27 | S34 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | RETEST Rel 05 - Integrazione | 0 | [53 empty] | 2023-08-28 | 2023-09-03 | S35 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | MNG Rel 05 - Integrazione | 0 | [53 empty] | 2023-09-04 | 2023-09-10 | S36 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 48 |  |  | 8 | 40 | [49 empty] | 2023-09-11 | 2023-09-17 | S37 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | DESIGN Price | 0 | [53 empty] | 2023-09-18 | 2023-09-24 | S38 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | DP sys + UAT Price | 0 | [53 empty] | 2023-09-25 | 2023-10-01 | S39 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | EXEC Price | 0 | [53 empty] | 2023-10-02 | 2023-10-08 | S40 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | MNG Price | 0
[13 empty] | 208 | 0 | 0 | 8 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Cutrullà Domenico | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 0
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 240 | [8 empty] | 40 |  |  | 40 | 40 |  |  |  |  | 40 | 40 | 40
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Montalbano Emanuele | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 80 | [8 empty] | 40 | 40
[12 empty] | EXEC Rel 05 - Integrazione | 168 | [10 empty] | 40 | 40 | 40 | 48
[12 empty] | RETEST Rel 05 - Integrazione | 80 | [14 empty] | 40 |  | 40
[12 empty] | MNG Rel 05 - Integrazione | 248 | [17 empty] | 40 | 16 | 40 | 40 | 32 | 40 | 40
[12 empty] | Data Preparation Rel 05 - Integrazione | 0
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 48 | 40 | 0 | 40 | 40 | 16 | 40 | 40 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Stefan Andrada | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 0
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 312 | [8 empty] | 40 | 40 |  | 40 | 40 |  |  |  |  | 40 | 40 | 40 | 32
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Tosti Nicola | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 40 | [18 empty] | 40
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 0
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Cicatelli Concetta | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 280 | [8 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 0
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 200 | [15 empty] | 32 | 32 | 40 | 40 | 24 | 32
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 40 | 40 | 24 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Autiero Stefano | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 40 | [8 empty] | 40
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 0
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 488 | [10 empty] | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 40 | 40 | 40 | 40 | 24 |  | 40
[12 empty] | MNG Price | 0
[13 empty] | 528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 40 | 40 | 40 | 40 | 24 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Ecaterina Mahu | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 0
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 104 | [8 empty] | 40 | 32 | 32
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Ratti Alessia | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 80 | [8 empty] | 40 | 40
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 352 | [10 empty] | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 40 | 24 | 24
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 40 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Mazzoni Alessandro | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 0
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 240 | [8 empty] | 40 | 40 | 40 | 40 | 40 | [11 empty] | 40
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Boggia Ilaria | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 0
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 496 | [8 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Motto Francesco | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 280 | [8 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40
[12 empty] | RETEST Rel 05 - Integrazione | 64 | [15 empty] | 32 | 32
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 0
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Carrieri Alessandro | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 0
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 160 | [9 empty] | 40 | 40 | 40 | 40
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 80 | [13 empty] | 40 | 40
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 288 | [15 empty] | 32 | 32 | 40 | 40 | 40 | 40 | 24 |  | 40
[13 empty] | 528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 40 | 40 | 40 | 40 | 24 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Malacrida Alessandro | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 0
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 206 | [10 empty] | 40 | 46 | 40 | 40 | 40
[12 empty] | Data Preparation Rel 05 - Integrazione | 16 | [15 empty] | 16
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 46 | 40 | 40 | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Romano Raffaele | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 0
[12 empty] | EXEC Rel 05 - Integrazione | 24 | [10 empty] | 24
[12 empty] | RETEST Rel 05 - Integrazione | 0
[12 empty] | MNG Rel 05 - Integrazione | 0
[12 empty] | Data Preparation Rel 05 - Integrazione | 280 | [11 empty] | 40 | 40 | 40 | 40 | 32 | 32 | 40 | [5 empty] | 16
[12 empty] | DESIGN Price | 0
[12 empty] | DP sys + UAT Price | 0
[12 empty] | EXEC Price | 0
[12 empty] | MNG Price | 0
[13 empty] | 304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 40 | 40 | 40 | 32 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | ACWP | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | EXEC Rel 05 - Integrazione | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | RETEST Rel 05 - Integrazione | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | MNG Rel 05 - Integrazione | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | Data Preparation Rel 05 - Integrazione | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | DESIGN Price | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | DP sys + UAT Price | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | EXEC Price | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | MNG Price | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | % completamento | 100% | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 100% | 0% | 0% | 0% | 20% | 40% | 60% | 90% | 90% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | EXEC Rel 05 - Integrazione | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 10% | 16% | 20% | 22% | 25% | 30% | 40% | 55% | 67% | 70% | 81% | 88% | 90% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | RETEST Rel 05 - Integrazione | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 16% | 20% | 22% | 22% | 40% | 55% | 60% | 60% | 65% | 80% | 88% | 90% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | MNG Rel 05 - Integrazione | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 11% | 15% | 15% | 30% | 60% | 60% | 65% | 65% | 65% | 75% | 80% | 85% | 85% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | Data Preparation Rel 05 - Integrazione | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 20% | 20% | 20% | 35% | 45% | 45% | 85% | 85% | 85% | 85% | 90% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | DESIGN Price | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 90% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | DP sys + UAT Price | 100% | 0% | 0% | 0% | 0% | 0% | 50% | 90% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | EXEC Price | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 50% | 85% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | MNG Price | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80% | 90% | 90% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[14 empty] | 0% | 0% | 0% | 1.8% | 3.6% | 8.9% | 20.45% | 26.5% | 34.22% | 44.75% | 46.91% | 50.09% | 58.55% | 64.5% | 69.95% | 81.12% | 82.4% | 87.76% | 90.94% | 93.05% | 93.05% | 96.3% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | EV | 103960 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design Rel 05 - Integrazione | 8510 | 0 | 0 | 0 | 1702 | 3404 | 5106 | 7659 | 7659 | 8084.5 | 8084.5 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510 | 8510
[12 empty] | EXEC Rel 05 - Integrazione | 27830 | 0 | 0 | 0 | 0 | 0 | 0 | 1391.5 | 2783 | 4452.8 | 5566 | 6122.6 | 6957.5 | 8349 | 11132 | 15306.5 | 18646.1 | 19481 | 22542.3 | 24490.4 | 25047 | 25047 | 26438.5 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830 | 27830
[12 empty] | RETEST Rel 05 - Integrazione | 11270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803.2 | 2254 | 2479.4 | 2479.4 | 4508 | 6198.5 | 6762 | 6762 | 7325.5 | 9016 | 9917.6 | 10143 | 10143 | 10706.5 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270 | 11270
[12 empty] | MNG Rel 05 - Integrazione | 8280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 828 | 910.8 | 1242 | 1242 | 2484 | 4968 | 4968 | 5382 | 5382 | 5382 | 6210 | 6624 | 7038 | 7038 | 7452 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280 | 8280
[12 empty] | Data Preparation Rel 05 - Integrazione | 20470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3070.5 | 4094 | 4094 | 4094 | 7164.5 | 9211.5 | 9211.5 | 17399.5 | 17399.5 | 17399.5 | 17399.5 | 18423 | 18423 | 19446.5 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470 | 20470
[12 empty] | DESIGN Price | 4830 | 0 | 0 | 0 | 0 | 0 | 0 | 4347 | 4347 | 4588.5 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830 | 4830
[12 empty] | DP sys + UAT Price | 9200 | 0 | 0 | 0 | 0 | 0 | 4600 | 8280 | 8280 | 8740 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200
[12 empty] | EXEC Price | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 4600 | 7820 | 8280 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200
[12 empty] | MNG Price | 4370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3496 | 3933 | 3933 | 4151.5 | 4151.5 | 4151.5 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370 | 4370
[14 empty] | 0 | 0 | 0 | 1702 | 3404 | 9706 | 21677.5 | 27577 | 36250.3 | 46586.5 | 48691 | 51687.9 | 60881 | 67401.5 | 72553.5 | 84299.6 | 85698 | 91277.8 | 94541.5 | 96761 | 96761 | 100153.5 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960 | 103960
[12 empty] | AVANZAMENTO PROGETTO | 100%: gg tot; S2: %avanz.; S3: risorsa; S4: gg effettivi; S5: coperto
Gestione Progetto
Recepimento requisiti funzionali e coordinamento
Analisi
[12 empty] | Design | 100%: 40; S2: 70%
[12 empty] | Esecuzione | 100%: gg tot; S2: %avanz.; S3: risorsa; S4: gg effettivi; S5: coperto
[12 empty] | Esecuzione, Retest, Test Management, NRT | 100%: 148; S4: 3
Restest e Rilascio
[12 empty] | Supporto UAT | 100%: 10
[12 empty] | AVANZAMENTO PROGETTO | 100%: 14.14%
AVANZAMENTO ANALISI | bar: 100% to S5
AVANZAMENTO ESECUZIONE | bar: 100% to S5
[12 empty] | GG RESIDUI | 100%: 170
Formulas:
Malacrida Alessandro = MIN([Malacrida Alessandro, row below]:C30)
Note on CG55: Chiara DE RIGGI: rev tab
Note on CH55: Chiara DE RIGGI: acwp
Note on AO118: Chiara DE RIGGI: 10h effettive
Note on AS327: Chiara DE RIGGI: lotto3

## CJ unico R5 Integration Cateno (hidden)
| Nome Progetto | CJ unico R5 Integration Cateno (metaconto)
| Responsabile | Malacrida Alessandro | [81 empty] | Note | BM | Referente | Workorder | Status | Text WO | Data Inizio | Data Fine | Fatturazione | OFFERTA | Residuo da Maturato | M% | Residuo da RevTab | RT% | Text Ressource | Time Code |  | PriceList | Hours 202003 | Hours 202004 | Hours 202005 | Hours 202006 | Hours 202007 | Hours 202008 | Hours 202009 | Hours 202010 | Hours 202011 | Hours 202012 | Hours 202101 | Hours 202102 | Hours 202103 | Hours 202104 | Hours 202105 | Hours 202106 | Hours 202107 | Hours 202108 | Hours 202109 | Maturato al 29/02 | Maturato 202003 | Maturato 202004 | Maturato 202005 | Maturato 202006 | Maturato 202007 | Maturato 202008 | Maturato 202009 | Maturato 202010 | Maturato 202011 | Maturato 202012 | Maturato 202101 | Maturato 202102 | Maturato 202103 | Maturato 202104 | Maturato 202105 | Maturato 202106 | Maturato 202107 | Maturato 202108 | Maturato 202109 | Totale Maturato | RevTab al 29/02 | RevTab 202003 | RevTab 202004 | RevTab 202005 | RevTab 202006 | RevTab 202007 | RevTab 202008 | RevTab 202009 | RevTab 202010 | RevTab 202011 | RevTab 202012 | RevTab 202101 | RevTab 202102 | RevTab 202103 | RevTab 202104 | RevTab 202105 | RevTab 202106 | RevTab 202107 | RevTab 202108 | RevTab 202109 | Totale RevTab
| Richiedente | Maccarrone Cateno | [6 empty] | Stima | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Addante, Davide | NSW |  | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Ambito | - | [6 empty] | Pianificazione | NO | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Mercuri, Emanuela | NSW |  | 36 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Risorse | Malacrida Alessandro | Arcari Gabriella | Cutrullà Domenico | Montalbano Emanuele | Pastore Maria | Brescia Gennaro |  | Go A partire | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Iovieno, Salvatore | NSW | P1716976.10Iovieno, SalvatoreNSW | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Release | [7 empty] | Creazione Offerta | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Brescia, Gennaro | NSW | P1716976.10Brescia, GennaroNSW | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Data Avvio lavori | 2021-08-23 | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Capodici, Paolo | NSW |  | 25 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Bucket | Design |  |  |  | Descrizione | [78 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Djimeli Tchinda, Yolande Alida | NSW |  | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| %completamento | 100% | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Malacrida, Alessandro | NSW |  | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Prossima MIlestone | 2022-01-10 | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Malorgio, Gloria | NSW | P1716976.10Malorgio, GloriaNSW | 30 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Riferimenti Stima | ISP20220125_CJUnico_integrazione_Metaconto_05_22.xlsx | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Cutrullà, Domenico | NSW |  | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Stima | 165 | 1320 | 37950 | 230 | #REF! | [5 empty] | 44585 | 44704 | [71 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Montalbano, Emanuele | NSW | P1716976.10Montalbano, EmanueleNSW | 35 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Stato | Coerente | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Montalbano, Emanuele | STR | P1716976.10Montalbano, EmanueleSTR | 35 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
BASELINE | [65 empty] | FTE |  |  | Settimana | BASELINE | EFFETTIVO | BCWS | EV | ACWP | CPI | SPI | CV | SV | COMMESSA | REV TAB | BCWS-ACWP |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Pastore, Maria | NSW |  | 25 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[66 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Pastore, Maria | STR |  | 25 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[9 empty] | Andamento progetto |  |  | FTE | 165 | 0 | 0 | 0 | 5 | 5 | 8 | 5 | 0 | 0 | 10 | 15 | 15 | 20 | 15 | 15 | 12 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-01-03 | 2022-01-09 | S2 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Calò, Gaia | NSW |  | 12.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[12 empty] | ORE | 1320 | 0 | 0 | 0 | 40 | 40 | 64 | 40 | 0 | 0 | 80 | 120 | 120 | 160 | 120 | 120 | 96 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-01-10 | 2022-01-16 | S3 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Rubes, Federico | NSW |  | 27.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[66 empty] | 0 | 2022-01-17 | 2022-01-23 | S4 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Tuzio, Giuseppe | NSW | P1716976.10Tuzio, GiuseppeNSW | 36 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 0.82143 | 2022-01-24 | 2022-01-30 | S5 | 1150 | 0 | 1150 | 0 | 0 | - | 0 | 0 | -1150 | -1150 | 0 | 1150 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Leonardi, Angelo | NSW |  | 27.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
|  | Data Inizio | Data Fine | Durata | PESO | n sett INIZIO | n sett FINE | NOTE Pianificazione | FTE Allocati |  |  |  | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 0.82143 | 2022-01-31 | 2022-02-06 | S6 | 1150 | 0 | 2300 | 0 | 0 | - | 0 | 0 | -2300 | -3450 | 0 | 2300 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Tento, Mattia | NSW |  | 12.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| CJ unico R5 Integration Cateno (metaconto) | 2022-01-24 | 2022-05-17 | 114 | 118% | 5 | 21 |  | 2.9 | 100% | allocazione budget "ideale" | Baseline | € | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | 1.3143 | 2022-02-07 | 2022-02-13 | S7 | 1840 | 0 | 4140 | 4140 | 0 | - | 1 | 4140 | 0 | -7590 | 828 | 4140
| Design | 2022-01-26 | 2022-02-15 | 21 | 20% | 5 | 8 |  | 0 | 11% | 4174.5 | Design | 4600 |  |  |  | 1150 | 1150 | 1150 | 1150 | [45 empty] | 0.82143 | 2022-02-14 | 2022-02-20 | S8 | 1150 | 0 | 5290 | 4600 | 0 | - | 0.86957 | 4600 | -690 | -12880 | 920 | 5290
| EXEC | 2022-02-23 | 2022-04-15 | 52 | 20% | 9 | 16 |  | 0.15 | 46% | 17457 | EXEC | 12650 | [9 empty] | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | [32 empty] | 0 | 2022-02-21 | 2022-02-27 | S9 | 0 | 0 | 5290 | 4600 | 0 | - | 0.86957 | 4600 | -690 | -18170 | 920 | 5290
| RETEST | 2022-01-24 | 2022-04-15 | 82 | 35% | 5 | 16 |  | 0.2 | 12% | 4554 | RETEST | 9200 | [12 empty] | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | [32 empty] | 0 | 2022-02-28 | 2022-03-06 | S10 | 0 | 0 | 5290 | 4600 | 0 | - | 0.86957 | 4600 | -690 | -23460 | 920 | 5290
| MNG | 2022-04-04 | 2022-05-17 | 44 | 7% | 15 | 21 |  | 0.55 | 17% | 6451.5 | MNG | 6210 | [10 empty] | 1150 | 1150 | 1150 | 1150 | 1150 | 460 | [36 empty] | 1.6429 | 2022-03-07 | 2022-03-13 | S11 | 2300 | 0 | 7590 | 6923 | 0 | - | 0.91212 | 6923 | -667 | -31050 | 1384.6 | 7590
| DATA PREP | 2022-01-26 | 2022-02-15 | 21 | 18% | 5 | 8 |  | 1 | 14% | 5313 | DATA PREP | 5290 | [5 empty] | 690 |  |  |  | 1150 | 1150 | 1150 | 1150 | [39 empty] | 2.4643 | 2022-03-14 | 2022-03-20 | S12 | 3450 | 0 | 11040 | 9246 | 0 | - | 0.8375 | 9246 | -1794 | -42090 | 1849.2 | 11040
|  |  |  | 0 | 18% | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | [52 empty] | 2.4643 | 2022-03-21 | 2022-03-27 | S13 | 3450 | 0 | 14490 | 9246 | 0 | - | 0.6381 | 9246 | -5244 | -56580 | 1849.2 | 14490
|  |  |  | 0 | 0% | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | [52 empty] | 3.2857 | 2022-03-28 | 2022-04-03 | S14 | 4600 | 0 | 19090 | 10143 | 0 | - | 0.53133 | 10143 | -8947 | -75670 | 2028.6 | 19090
|  |  |  | 0 | 0% | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | [52 empty] | 2.4643 | 2022-04-04 | 2022-04-10 | S15 | 3450 | 0 | 22540 | 15479 | 0 | - | 0.68673 | 15479 | -7061 | -98210 | 3095.8 | 22540
|  |  |  | 0 | 0% | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | [52 empty] | 2.4643 | 2022-04-11 | 2022-04-17 | S16 | 3450 | 0 | 25990 | 19665 | 0 | - | 0.75664 | 19665 | -6325 | -124200 | 3933 | 25990
[13 empty] | 37950 | 0 | 0 | 0 | 1150 | 1150 | 1840 | 1150 | 0 | 0 | 2300 | 3450 | 3450 | 4600 | 3450 | 3450 | 2760 | 2300 | 2300 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9714 | 2022-04-18 | 2022-04-24 | S17 | 2760 | 0 | 28750 | 23425.5 | 0 | - | 0.8148 | 23425.5 | -5324.5 | -152950 | 4685.1 | 28750
|  |  |  | 0 | [8 empty] | 0 | [52 empty] | 1.6429 | 2022-04-25 | 2022-05-01 | S18 | 2300 | 0 | 31050 | 24196 | 0 | - | 0.77926 | 24196 | -6854 | -184000 | 4839.2 | 31050
| Offerta |  |  | 0 | [61 empty] | 1.6429 | 2022-05-02 | 2022-05-08 | S19 | 2300 | 0 | 33350 | 24817 | 0 | - | 0.74414 | 24817 | -8533 | -217350 | 4963.4 | 33350
|  |  |  | 0 | [5 empty] | % Compl | % Budget | Costo | Tempo | [52 empty] | 1.6429 | 2022-05-09 | 2022-05-15 | S20 | 2300 | 0 | 35650 | 28313 | 0 | - | 0.79419 | 28313 | -7337 | -253000 | 5662.6 | 35650
|  |  |  | 0 | [5 empty] | 100% | #REF! | #REF! | #REF! | [52 empty] | 1.6429 | 2022-05-16 | 2022-05-22 | S21 | 2300 | 0 | 37950 | 30153 | 0 | - | 0.79455 | 30153 | -7797 | -290950 | 6030.6 | 37950
[11 empty] | #REF! | #REF! | #REF! | [52 empty] | 0 | 2022-05-23 | 2022-05-29 | S22 | 0 | 0 | 37950 | 30153 | 0 | - | 0.79455 | 30153 | -7797 | -328900 | 6030.6 | 37950
[66 empty] | 0 | 2022-05-30 | 2022-06-05 | S23 | 0 | 0 | 37950 | 30153 | 0 | - | 0.79455 | 30153 | -7797 | -366850 | 6030.6 | 37950
[12 empty] | Arcari Gabriella | #REF! | [52 empty] | 0 | 2022-06-06 | 2022-06-12 | S24 | 0 | 0 | 37950 | 33591.5 | 0 | - | 0.88515 | 33591.5 | -4358.5 | -404800 | 6718.3 | 37950
[12 empty] | Cutrullà Domenico | #REF! | [52 empty] | 0 | 2022-06-13 | 2022-06-19 | S25 | 0 | 0 | 37950 | 33591.5 | 0 | - | 0.88515 | 33591.5 | -4358.5 | -442750 | 6718.3 | 37950
[12 empty] | Tosti Nicola | #REF! | [52 empty] | 0 | 2022-06-20 | 2022-06-26 | S26 | 0 | 0 | 37950 | 33591.5 | 0 | - | 0.88515 | 33591.5 | -4358.5 | -480700 | 6718.3 | 37950
[12 empty] | Capodici Paolo | #REF! | [52 empty] | 0 | 2022-06-27 | 2022-07-03 | S27 | 0 | 0 | 37950 | 33591.5 | 0 | - | 0.88515 | 33591.5 | -4358.5 | -518650 | 6718.3 | 37950
[12 empty] | Mazzoni Alessandro | #REF! | [52 empty] | 0 | 2022-07-04 | 2022-07-10 | S28 | 0 | 0 | 37950 | 33591.5 | 0 | - | 0.88515 | 33591.5 | -4358.5 | -556600 | 6718.3 | 37950
[12 empty] | Pastore Maria | #REF! | [52 empty] | 0 | 2022-07-11 | 2022-07-17 | S29 | 0 | 0 | 37950 | 37950 | 0 | - | 1 | 37950 | 0 | -594550 | 7590 | 37950
[12 empty] | Rodsari Omid (DH) | #REF! | [52 empty] | 0 | 2022-07-18 | 2022-07-24 | S30 | 0 | 0 | 37950 | 37950 | 0 | - | 1 | 37950 | 0 | -632500 | 7590 | 37950
[12 empty] | gg/u | #REF! | [52 empty] | 0 | 2022-07-25 | 2022-07-31 | S31 | 0 | 0 | 37950 | 37950 | 0 | - | 1 | 37950 | 0 | -670450 | 7590 | 37950
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2022-08-01 | 2022-08-07 | S32 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-08-08 | 2022-08-14 | S33 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2022-08-15 | 2022-08-21 | S34 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | FTE | #REF! | [52 empty] | 0 | 2022-08-22 | 2022-08-28 | S35 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| Supporto UAT | 3 | [9 empty] | BCWS | #REF! | [52 empty] | 0 | 2022-08-29 | 2022-09-04 | S36 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| Supporto Week end | 3.625 | [9 empty] | EV | #REF! | [52 empty] | 0 | 2022-09-05 | 2022-09-11 | S37 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | ACWP | #REF! | [52 empty] | 0 | 2022-09-12 | 2022-09-18 | S38 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | CPI | #REF! | [52 empty] | 0 | 2022-09-19 | 2022-09-25 | S39 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | SPI | #REF! | [52 empty] | 0 | 2022-09-26 | 2022-10-02 | S40 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | CV | #REF! | [52 empty] | 0 | 2022-10-03 | 2022-10-09 | S41 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0 | 0 | 0
[12 empty] | SV | #REF! | [52 empty] | 0 | 2022-10-10 | 2022-10-16 | S42 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | REV_TAB | #REF! | [52 empty] | 0 | 2022-10-17 | 2022-10-23 | S43 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-10-24 | 2022-10-30 | S44 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-10-31 | 2022-11-06 | S45 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-11-07 | 2022-11-13 | S46 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-11-14 | 2022-11-20 | S47 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-11-21 | 2022-11-27 | S48 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-11-28 | 2022-12-04 | S49 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
EFFETTIVO | [65 empty] | 0 | 2022-12-05 | 2022-12-11 | S50 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[66 empty] | 0 | 2022-12-12 | 2022-12-18 | S51 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | FTE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2022-12-19 | 2022-12-25 | S52 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | ORE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 40 | 88 | 32 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-12-26 | 2023-01-01 | S53 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | Tariffa €/h | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 0 | 2023-01-02 | 2023-01-08 | S1 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 0 | 2023-01-09 | 2023-01-15 | S2 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
|  | 43290 | 43392 | Durata | % | n sett INIZIO | n sett FINE | NOTE Realizzazione |  |  |  |  | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 0 | 2023-01-16 | 2023-01-22 | S3 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| CJ unico R5 Integration Cateno (metaconto) | 0 |  | 1899-12-31 | 100% | 0 | 0 |  |  |  |  | Arcari Gabriella | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | 0 | 2023-01-23 | 2023-01-29 | S4 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| Analisi |  |  | 0 | 100% | 0 | 0 |  |  |  |  | Design | 0 | [52 empty] | 0 | 2023-01-30 | 2023-02-05 | S5 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| Sviluppo |  |  | 0 | 100% | 0 | 0 |  |  |  |  | EXEC | 72 | [15 empty] | 32 | [6 empty] | 40 | [29 empty] | 0 | 2023-02-06 | 2023-02-12 | S6 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| System test |  |  | 0 | 100% | 0 | 0 |  |  |  |  | RETEST | 0 | [52 empty] | 0 | 2023-02-13 | 2023-02-19 | S7 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| UAT |  |  | 0 | 100% | 0 | 0 |  |  |  |  | MNG | 0 | [52 empty] | 0 | 2023-02-20 | 2023-02-26 | S8 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| PRODUZIONE |  |  | 0 | 100% | 0 | 0 |  |  |  |  | DATA PREP | 0 | [52 empty] | 0 | 2023-02-27 | 2023-03-05 | S9 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [52 empty] | 0 | 2023-03-06 | 2023-03-12 | S10 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [52 empty] | 0 | 2023-03-13 | 2023-03-19 | S11 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | #REF! | 0 | [52 empty] | 0 | 2023-03-20 | 2023-03-26 | S12 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | #REF! | 0 | [52 empty] | 0 | 2023-03-27 | 2023-04-02 | S13 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-04-03 | 2023-04-09 | S14 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2023-04-10 | 2023-04-16 | S15 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 0 | 2023-04-17 | 2023-04-23 | S16 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 0 | 2023-04-24 | 2023-04-30 | S17 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Cutrullà Domenico | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | 0 | 2023-05-01 | 2023-05-07 | S18 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Design | 0 | [52 empty] | 0 | 2023-05-08 | 2023-05-14 | S19 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | si | invio Stima |  |  |  | EXEC | 0 | [52 empty] | 0 | 2023-05-15 | 2023-05-21 | S20 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | si | accettazione STIMA |  |  |  | RETEST | 0 | [52 empty] | 0 | 2023-05-22 | 2023-05-28 | S21 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[8 empty] | Pianificazione |  |  |  | MNG | 0 | [52 empty] | 0 | 2023-05-29 | 2023-06-04 | S22 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | si | GO a Partire |  |  |  | DATA PREP | 120 | [9 empty] | 40 | 40 | [11 empty] | 40 | [29 empty] | 0 | 2023-06-05 | 2023-06-11 | S23 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | si | Creazione offerta |  |  |  | 0 | 0 | [52 empty] | 0 | 2023-06-12 | 2023-06-18 | S24 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | no | invio proposta Formale |  |  |  | 0 | 0 | [52 empty] | 0 | 2023-06-19 | 2023-06-25 | S25 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | no | Creazione work order |  |  |  | #REF! | 0 | [52 empty] | 0 | 2023-06-26 | 2023-07-02 | S26 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | #REF! | 0 | [52 empty] | 0 | 2023-07-03 | 2023-07-09 | S27 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-07-10 | 2023-07-16 | S28 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2023-07-17 | 2023-07-23 | S29 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 0 | 2023-07-24 | 2023-07-30 | S30 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 0 | 2023-07-31 | 2023-08-06 | S31 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Tosti Nicola | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | 0 | 2023-08-07 | 2023-08-13 | S32 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Design | 0 | [52 empty] | 0 | 2023-08-14 | 2023-08-20 | S33 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | EXEC | 40 | [15 empty] | 24 | [7 empty] | 16 | [28 empty] | 0 | 2023-08-21 | 2023-08-27 | S34 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | RETEST | 0 | [52 empty] | 0 | 2023-08-28 | 2023-09-03 | S35 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | MNG | 0 | [53 empty] | 2023-09-04 | 2023-09-10 | S36 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | DATA PREP | 0 | [53 empty] | 2023-09-11 | 2023-09-17 | S37 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0 | [53 empty] | 2023-09-18 | 2023-09-24 | S38 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0 | [53 empty] | 2023-09-25 | 2023-10-01 | S39 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | #REF! | 0 | [53 empty] | 2023-10-02 | 2023-10-08 | S40 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | #REF! | 0
[13 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Capodici Paolo | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 40 | [11 empty] | 40
[12 empty] | EXEC | 72 | [14 empty] | 40 | 32
[12 empty] | RETEST | 56 | [16 empty] | 32 | [6 empty] | 24
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Mazzoni Alessandro | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 0
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 40 | [23 empty] | 40
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Pastore Maria | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 0
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 40 | [22 empty] | 40
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 28.75
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Galeota Raffaela | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 0
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 432 | [9 empty] | 40 | 40 | 40 | 40 | 48 | 40 | 32 | 32 | 40 | 40 |  |  |  | 40
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 48 | 40 | 32 | 32 | 40 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Capodici Paolo | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 0
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Stefan Andrada | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 0
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 40 | [23 empty] | 40
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Malorgio Gloria | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 40 | [17 empty] | 40
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Rodsari Omid (DH) | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 0
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Ratti Alessia | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 0
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Mingione Giovanna | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 0
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Italiano Rossella | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 0
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Flotta Armando | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 40 | [18 empty] | 40
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Autiero Stefano | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 0
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | Yuliya Savostykova | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 0
[12 empty] | EXEC | 0
[12 empty] | RETEST | 0
[12 empty] | MNG | 0
[12 empty] | DATA PREP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | ACWP | #REF! | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | EXEC | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | RETEST | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | MNG | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | DATA PREP | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | % completamento | 100% | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 100% | 0% | 0% | 0% | 0% | 0% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | EXEC | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 20% | 25% | 27% | 31% | 46% | 46% | 46% | 70% | 70% | 70% | 70% | 85% | 85% | 85% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | RETEST | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 40% | 45% | 45% | 50% | 70% | 70% | 70% | 80% | 80% | 80% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | MNG | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 35% | 35% | 65% | 70% | 80% | 80% | 80% | 80% | 80% | 90% | 90% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | DATA PREP | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 40% | 40% | 45% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | bar: 100% to S53
0 | bar: 100% to S53
#REF! | bar: 100% to S53
#REF! | bar: 100% to S53
[14 empty] | 0% | 0% | 0% | 0% | 0% | 18% | 20% | 20% | 20% | 25.6% | 31.2% | 31.2% | 33.1% | 45.85% | 60.65% | 65.75% | 67.85% | 68.55% | 75.1% | 82.1% | 82.1% | 82.1% | 89.3% | 89.3% | 89.3% | 89.3% | 89.3% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[13 empty] | DAL | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
[13 empty] | AL | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01
[12 empty] | EV | 37950 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53
[12 empty] | Design | 4600 | 0 | 0 | 0 | 0 | 0 | 4140 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600
[12 empty] | EXEC | 12650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1265 | 2530 | 2530 | 3162.5 | 3415.5 | 3921.5 | 5819 | 5819 | 5819 | 8855 | 8855 | 8855 | 8855 | 10752.5 | 10752.5 | 10752.5 | 10752.5 | 10752.5 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650 | 12650
[12 empty] | RETEST | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 3680 | 4140 | 4140 | 4600 | 6440 | 6440 | 6440 | 7360 | 7360 | 7360 | 7360 | 7360 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200
[12 empty] | MNG | 6210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173.5 | 2173.5 | 4036.5 | 4347 | 4968 | 4968 | 4968 | 4968 | 4968 | 5589 | 5589 | 5589 | 5589 | 5589 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210 | 6210
[12 empty] | DATA PREP | 5290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058 | 2116 | 2116 | 2380.5 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290 | 5290
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 4140 | 4600 | 4600 | 4600 | 6923 | 9246 | 9246 | 10143 | 15479 | 19665 | 23425.5 | 24196 | 24817 | 28313 | 30153 | 30153 | 30153 | 33591.5 | 33591.5 | 33591.5 | 33591.5 | 33591.5 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950 | 37950
[12 empty] | AVANZAMENTO PROGETTO | 100%: gg tot; S2: %avanz.; S3: risorsa; S4: gg effettivi; S5: coperto
Gestione Progetto
Recepimento requisiti funzionali e coordinamento
Analisi
[12 empty] | Design | 100%: 40; S2: 70%
[12 empty] | Esecuzione | 100%: gg tot; S2: %avanz.; S3: risorsa; S4: gg effettivi; S5: coperto
[12 empty] | Esecuzione, Retest, Test Management, NRT | 100%: 148; S4: 3
Restest e Rilascio
[12 empty] | Supporto UAT | 100%: 10
[12 empty] | AVANZAMENTO PROGETTO | 100%: 14.14%
AVANZAMENTO ANALISI | bar: 100% to S5
AVANZAMENTO ESECUZIONE | bar: 100% to S5
[12 empty] | GG RESIDUI | 100%: 170
Formulas:
Malacrida Alessandro = MIN([Malacrida Alessandro, row below]:C30)
Note on CG55: Chiara DE RIGGI: rev tab
Note on CH55: Chiara DE RIGGI: acwp
Note on O118: Chiara DE RIGGI: gennaio
Note on AO118: Chiara DE RIGGI: 10h effettive
Note on AS327: Chiara DE RIGGI: lotto3

## CJ U. Model Change 05 2022 Petr (hidden)
| Nome Progetto | CJ Unico Model Change 05 2022
| Responsabile | Malacrida Alessandro | [81 empty] | Note | BM | Referente | Workorder | Status | Text WO | Data Inizio | Data Fine | Fatturazione | OFFERTA | Residuo da Maturato | M% | Residuo da RevTab | RT% | Text Ressource | Time Code |  | PriceList | Hours 202003 | Hours 202004 | Hours 202005 | Hours 202006 | Hours 202007 | Hours 202008 | Hours 202009 | Hours 202010 | Hours 202011 | Hours 202012 | Hours 202101 | Hours 202102 | Hours 202103 | Hours 202104 | Hours 202105 | Hours 202106 | Hours 202107 | Hours 202108 | Hours 202109 | Maturato al 29/02 | Maturato 202003 | Maturato 202004 | Maturato 202005 | Maturato 202006 | Maturato 202007 | Maturato 202008 | Maturato 202009 | Maturato 202010 | Maturato 202011 | Maturato 202012 | Maturato 202101 | Maturato 202102 | Maturato 202103 | Maturato 202104 | Maturato 202105 | Maturato 202106 | Maturato 202107 | Maturato 202108 | Maturato 202109 | Totale Maturato | RevTab al 29/02 | RevTab 202003 | RevTab 202004 | RevTab 202005 | RevTab 202006 | RevTab 202007 | RevTab 202008 | RevTab 202009 | RevTab 202010 | RevTab 202011 | RevTab 202012 | RevTab 202101 | RevTab 202102 | RevTab 202103 | RevTab 202104 | RevTab 202105 | RevTab 202106 | RevTab 202107 | RevTab 202108 | RevTab 202109 | Totale RevTab
| Richiedente | Petrosino Giovanni | [6 empty] | Stima | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Addante, Davide | NSW |  | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Ambito | - | [6 empty] | Pianificazione | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Mercuri, Emanuela | NSW |  | 36 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Risorse | Malacrida Alessandro | Arcari Gabriella | Cutrullà Domenico | Montalbano Emanuele | Pastore Maria | Brescia Gennaro |  | Go A partire | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Iovieno, Salvatore | NSW | P1716976.10Iovieno, SalvatoreNSW | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Release | [7 empty] | Creazione Offerta | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Brescia, Gennaro | NSW | P1716976.10Brescia, GennaroNSW | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Data Avvio lavori | 2022-01-26 | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Capodici, Paolo | NSW |  | 25 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Bucket | Design |  |  |  | Descrizione | ISP20220418283_CJ_RLO_Model_Change_rel05 | [77 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Djimeli Tchinda, Yolande Alida | NSW |  | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| %completamento | 100% | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Malacrida, Alessandro | NSW |  | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Prossima MIlestone | [83 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Malorgio, Gloria | NSW | P1716976.10Malorgio, GloriaNSW | 30 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Riferimenti Stima | ISP20220131_RLO_Model_Change_Retail_05_22_TestFactory.xlsx | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Cutrullà, Domenico | NSW |  | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Stima | 283 | 2264 | 65090 | 230 | #REF! | [5 empty] | 44585 | 44704 | [71 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Montalbano, Emanuele | NSW | P1716976.10Montalbano, EmanueleNSW | 35 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Stato | Coerente | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Montalbano, Emanuele | STR | P1716976.10Montalbano, EmanueleSTR | 35 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
BASELINE | [65 empty] | FTE |  |  | Settimana | BASELINE | EFFETTIVO | BCWS | EV | ACWP | CPI | SPI | CV | SV | COMMESSA | REV TAB | BCWS-ACWP |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Pastore, Maria | NSW |  | 25 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[66 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Pastore, Maria | STR |  | 25 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[9 empty] | Andamento progetto |  |  | FTE | 282 | 15 | 15 | 15 | 15 | 13 | 5 | 0 | 0 | 21 | 21 | 22 | 22 | 14 | 14 | 26 | 22 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-12-28 | 2021-01-03 | S53 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Calò, Gaia | NSW |  | 12.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[12 empty] | ORE | 2256 | 120 | 120 | 120 | 120 | 104 | 40 | 0 | 0 | 168 | 168 | 176 | 176 | 112 | 112 | 208 | 176 | 168 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-01-04 | 2021-01-10 | S2 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Rubes, Federico | NSW |  | 27.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[66 empty] | 0 | 2021-01-11 | 2021-01-17 | S3 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Tuzio, Giuseppe | NSW | P1716976.10Tuzio, GiuseppeNSW | 36 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 0 | 2021-01-18 | 2021-01-24 | S4 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Leonardi, Angelo | NSW |  | 27.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
|  | Data Inizio | Data Fine | Durata | PESO | n sett INIZIO | n sett FINE | NOTE Pianificazione | FTE Allocati |  |  |  | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 0 | 2021-01-25 | 2021-01-31 | S5 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Tento, Mattia | NSW |  | 12.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| CJ Unico Model Change 05 2022 | 2022-01-24 | 2022-05-17 | 114 | 100% | 5 | 21 |  | #REF! | 100% | allocazione budget "ideale" | Baseline | € | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | 0 | 2021-02-01 | 2021-02-07 | S6 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| DESIGN | 2022-01-26 | 2022-02-15 | 21 | 27% | 5 | 8 |  | 1 | 27% | 17574.3 | DESIGN | 16790 | 3450 | 3450 | 3450 | 3450 | 2990 | [47 empty] | 0 | 2021-02-08 | 2021-02-14 | S7 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| EXEC | 2022-03-23 | 2022-04-15 | 24 | 35% | 13 | 16 |  | #REF! | 35% | 22781.5 | EXEC | 25070 | [5 empty] | 1150 |  |  | 3450 | 3450 | 3450 | 3450 |  |  | 2760 | 2760 | 2300 | 2300 | [34 empty] | 0 | 2021-02-15 | 2021-02-21 | S8 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| MNG | 2022-01-24 | 2022-04-15 | 82 | 12% | 5 | 16 |  | #REF! | 12% | 7810.8 | MNG | 6900 | [8 empty] | 920 | 920 | 1150 | 1150 | 920 | 920 | 920 | [37 empty] | 0 | 2021-02-22 | 2021-02-28 | S9 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| UAT | 2022-04-04 | 2022-05-17 | 44 | 16% | 15 | 21 |  | #REF! | 16% | 10414.4 | UAT | 11040 | [12 empty] | 1840 | 1840 | 1840 | 1840 | 1840 | 1840 | [34 empty] | 0 | 2021-03-01 | 2021-03-07 | S10 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| DP | 2022-03-23 | 2022-05-17 | 56 | 10% | 13 | 21 | 1 | #REF! | 10% | 6509 | DP | 5060 | [8 empty] | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 690 | 690 | [34 empty] | 0 | 2021-03-08 | 2021-03-14 | S11 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! | 0% | 0 | 0 | 0 | [52 empty] | 0 | 2021-03-15 | 2021-03-21 | S12 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! | 0% | 0 | 0 | 0 | [52 empty] | 0 | 2021-03-22 | 2021-03-28 | S13 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! | 0% | 0 | 0 | 0 | [52 empty] | 0 | 2021-03-29 | 2021-04-04 | S14 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! | 0% | 0 | 0 | 0 | [52 empty] | 0 | 2021-04-05 | 2021-04-11 | S15 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[13 empty] | 64860 | 3450 | 3450 | 3450 | 3450 | 2990 | 1150 | 0 | 0 | 4830 | 4830 | 5060 | 5060 | 3220 | 3220 | 5980 | 5060 | 4830 | 4830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-12 | 2021-04-18 | S16 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 65090 | [8 empty] | 230 | [52 empty] | 0 | 2021-04-19 | 2021-04-25 | S17 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| Offerta | ISP20220418283_CJ_RLO_Model_Change_rel05 | 283 | 65090 | [61 empty] | 0 | 2021-04-26 | 2021-05-02 | S18 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | [5 empty] | % Compl | % Budget | Costo | Tempo | [52 empty] | 0 | 2021-05-03 | 2021-05-09 | S19 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | [5 empty] | 100% | #REF! | #REF! | #REF! | [52 empty] | 0 | 2021-05-10 | 2021-05-16 | S20 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | [52 empty] | 0 | 2021-05-17 | 2021-05-23 | S21 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[66 empty] | 0 | 2021-05-24 | 2021-05-30 | S22 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | Cicatelli Concetta | #REF! | [52 empty] | 0 | 2021-05-31 | 2021-06-06 | S23 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | Barbano Angela | #REF! | [52 empty] | 0 | 2021-06-07 | 2021-06-13 | S24 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | Stefan Andrada | #REF! | [52 empty] | 0 | 2021-06-14 | 2021-06-20 | S25 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | Italiano Rossella | #REF! | [52 empty] | 0 | 2021-06-21 | 2021-06-27 | S26 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | Arcari Gabriella | #REF! | [52 empty] | 0 | 2021-06-28 | 2021-07-04 | S27 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | Cutrullà Domenico | #REF! | [52 empty] | 0 | 2021-07-05 | 2021-07-11 | S28 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | Cetronio Giuseppe Rosario | #REF! | [52 empty] | 0 | 2021-07-12 | 2021-07-18 | S29 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | gg/u | #REF! | [52 empty] | 0 | 2021-07-19 | 2021-07-25 | S30 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2021-07-26 | 2021-08-01 | S31 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[66 empty] | 0 | 2021-08-02 | 2021-08-08 | S32 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2021-08-09 | 2021-08-15 | S33 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | FTE | #REF! | [52 empty] | 0 | 2021-08-16 | 2021-08-22 | S34 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| Supporto UAT | 3 | [9 empty] | BCWS | #REF! | [52 empty] | 0 | 2021-08-23 | 2021-08-29 | S35 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| Supporto Week end | 3.625 | [9 empty] | EV | #REF! | [13 empty] | 22/04/2022: Rilascio APP spostato al 27/04. TC 100 da fare | [38 empty] | 0 | 2021-08-30 | 2021-09-05 | S36 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | ACWP | #REF! | [52 empty] | 0 | 2021-09-06 | 2021-09-12 | S37 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | CPI | #REF! | [52 empty] | 0 | 2021-09-13 | 2021-09-19 | S38 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | SPI | #REF! | [52 empty] | 0 | 2021-09-20 | 2021-09-26 | S39 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | CV | #REF! | [52 empty] | 0 | 2021-09-27 | 2021-10-03 | S40 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | SV | #REF! | [52 empty] | 0 | 2021-10-04 | 2021-10-10 | S41 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | REV_TAB | #REF! | [52 empty] | 0 | 2021-10-11 | 2021-10-17 | S42 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[66 empty] | 0 | 2021-10-18 | 2021-10-24 | S43 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[66 empty] | 0 | 2021-10-25 | 2021-10-31 | S44 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[66 empty] | 0 | 2021-11-01 | 2021-11-07 | S45 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[66 empty] | 0 | 2021-11-08 | 2021-11-14 | S46 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[66 empty] | 0 | 2021-11-15 | 2021-11-21 | S47 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[66 empty] | 0 | 2021-11-22 | 2021-11-28 | S48 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
EFFETTIVO | [65 empty] | 0 | 2021-11-29 | 2021-12-05 | S49 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[66 empty] | 0 | 2021-12-06 | 2021-12-12 | S50 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | FTE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2021-12-13 | 2021-12-19 | S51 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | ORE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 128 | 72 | 64 | 96 | 40 | 0 | 8 | 24 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-20 | 2021-12-26 | S52 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 2021-12-27 | 2022-01-02 | S53 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 0 | 2022-01-03 | 2022-01-09 | S2 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  | 43290 | 43392 | Durata | % | n sett INIZIO | n sett FINE | NOTE Realizzazione |  |  |  |  | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 0 | 2022-01-10 | 2022-01-16 | S3 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| CJ Unico Model Change 05 2022 | 0 |  | 1899-12-31 | 100% | 0 | 0 |  |  |  |  | Cicatelli Concetta | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | 0 | 2022-01-17 | 2022-01-23 | S4 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| Analisi |  |  | 0 | 100% | 0 | 0 |  |  |  |  | DESIGN | 0 | [52 empty] | 2.4643 | 2022-01-24 | 2022-01-30 | S5 | 3450 | 0 | 3450 | 0 | 0 | - | 0 | 0 | -3450 | -3450 | 0 | 3450
| Sviluppo |  |  | 0 | 100% | 0 | 0 |  |  |  |  | EXEC | 0 | [52 empty] | 2.4643 | 2022-01-31 | 2022-02-06 | S6 | 3450 | 0 | 6900 | 0 | 0 | - | 0 | 0 | -6900 | -10350 | 0 | 6900
| System test |  |  | 0 | 100% | 0 | 0 |  |  |  |  | MNG | 0 | [52 empty] | 2.4643 | 2022-02-07 | 2022-02-13 | S7 | 3450 | 0 | 10350 | 10074 | 0 | - | 0.97333 | 10074 | -276 | -20700 | 2014.8 | 10350
| UAT |  |  | 0 | 100% | 0 | 0 |  |  |  |  | UAT | 0 | [52 empty] | 2.4643 | 2022-02-14 | 2022-02-20 | S8 | 3450 | 0 | 13800 | 11258.5 | 0 | - | 0.81583 | 11258.5 | -2541.5 | -34500 | 2251.7 | 13800
| PRODUZIONE |  |  | 0 | 100% | 0 | 0 |  |  |  |  | DP | 80 | [20 empty] | 40 | 40 | [30 empty] | 2.1357 | 2022-02-21 | 2022-02-27 | S9 | 2990 | 0 | 16790 | 16295.5 | 0 | - | 0.97055 | 16295.5 | -494.5 | -51290 | 3259.1 | 16790
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [52 empty] | 0.82143 | 2022-02-28 | 2022-03-06 | S10 | 1150 | 0 | 17940 | 17135 | 0 | - | 0.95513 | 17135 | -805 | -69230 | 3427 | 17940
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [52 empty] | 0 | 2022-03-07 | 2022-03-13 | S11 | 0 | 0 | 17940 | 17135 | 0 | - | 0.95513 | 17135 | -805 | -87170 | 3427 | 17940
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | #REF! | 0 | [52 empty] | 0 | 2022-03-14 | 2022-03-20 | S12 | 0 | 0 | 17940 | 17135 | 0 | - | 0.95513 | 17135 | -805 | -105110 | 3427 | 17940
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | #REF! | 0 | [52 empty] | 3.45 | 2022-03-21 | 2022-03-27 | S13 | 4830 | 0 | 22770 | 19987 | 0 | - | 0.87778 | 19987 | -2783 | -127880 | 3997.4 | 22770
[13 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.45 | 2022-03-28 | 2022-04-03 | S14 | 4830 | 0 | 27600 | 25251.7 | 0 | - | 0.91492 | 25251.7 | -2348.3 | -155480 | 5050.34 | 27600
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3.6143 | 2022-04-04 | 2022-04-10 | S15 | 5060 | 0 | 32660 | 28198 | 0 | - | 0.86338 | 28198 | -4462 | -188140 | 5639.6 | 32660
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 3.6143 | 2022-04-11 | 2022-04-17 | S16 | 5060 | 0 | 37720 | 30486.5 | 0 | - | 0.80823 | 30486.5 | -7233.5 | -225860 | 6097.3 | 37720
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2.3 | 2022-04-18 | 2022-04-24 | S17 | 3220 | 0 | 40940 | 37885.6 | 0 | - | 0.92539 | 37885.6 | -3054.4 | -266800 | 7577.12 | 40940
[12 empty] | Barbano Angela | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | 2.3 | 2022-04-25 | 2022-05-01 | S18 | 3220 | 0 | 44160 | 39330 | 0 | - | 0.89062 | 39330 | -4830 | -310960 | 7866 | 44160
[12 empty] | DESIGN | 288 | [8 empty] | 40 | 40 | 40 | 32 | 32 | 32 | 40 |  | 8 | 24 | [34 empty] | 4.2714 | 2022-05-02 | 2022-05-08 | S19 | 5980 | 0 | 50140 | 40413.3 | 0 | - | 0.80601 | 40413.3 | -9726.7 | -361100 | 8082.66 | 50140
[7 empty] | si | invio Stima |  |  |  | EXEC | 0 | [52 empty] | 3.6143 | 2022-05-09 | 2022-05-15 | S20 | 5060 | 0 | 55200 | 41480.5 | 0 | - | 0.75146 | 41480.5 | -13719.5 | -416300 | 8296.1 | 55200
[7 empty] | si | accettazione STIMA |  |  |  | MNG | 0 | [52 empty] | 3.45 | 2022-05-16 | 2022-05-22 | S21 | 4830 | 0 | 60030 | 44769.5 | 0 | - | 0.74579 | 44769.5 | -15260.5 | -476330 | 8953.9 | 60030
[7 empty] | si | Pianificazione |  |  |  | UAT | 0 | [52 empty] | 3.45 | 2022-05-23 | 2022-05-29 | S22 | 4830 | 0 | 64860 | 44769.5 | 0 | - | 0.69025 | 44769.5 | -20090.5 | -541190 | 8953.9 | 64860
[7 empty] | si | GO a Partire |  |  |  | DP | 0 | [52 empty] | 0 | 2022-05-30 | 2022-06-05 | S23 | 0 | 0 | 64860 | 47465.1 | 0 | - | 0.73181 | 47465.1 | -17394.9 | -606050 | 9493.02 | 64860
[7 empty] | si | Creazione offerta |  |  |  | 0 | 0 | [52 empty] | 0 | 2022-06-06 | 2022-06-12 | S24 | 0 | 0 | 64860 | 50179.1 | 0 | - | 0.77365 | 50179.1 | -14680.9 | -670910 | 10035.82 | 64860
[7 empty] | si | invio proposta Formale |  |  |  | 0 | 0 | [52 empty] | 0 | 2022-06-13 | 2022-06-19 | S25 | 0 | 0 | 64860 | 59236.5 | 0 | - | 0.9133 | 59236.5 | -5623.5 | -735770 | 11847.3 | 64860
[7 empty] | no | Creazione work order |  |  |  | #REF! | 0 | [52 empty] | 0 | 2022-06-20 | 2022-06-26 | S26 | 0 | 0 | 64860 | 59236.5 | 0 | - | 0.9133 | 59236.5 | -5623.5 | -800630 | 11847.3 | 64860
[12 empty] | #REF! | 0 | [52 empty] | 0 | 2022-06-27 | 2022-07-03 | S27 | 0 | 0 | 64860 | 59236.5 | 0 | - | 0.9133 | 59236.5 | -5623.5 | -865490 | 11847.3 | 64860
[13 empty] | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 32 | 32 | 32 | 40 | 0 | 8 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-07-04 | 2022-07-10 | S28 | 0 | 0 | 64860 | 59236.5 | 0 | - | 0.9133 | 59236.5 | -5623.5 | -930350 | 11847.3 | 64860
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2022-07-11 | 2022-07-17 | S29 | 0 | 0 | 64860 | 64860 | 0 | - | 1 | 64860 | 0 | -995210 | 12972 | 64860
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 0 | 2022-07-18 | 2022-07-24 | S30 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 0 | 2022-07-25 | 2022-07-31 | S31 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Stefan Andrada | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 |  | 2022-08-01 | 2022-08-07 | S32 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | DESIGN | 40 | [7 empty] | 40 | [45 empty] | 2022-08-08 | 2022-08-14 | S33 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | EXEC | 0 | [53 empty] | 2022-08-15 | 2022-08-21 | S34 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | MNG | 0 | [53 empty] | 2022-08-22 | 2022-08-28 | S35 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | UAT | 0 | [53 empty] | 2022-08-29 | 2022-09-04 | S36 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | DP | 152 | [10 empty] | 48 | 40 | 32 | 32 | [39 empty] | 2022-09-05 | 2022-09-11 | S37 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0 | [53 empty] | 2022-09-12 | 2022-09-18 | S38 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0 | [53 empty] | 2022-09-19 | 2022-09-25 | S39 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | #REF! | 0 | [53 empty] | 2022-09-26 | 2022-10-02 | S40 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | #REF! | 0
[13 empty] | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 48 | 40 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | Italiano Rossella | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 192 | [7 empty] | 40 | 40 | 40 | 40 |  |  | 32
[12 empty] | MNG | 0
[12 empty] | UAT | 0
[12 empty] | DP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | Arcari Gabriella | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 160 | [8 empty] | 40 | 40 | 40 | 40
[12 empty] | EXEC | 320 | [12 empty] | 32 | 32 | 40 | 40 | 40 | 40 | 32 |  | 40 | 24
[12 empty] | MNG | 0
[12 empty] | UAT | 0
[12 empty] | DP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 32 | 32 | 40 | 40 | 40 | 40 | 32 | 0 | 40 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | Cutrullà Domenico | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 160 | [10 empty] | 48 | 40 | 40 | 32
[12 empty] | MNG | 0
[12 empty] | UAT | 112 | [17 empty] | 40 | 32 |  | 40
[12 empty] | DP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 40 | 40 | 32 | 0 | 0 | 0 | 40 | 32 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | Galeota Raffaela | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 0
[12 empty] | MNG | 0
[12 empty] | UAT | 0
[12 empty] | DP | 136 | [16 empty] | 40 | 40 | 24 | 32
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 24 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | Mazzoni Alessandro | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 336 | [10 empty] | 40 | 40 | 32 | 32 | 40 | 40 | 40 | 40 | 32
[12 empty] | MNG | 0
[12 empty] | UAT | 0
[12 empty] | DP | 40 | [22 empty] | 40
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 32 | 32 | 40 | 40 | 40 | 40 | 32 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | Pastore Maria | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 40 | [11 empty] | 40
[12 empty] | EXEC | 0
[12 empty] | MNG | 0
[12 empty] | UAT | 0
[12 empty] | DP | 192 | [14 empty] | 40 | 40 | 40 | 40 | 32
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | Zaffarana Giovanni | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 40 | [11 empty] | 40
[12 empty] | EXEC | 144 | [12 empty] | 32 | 32 | 40 | 40
[12 empty] | MNG | 0
[12 empty] | UAT | 0
[12 empty] | DP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 32 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[7 empty] | COMMESSA | CJBrevetermine24042020 |  |  |  | Cetronio Giuseppe Rosario | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[7 empty] | STATO | in corso |  |  |  | DESIGN | 0
[7 empty] | IMPORTO | 22854 |  |  |  | EXEC | 0
[7 empty] | GIORNI STIMATI | 78 |  |  |  | MNG | 0
[7 empty] | SETTIMANA | #REF! |  |  |  | UAT | 0
[7 empty] | RESIDUO APRILE | 22854 |  |  |  | DP | 232 | [14 empty] | 40 | 40 | 40 | 40 | 32 | 40
[7 empty] | Leuci Antonella | 1 |  |  |  | 0 | 0
[7 empty] | residuo | #REF! |  |  |  | 0 | 0
[7 empty] | Malacrida Alessandro | 6 |  |  |  | #REF! | 0
[7 empty] | residuo | #REF! |  |  |  | #REF! | 0
[7 empty] | RESIDUO MAGGIO | #REF! |  |  |  |  | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Giorni Residui | #REF! |  |  |  |  | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | Boggia Ilaria | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 24 | [17 empty] | 24
[12 empty] | MNG | 0
[12 empty] | UAT | 0
[12 empty] | DP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | Romano Raffaele | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 24 | [21 empty] | 24
[12 empty] | MNG | 0
[12 empty] | UAT | 0
[12 empty] | DP | 40 | [22 empty] | 40
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | Cetronio Giuseppe Rosario | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 0
[12 empty] | MNG | 0
[12 empty] | UAT | 0
[12 empty] | DP | 136 | [18 empty] | 16 | 40 | 40 | 40
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | Risorsa | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 0
[12 empty] | MNG | 0
[12 empty] | UAT | 0
[12 empty] | DP | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | ACWP | #REF! | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | EXEC | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | MNG | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | UAT | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | DP | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | % completamento | 100% | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 100% | 0% | 0% | 60% | 65% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | EXEC | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 31% | 40% | 45% | 46% | 50% | 53% | 55% | 55% | 55% | 63% | 63% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | MNG | 100% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 10% | 10% | 20% | 35% | 65% | 65% | 65% | 70% | 70% | 70% | 80% | 80% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | UAT | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 46% | 50% | 53% | 55% | 55% | 55% | 55% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | DP | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 65% | 65% | 65% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | bar: 100% to S3
0 | bar: 100% to S3
#REF! | bar: 100% to S3
#REF! | bar: 100% to S3
[14 empty] | 0% | 0% | 16.2% | 18.15% | 26.25% | 27.6% | 27.6% | 27.6% | 31.7% | 39.05% | 43.4% | 46.95% | 58.26% | 60.3% | 61.83% | 63.45% | 69.95% | 69.95% | 73.95% | 78.15% | 91.15% | 91.15% | 91.15% | 91.15% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[13 empty] | DAL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
[13 empty] | AL | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22
[12 empty] | EV | 64860 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3
[12 empty] | DESIGN | 16790 | 0 | 0 | 10074 | 10913.5 | 15950.5 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790 | 16790
[12 empty] | EXEC | 25070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2507 | 7771.7 | 10028 | 11281.5 | 11532.2 | 12535 | 13287.1 | 13788.5 | 13788.5 | 13788.5 | 15794.1 | 15794.1 | 23816.5 | 23816.5 | 23816.5 | 23816.5 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070 | 25070
[12 empty] | MNG | 6900 | 0 | 0 | 0 | 345 | 345 | 345 | 345 | 345 | 690 | 690 | 1380 | 2415 | 4485 | 4485 | 4485 | 4830 | 4830 | 4830 | 5520 | 5520 | 6555 | 6555 | 6555 | 6555 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900 | 6900
[12 empty] | UAT | 11040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5078.4 | 5520 | 5851.2 | 6072 | 6072 | 6072 | 6072 | 8280 | 8280 | 8280 | 8280 | 8280 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040 | 11040
[12 empty] | DP | 5060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3289 | 3289 | 3289 | 3795 | 3795 | 3795 | 3795 | 3795 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 10074 | 11258.5 | 16295.5 | 17135 | 17135 | 17135 | 19987 | 25251.7 | 28198 | 30486.5 | 37885.6 | 39330 | 40413.3 | 41480.5 | 44769.5 | 44769.5 | 47465.1 | 50179.1 | 59236.5 | 59236.5 | 59236.5 | 59236.5 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860 | 64860
[12 empty] | AVANZAMENTO PROGETTO | 100%: gg tot; S5: %avanz.; S6: risorsa; S7: gg effettivi; S8: coperto
Gestione Progetto
Recepimento requisiti funzionali e coordinamento
Analisi
[12 empty] | Design | 100%: 40; S5: 70%
[12 empty] | Esecuzione | 100%: gg tot; S5: %avanz.; S6: risorsa; S7: gg effettivi; S8: coperto
[12 empty] | Esecuzione, Retest, Test Management, NRT | 100%: 148; S7: 3
Restest e Rilascio
[12 empty] | Supporto UAT | 100%: 10
[12 empty] | AVANZAMENTO PROGETTO | 100%: 14.14%
AVANZAMENTO ANALISI | bar: 100% to S8
AVANZAMENTO ESECUZIONE | bar: 100% to S8
[12 empty] | GG RESIDUI | 100%: 170
Formulas:
Malacrida Alessandro = MIN([Malacrida Alessandro, row below]:C30)
Note on CG55: Chiara DE RIGGI: rev tab
Note on CH55: Chiara DE RIGGI: acwp
Note on AO118: Chiara DE RIGGI: 10h effettive
Note on AS299: Chiara DE RIGGI: lotto3

## Delibera Accentrata - rel.07_22 (hidden)
| Nome Progetto | Delibera Accentrata - rel.07_22
| Responsabile | Malacrida Alessandro | [81 empty] | Note | BM | Referente | Workorder | Status | Text WO | Data Inizio | Data Fine | Fatturazione | OFFERTA | Residuo da Maturato | M% | Residuo da RevTab | RT% | Text Ressource | Time Code |  | PriceList | Hours 202003 | Hours 202004 | Hours 202005 | Hours 202006 | Hours 202007 | Hours 202008 | Hours 202009 | Hours 202010 | Hours 202011 | Hours 202012 | Hours 202101 | Hours 202102 | Hours 202103 | Hours 202104 | Hours 202105 | Hours 202106 | Hours 202107 | Hours 202108 | Hours 202109 | Maturato al 29/02 | Maturato 202003 | Maturato 202004 | Maturato 202005 | Maturato 202006 | Maturato 202007 | Maturato 202008 | Maturato 202009 | Maturato 202010 | Maturato 202011 | Maturato 202012 | Maturato 202101 | Maturato 202102 | Maturato 202103 | Maturato 202104 | Maturato 202105 | Maturato 202106 | Maturato 202107 | Maturato 202108 | Maturato 202109 | Totale Maturato | RevTab al 29/02 | RevTab 202003 | RevTab 202004 | RevTab 202005 | RevTab 202006 | RevTab 202007 | RevTab 202008 | RevTab 202009 | RevTab 202010 | RevTab 202011 | RevTab 202012 | RevTab 202101 | RevTab 202102 | RevTab 202103 | RevTab 202104 | RevTab 202105 | RevTab 202106 | RevTab 202107 | RevTab 202108 | RevTab 202109 | Totale RevTab
| Richiedente | Massimiliano Giuliani Bolognini | [6 empty] | Stima | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Addante, Davide | NSW |  | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Ambito | - | [6 empty] | Pianificazione | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Mercuri, Emanuela | NSW |  | 36 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Risorse | Malacrida Alessandro | Arcari Gabriella | Cutrullà Domenico | Montalbano Emanuele | Pastore Maria | Brescia Gennaro |  | Go A partire | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Iovieno, Salvatore | NSW | P1716976.10Iovieno, SalvatoreNSW | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Release | [7 empty] | Creazione Offerta | SI | [74 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Brescia, Gennaro | NSW | P1716976.10Brescia, GennaroNSW | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Data Avvio lavori | [83 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Capodici, Paolo | NSW |  | 25 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Bucket | Design |  |  |  | Descrizione | ISP20220502122_DeliberaAccentrata_rel_07 | [77 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Djimeli Tchinda, Yolande Alida | NSW |  | 12.5 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| %completamento | 100% | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Malacrida, Alessandro | NSW |  | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Prossima MIlestone | [83 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Malorgio, Gloria | NSW | P1716976.10Malorgio, GloriaNSW | 30 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Riferimenti Stima | ISP20220310_DeliberaAccentrata_rel_07_22.xlsx EXTRA - Data Preparation UAT Maggio ISP20220406_RLO_EvolutiveMyKey.xlsx | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Cutrullà, Domenico | NSW |  | 34.62 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Stima | 122 | 976 | 28060 | 230 | #REF! | [5 empty] | 44704 | 44753 | [71 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Montalbano, Emanuele | NSW | P1716976.10Montalbano, EmanueleNSW | 35 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Stato | Coerente | [82 empty] | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Montalbano, Emanuele | STR | P1716976.10Montalbano, EmanueleSTR | 35 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
BASELINE | [65 empty] | FTE |  |  | Settimana | BASELINE | EFFETTIVO | BCWS | EV | ACWP | CPI | SPI | CV | SV | COMMESSA | REV TAB | BCWS-ACWP |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Pastore, Maria | NSW |  | 25 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[66 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Pastore, Maria | STR |  | 25 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[9 empty] | Andamento progetto |  |  | FTE | 122 | 20 | 14 | 19 | 32 | 29 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-01-03 | 2022-01-09 | S2 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Calò, Gaia | NSW |  | 12.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[12 empty] | ORE | 976 | 160 | 112 | 152 | 256 | 232 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-01-10 | 2022-01-16 | S3 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Rubes, Federico | NSW |  | 27.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[66 empty] | 0 | 2022-01-17 | 2022-01-23 | S4 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Tuzio, Giuseppe | NSW | P1716976.10Tuzio, GiuseppeNSW | 36 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 0 | 2022-01-24 | 2022-01-30 | S5 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Leonardi, Angelo | NSW |  | 27.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
|  | Data Inizio | Data Fine | Durata | PESO | n sett INIZIO | n sett FINE | NOTE Pianificazione | FTE Allocati |  |  |  | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11 | 0 | 2022-01-31 | 2022-02-06 | S6 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0 |  |  |  | DOR | Crediti - Pensabene | P1716976.10 | Nuovo |  | 2021-06-16 | 2021-07-31 |  | 79810 | 79810 | 0% | 35914.5 | 55% | Tento, Mattia | NSW |  | 12.5 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 43895.5 | 43895.5
| Delibera Accentrata - rel.07_22 | 2022-05-23 | 2022-07-08 | 47 | 100% | 22 | 28 |  | #REF! | 100% | allocazione budget "ideale" | Baseline | € | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | 0 | 2022-02-07 | 2022-02-13 | S7 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| Design + review | 2022-06-06 |  | 0 | 18% | 24 | 0 | 9 | 1 | 13% | 3647.8 | Design + review | 2300 | 2300 | [51 empty] | 0 | 2022-02-14 | 2022-02-20 | S8 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| Esecuzione (system + retest 30%) | 2022-06-06 | 2022-07-08 | 33 | 20% | 24 | 28 | 13 | #REF! | 45% | 12627 | Esecuzione (system + retest 30%) | 11960 | 1150 | 1150 | 1610 | 3450 | 3450 | 1150 | [46 empty] | 0 | 2022-02-21 | 2022-02-27 | S9 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| NRT | 2022-06-06 | 2022-07-08 | 33 | 35% | 24 | 28 | 7 | #REF! | 5% | 1403 | NRT | 2300 |  |  |  | 1150 | 1150 | [47 empty] | 0 | 2022-02-28 | 2022-03-06 | S10 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| Management | 2022-05-23 | 2022-07-08 | 47 | 7% | 22 | 28 | 7 | #REF! | 15% | 4209 | Management | 5060 | 1150 | 1150 | 1150 | 1150 | 460 | [47 empty] | 0 | 2022-03-07 | 2022-03-13 | S11 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| Data preparation | 2022-05-23 | 2022-07-08 | 47 | 20% | 22 | 28 | 20 | #REF! | 16% | 4489.6 | Data preparation | 3680 |  | 920 | 920 | 920 | 920 | [47 empty] | 0 | 2022-03-14 | 2022-03-20 | S12 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| Esecuzione (system + retest 30%) Evolutive MyKey |  |  | 0 | 0% | 0 | 0 | 17 | #REF! | 6% | 1683.6 | Esecuzione (system + retest 30%) Evolutive MyKey | 2760 |  |  | 690 | 690 | 690 | 690 | [46 empty] | 0 | 2022-03-21 | 2022-03-27 | S13 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! | 0% | 0 | 0 | 0 | [52 empty] | 0 | 2022-03-28 | 2022-04-03 | S14 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! | 0% | 0 | 0 | 0 | [52 empty] | 0 | 2022-04-04 | 2022-04-10 | S15 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! | 0% | 0 | 0 | 0 | [52 empty] | 0 | 2022-04-11 | 2022-04-17 | S16 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[13 empty] | 28060 | 4600 | 3220 | 4370 | 7360 | 6670 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-04-18 | 2022-04-24 | S17 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | [8 empty] | 0 | [52 empty] | 0 | 2022-04-25 | 2022-05-01 | S18 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
| Offerta | ISP20220502122_DeliberaAccentrata_rel_07 |  | 0 | [61 empty] | 0 | 2022-05-02 | 2022-05-08 | S19 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | [5 empty] | % Compl | % Budget | Costo | Tempo | [52 empty] | 0 | 2022-05-09 | 2022-05-15 | S20 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | [5 empty] | 100% | #REF! | #REF! | #REF! | [52 empty] | 0 | 2022-05-16 | 2022-05-22 | S21 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | [52 empty] | 0 | 2022-05-23 | 2022-05-29 | S22 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[66 empty] | 0 | 2022-05-30 | 2022-06-05 | S23 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | Malacrida Alessandro | #REF! | [52 empty] | 0 | 2022-06-06 | 2022-06-12 | S24 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 | 0 | 0 | 0
[12 empty] | Montalbano Emanuele | #REF! | [52 empty] | 3.2857 | 2022-06-13 | 2022-06-19 | S25 | 4600 | 0 | 4600 | 5888 | 0 | - | 1.28 | 5888 | 1288 | -4600 | 1177.6 | 4600
|  | 15 | 14.02% | [8 empty] | Stefan Andrada | #REF! | [52 empty] | 2.3 | 2022-06-20 | 2022-06-26 | S26 | 3220 | 0 | 7820 | 6762 | 0 | - | 0.86471 | 6762 | -1058 | -12420 | 1352.4 | 7820
|  | 55 | 51.4% | [8 empty] | Capodici Paolo | #REF! | [52 empty] | 3.1214 | 2022-06-27 | 2022-07-03 | S27 | 4370 | 0 | 12190 | 10143 | 0 | - | 0.83208 | 10143 | -2047 | -24610 | 2028.6 | 12190
|  | 23 | 21.5% | [8 empty] | Carrieri Alessandro | #REF! | [52 empty] | 5.2571 | 2022-07-04 | 2022-07-10 | S28 | 7360 | 0 | 19550 | 23956.8 | 0 | - | 1.2254 | 23956.8 | 4406.8 | -44160 | 4791.36 | 19550
|  | 14 | 13.08% | [8 empty] | Cutrullà Domenico | #REF! | [52 empty] | 4.7643 | 2022-07-11 | 2022-07-17 | S29 | 6670 | 0 | 26220 | 23956.8 | 0 | - | 0.91368 | 23956.8 | -2263.2 | -70380 | 4791.36 | 26220
[12 empty] | Ratti Alessia | #REF! | [52 empty] | 1.3143 | 2022-07-18 | 2022-07-24 | S30 | 1840 | 0 | 28060 | 23956.8 | 0 | - | 0.85377 | 23956.8 | -4103.2 | -98440 | 4791.36 | 28060
|  | 107 | [9 empty] | gg/u | #REF! | [52 empty] | 0 | 2022-07-25 | 2022-07-31 | S31 | 0 | 0 | 28060 | 28060 | 0 | - | 1 | 28060 | 0 | -126500 | 5612 | 28060
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2022-08-01 | 2022-08-07 | S32 | 0 | 0 | 28060 | 28060 | 0 | - | 1 | 28060 | 0 | -154560 | 5612 | 28060
[66 empty] | 0 | 2022-08-08 | 2022-08-14 | S33 | 0 | 0 | 28060 | 28060 | 0 | - | 1 | 28060 | 0 | -182620 | 5612 | 28060
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2022-08-15 | 2022-08-21 | S34 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -210680 |  | 28060
[12 empty] | FTE | #REF! | [52 empty] | 0 | 2022-08-22 | 2022-08-28 | S35 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -238740 |  | 28060
| Supporto UAT | 3 | [9 empty] | BCWS | #REF! | [52 empty] | 0 | 2022-08-29 | 2022-09-04 | S36 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -266800 |  | 28060
| Supporto Week end | 3.625 | [9 empty] | EV | #REF! | [52 empty] | 0 | 2022-09-05 | 2022-09-11 | S37 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -294860 |  | 28060
[12 empty] | ACWP | #REF! | [52 empty] | 0 | 2022-09-12 | 2022-09-18 | S38 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -322920 |  | 28060
[12 empty] | CPI | #REF! | [52 empty] | 0 | 2022-09-19 | 2022-09-25 | S39 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -350980 |  | 28060
[12 empty] | SPI | #REF! | [52 empty] | 0 | 2022-09-26 | 2022-10-02 | S40 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -379040 |  | 28060
[12 empty] | CV | #REF! | [52 empty] | 0 | 2022-10-03 | 2022-10-09 | S41 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -407100 |  | 28060 | 0 | 0
[12 empty] | SV | #REF! | [52 empty] | 0 | 2022-10-10 | 2022-10-16 | S42 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -435160 |  | 28060
[12 empty] | REV_TAB | #REF! | [52 empty] | 0 | 2022-10-17 | 2022-10-23 | S43 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -463220 |  | 28060
[66 empty] | 0 | 2022-10-24 | 2022-10-30 | S44 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -491280 |  | 28060
[66 empty] | 0 | 2022-10-31 | 2022-11-06 | S45 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -519340 |  | 28060
[66 empty] | 0 | 2022-11-07 | 2022-11-13 | S46 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -547400 |  | 28060
[66 empty] | 0 | 2022-11-14 | 2022-11-20 | S47 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -575460 |  | 28060
[66 empty] | 0 | 2022-11-21 | 2022-11-27 | S48 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -603520 |  | 28060
[66 empty] | 0 | 2022-11-28 | 2022-12-04 | S49 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -631580 |  | 28060
EFFETTIVO | [65 empty] | 0 | 2022-12-05 | 2022-12-11 | S50 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -659640 |  | 28060
[66 empty] | 0 | 2022-12-12 | 2022-12-18 | S51 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -687700 |  | 28060
[12 empty] | FTE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2022-12-19 | 2022-12-25 | S52 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -715760 |  | 28060
[12 empty] | ORE |  | 0 | 104 | 72 | 40 | 40 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-12-26 | 2023-01-01 | S53 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -743820 |  | 28060
[13 empty] | Tariffa €/h | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 0 | 2023-01-02 | 2023-01-08 | S1 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -771880 |  | 28060
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 0 | 2023-01-09 | 2023-01-15 | S2 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -799940 |  | 28060
|  | 43290 | 43392 | Durata | % | n sett INIZIO | n sett FINE | NOTE Realizzazione |  |  |  |  | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11 | 0 | 2023-01-16 | 2023-01-22 | S3 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -828000 |  | 28060
| Delibera Accentrata - rel.07_22 | 0 |  | 1899-12-31 | 100% | 0 | 0 |  |  |  |  | Malacrida Alessandro | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | 0 | 2023-01-23 | 2023-01-29 | S4 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -856060 |  | 28060
| Analisi |  |  | 0 | 100% | 0 | 0 |  |  |  |  | Design + review | 0 | [52 empty] | 0 | 2023-01-30 | 2023-02-05 | S5 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -884120 |  | 28060
| Sviluppo |  |  | 0 | 100% | 0 | 0 |  |  |  |  | Esecuzione (system + retest 30%) | 0 | [52 empty] | 0 | 2023-02-06 | 2023-02-12 | S6 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -912180 |  | 28060
| System test |  |  | 0 | 100% | 0 | 0 |  |  |  |  | NRT | 0 | [52 empty] | 0 | 2023-02-13 | 2023-02-19 | S7 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -940240 |  | 28060
| UAT |  |  | 0 | 100% | 0 | 0 |  |  |  |  | Management | 40 | [5 empty] | 40 | [46 empty] | 0 | 2023-02-20 | 2023-02-26 | S8 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -968300 |  | 28060
| PRODUZIONE |  |  | 0 | 100% | 0 | 0 |  |  |  |  | Data preparation | 0 | [52 empty] | 0 | 2023-02-27 | 2023-03-05 | S9 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -996360 |  | 28060
| #REF! |  |  | 0 | 100% | 0 | 0 |  |  |  |  | Esecuzione (system + retest 30%) Evolutive MyKey | 0 | [52 empty] | 0 | 2023-03-06 | 2023-03-12 | S10 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -1024420 |  | 28060
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [52 empty] | 0 | 2023-03-13 | 2023-03-19 | S11 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -1052480 |  | 28060
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | #REF! | 0 | [52 empty] | 0 | 2023-03-20 | 2023-03-26 | S12 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -1080540 |  | 28060
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | #REF! | 0 | [52 empty] | 0 | 2023-03-27 | 2023-04-02 | S13 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -1108600 |  | 28060
[13 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-04-03 | 2023-04-09 | S14 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -1136660 |  | 28060
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2023-04-10 | 2023-04-16 | S15 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 | -1164720 |  | 28060
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 0 | 2023-04-17 | 2023-04-23 | S16 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 |  |  | 28060
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11 | 0 | 2023-04-24 | 2023-04-30 | S17 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 |  |  | 28060
[12 empty] | Montalbano Emanuele | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | 0 | 2023-05-01 | 2023-05-07 | S18 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 |  |  | 28060
[12 empty] | Design + review | 72 |  | 32 | 40 | [49 empty] | 0 | 2023-05-08 | 2023-05-14 | S19 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 |  |  | 28060
[7 empty] | si | invio Stima |  |  |  | Esecuzione (system + retest 30%) | 0 | [52 empty] | 0 | 2023-05-15 | 2023-05-21 | S20 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 |  |  | 28060
[7 empty] | si | accettazione STIMA |  |  |  | NRT | 0 | [52 empty] | 0 | 2023-05-22 | 2023-05-28 | S21 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 |  |  | 28060
[7 empty] | si | Pianificazione |  |  |  | Management | 120 |  |  |  | 40 | 40 | 40 | [46 empty] | 0 | 2023-05-29 | 2023-06-04 | S22 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 |  |  | 28060
[7 empty] | si | GO a Partire |  |  |  | Data preparation | 0 | [52 empty] | 0 | 2023-06-05 | 2023-06-11 | S23 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 |  |  | 28060
[7 empty] | si | Creazione offerta |  |  |  | Esecuzione (system + retest 30%) Evolutive MyKey | 0 | [52 empty] | 0 | 2023-06-12 | 2023-06-18 | S24 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 |  |  | 28060
[7 empty] | si | invio proposta Formale |  |  |  | 0 | 0 | [52 empty] | 0 | 2023-06-19 | 2023-06-25 | S25 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 |  |  | 28060
[7 empty] | no | Creazione work order |  |  |  | #REF! | 0 | [52 empty] | 0 | 2023-06-26 | 2023-07-02 | S26 | 0 | 0 | 28060 |  |  | - | 0 | 0 | -28060 |  |  | 0
[12 empty] | #REF! | 0 | [52 empty] | 0 | 2023-07-03 | 2023-07-09 | S27 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | 192 | 0 | 32 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-07-10 | 2023-07-16 | S28 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2023-07-17 | 2023-07-23 | S29 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 0 | 2023-07-24 | 2023-07-30 | S30 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11 | 0 | 2023-07-31 | 2023-08-06 | S31 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Stefan Andrada | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 |  | 2023-08-07 | 2023-08-13 | S32 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Design + review | 0 | [53 empty] | 2023-08-14 | 2023-08-20 | S33 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | Esecuzione (system + retest 30%) | 0 | [53 empty] | 2023-08-21 | 2023-08-27 | S34 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | NRT | 0 | [53 empty] | 2023-08-28 | 2023-09-03 | S35 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | Management | 0 | [53 empty] | 2023-09-04 | 2023-09-10 | S36 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | Data preparation | 112 |  | 40 | 32 |  |  | 40 | [47 empty] | 2023-09-11 | 2023-09-17 | S37 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0 | [53 empty] | 2023-09-18 | 2023-09-24 | S38 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0 | [53 empty] | 2023-09-25 | 2023-10-01 | S39 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | #REF! | 0 | [53 empty] | 2023-10-02 | 2023-10-08 | S40 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | #REF! | 0
[13 empty] | 112 | 0 | 40 | 32 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | Capodici Paolo | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 32 |  | 32
[12 empty] | Esecuzione (system + retest 30%) | 0
[12 empty] | NRT | 0
[12 empty] | Management | 0
[12 empty] | Data preparation | 0
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 32 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | Carrieri Alessandro | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 0
[12 empty] | Esecuzione (system + retest 30%) | 64 |  | 32 | 32
[12 empty] | NRT | 0
[12 empty] | Management | 0
[12 empty] | Data preparation | 0
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 64 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | Cutrullà Domenico | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 0
[12 empty] | Esecuzione (system + retest 30%) | 0
[12 empty] | NRT | 0
[12 empty] | Management | 0
[12 empty] | Data preparation | 80 |  | 40 | 40
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 80 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | Galeota Raffaela | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 0
[12 empty] | Esecuzione (system + retest 30%) | 0
[12 empty] | NRT | 0
[12 empty] | Management | 0
[12 empty] | Data preparation | 72 |  | 32 | 40
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 72 | 0 | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | Autiero Stefano | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 72 |  | 32 | 40
[12 empty] | Esecuzione (system + retest 30%) | 80 |  |  |  | 40 | 40
[12 empty] | NRT | 0
[12 empty] | Management | 0
[12 empty] | Data preparation | 0
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 152 | 0 | 32 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | Tosti Nicola | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 0
[12 empty] | Esecuzione (system + retest 30%) | 0
[12 empty] | NRT | 0
[12 empty] | Management | 0
[12 empty] | Data preparation | 16 |  | 8 | 8
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 16 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | Cicatelli Concetta | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 0
[12 empty] | Esecuzione (system + retest 30%) | 40 |  | 40
[12 empty] | NRT | 0
[12 empty] | Management | 0
[12 empty] | Data preparation | 0
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[7 empty] | COMMESSA | CJBrevetermine24042020 |  |  |  | Ratti Alessia | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[7 empty] | STATO | in corso |  |  |  | Design + review | 0
[7 empty] | IMPORTO | 22854 |  |  |  | Esecuzione (system + retest 30%) | 32 |  | 32
[7 empty] | GIORNI STIMATI | 78 |  |  |  | NRT | 0
[7 empty] | SETTIMANA | #REF! |  |  |  | Management | 0
[7 empty] | RESIDUO APRILE | 22854 |  |  |  | Data preparation | 0
[7 empty] | Leuci Antonella | 1 |  |  |  | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[7 empty] | residuo | #REF! |  |  |  | 0 | 0
[7 empty] | Malacrida Alessandro | 6 |  |  |  | #REF! | 0
[7 empty] | residuo | #REF! |  |  |  | #REF! | 0
[7 empty] | RESIDUO MAGGIO | #REF! |  |  |  |  | 32 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Giorni Residui | #REF! |  |  |  |  | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | Dell'Anno Felicia | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 0
[12 empty] | Esecuzione (system + retest 30%) | 0
[12 empty] | NRT | 0
[12 empty] | Management | 0
[12 empty] | Data preparation | 32 |  |  | 32
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 32 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | Pastore Maria | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 0
[12 empty] | Esecuzione (system + retest 30%) | 0
[12 empty] | NRT | 0
[12 empty] | Management | 0
[12 empty] | Data preparation | 40 | [6 empty] | 40
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | Risorsa | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 0
[12 empty] | Esecuzione (system + retest 30%) | 0
[12 empty] | NRT | 0
[12 empty] | Management | 0
[12 empty] | Data preparation | 0
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | Risorsa | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 0
[12 empty] | Esecuzione (system + retest 30%) | 0
[12 empty] | NRT | 0
[12 empty] | Management | 0
[12 empty] | Data preparation | 0
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 0
[12 empty] | 0 | 0
[12 empty] | #REF! | 0
[12 empty] | #REF! | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | ACWP | #REF! | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | Esecuzione (system + retest 30%) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | NRT | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | Management | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | Data preparation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | % completamento | 100% | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | Esecuzione (system + retest 30%) | 100% | 30% | 30% | 45% | 98% | 98% | 98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | NRT | 100% | 0% | 0% | 50% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | Management | 100% | 0% | 10% | 15% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | Data preparation | 100% | 0% | 10% | 15% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | bar: 100% to S23
#REF! | bar: 100% to S23
#REF! | bar: 100% to S23
[14 empty] | 24% | 26.7% | 48.55% | 93.4% | 93.4% | 93.4% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[13 empty] | DAL | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[13 empty] | AL | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11
[12 empty] | EV | 28060 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23
[12 empty] | Design + review | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300
[12 empty] | Esecuzione (system + retest 30%) | 11960 | 3588 | 3588 | 5382 | 11720.8 | 11720.8 | 11720.8 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960 | 11960
[12 empty] | NRT | 2300 | 0 | 0 | 1150 | 2070 | 2070 | 2070 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300
[12 empty] | Management | 5060 | 0 | 506 | 759 | 4554 | 4554 | 4554 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060 | 5060
[12 empty] | Data preparation | 3680 | 0 | 368 | 552 | 3312 | 3312 | 3312 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680 | 3680
[12 empty] | Esecuzione (system + retest 30%) Evolutive MyKey | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760 | 2760
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5888 | 6762 | 10143 | 23956.8 | 23956.8 | 23956.8 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060 | 28060
[12 empty] | AVANZAMENTO PROGETTO | 100%: gg tot; S25: %avanz.; S26: risorsa; S27: gg effettivi; S28: coperto
Gestione Progetto
Recepimento requisiti funzionali e coordinamento
Analisi
[12 empty] | Design | 100%: 40; S25: 70%
[12 empty] | Esecuzione | 100%: gg tot; S25: %avanz.; S26: risorsa; S27: gg effettivi; S28: coperto
[12 empty] | Esecuzione, Retest, Test Management, NRT | 100%: 148; S27: 3
Restest e Rilascio
[12 empty] | Supporto UAT | 100%: 10
[12 empty] | AVANZAMENTO PROGETTO | 100%: 14.14%
AVANZAMENTO ANALISI | bar: 100% to S28
AVANZAMENTO ESECUZIONE | bar: 100% to S28
[12 empty] | GG RESIDUI | 100%: 170
Formulas:
Malacrida Alessandro = MIN([Malacrida Alessandro, row below]:C30)
Note on CG55: Chiara DE RIGGI: rev tab
Note on CH55: Chiara DE RIGGI: acwp
Note on AO118: Chiara DE RIGGI: 10h effettive
Note on AS299: Chiara DE RIGGI: lotto3

## Dialogo Industriale 03 2022 (hidden)
| Nome Progetto | Dialogo Industriale 03 2022
| Responsabile | Malacrida Alessandro | [79 empty] | Note | BM | Referente | Workorder | Status | Text WO | Data Inizio | Data Fine | Fatturazione | OFFERTA | Residuo da Maturato | M% | Residuo da RevTab | RT% | Text Ressource | Time Code |  | PriceList | Hours 202003 | Hours 202004 | Hours 202005 | Hours 202006 | Hours 202007 | Hours 202008 | Hours 202009 | Hours 202010 | Hours 202011 | Hours 202012 | Hours 202101 | Hours 202102 | Hours 202103 | Hours 202104 | Hours 202105 | Hours 202106 | Hours 202107 | Maturato al 29/02 | Maturato 202003 | Maturato 202004 | Maturato 202005 | Maturato 202006 | Maturato 202007 | Maturato 202008 | Maturato 202009 | Maturato 202010 | Maturato 202011 | Maturato 202012 | Maturato 202101 | Maturato 202102 | Maturato 202103 | Maturato 202104 | Maturato 202105 | Maturato 202106 | Maturato 202107 | Totale Maturato | RevTab al 29/02 | RevTab 202003 | RevTab 202004 | RevTab 202005 | RevTab 202006 | RevTab 202007 | RevTab 202008 | RevTab 202009 | RevTab 202010 | RevTab 202011 | RevTab 202012 | RevTab 202101 | RevTab 202102 | RevTab 202103 | RevTab 202104 | RevTab 202105 | RevTab 202106 | RevTab 202107 | Totale RevTab
| Richiedente | Casagrande Lorenzo | [6 empty] | Stima | SI | [72 empty] | DOR | Crediti - Pensabene | P999999 | Nuovo |  | 2021-07-15 | 2021-12-31 |  | 9430 | 9430 | 0% | 9430 | 0% | Arcari, Gabriella | NSW | P999999Arcari, GabriellaNSW | 34.62 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
| Ambito | - | [6 empty] | Pianificazione | SI | [72 empty] | DOR | Crediti - Pensabene | [7 empty] | 0 | #DIV/0! | 0 | #DIV/0! | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
| Risorse | Risorsa | Risorsa | Risorsa | Risorsa | Risorsa | Risorsa |  | Go A partire | SI | [72 empty] | DOR | Crediti - Automation | [7 empty] | 0 | #DIV/0! | 0 | #DIV/0! | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Release | Release | [6 empty] | Creazione Offerta | SI | [72 empty] | DOR | Crediti - Automation | [7 empty] | 0 | #DIV/0! | 0 | #DIV/0!
| Data Avvio lavori | 2022-02-07
| Bucket | Retest |  |  |  | Descrizione | ODA 7200172731 per 29 ggu su Evolutive 2022 --> OFFERTA: ISP2021102129EvolutiveDialogo - Scaliamo 15 gg dal plafond (di fatto azzerandolo) --> riferimento ISP2021080290IntegrazioneNCC - Restano 6 gg da coprire con future RDA AFU OK
| %completamento | 98.2%
| Prossima MIlestone | 2022-03-25
| Riferimenti Stima | ISP20220203_Dialogo_Industriale_evo_03_22.xlsx
| Stima | 50 | 400 | 11500 | 230 | #REF! | [5 empty] | 44599 | 44648
| Stato | Coerente
BASELINE | [65 empty] | FTE pianificate |  |  | Settimana | BASELINE | EFFETTIVO | BCWS | EV | ACWP | CPI | SPI | CV | SV | COMMESSA | REV TAB | BCWS-ACWP
[66 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | FTE | 50 | 7 | 6 | 12 | 10 | 11 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-12-28 | 2021-01-03 | S53 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | ORE | 400 | 56 | 48 | 96 | 80 | 88 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-01-04 | 2021-01-10 | S2 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2021-01-11 | 2021-01-17 | S3 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 0 | 2021-01-18 | 2021-01-24 | S4 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  | Data Inizio | Data Fine | Durata | PESO | n sett INIZIO | n sett FINE | NOTE Pianificazione | FTE Allocati |  |  |  | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 0 | 2021-01-25 | 2021-01-31 | S5 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| Dialogo Industriale 03 2022 | 2022-02-07 | 2022-03-25 | 47 | 100% | 7 | 13 |  | #REF! | 100% | allocazione budget "ideale" | Baseline | € | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | 0 | 2021-02-01 | 2021-02-07 | S6 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| DESIGN | 2022-02-07 | 2022-03-07 | 29 | 22% | 7 | 11 |  | 1 | 15% | 1725 | DESIGN | 2530 | 1150 | 920 | 460 | [49 empty] | 0 | 2021-02-08 | 2021-02-14 | S7 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| DATA PREP | 2022-02-21 | 2022-03-07 | 15 | 12% | 9 | 11 |  | #REF! | 15% | 1725 | DATA PREP | 1380 |  |  | 460 | 460 | 460 | [47 empty] | 0 | 2021-02-15 | 2021-02-21 | S8 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| EXEC 1 | 2022-02-21 | 2022-03-07 | 15 | 30% | 9 | 11 |  | #REF! | 30% | 3450 | EXEC 1 | 3450 |  |  | 1150 | 1150 | 1150 | [47 empty] | 0 | 2021-02-22 | 2021-02-28 | S9 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| MNG | 2022-02-07 | 2022-03-07 | 29 | 24% | 7 | 11 |  | #REF! | 26% | 2990 | MNG | 2760 | 460 | 460 | 690 | 690 | 460 | [47 empty] | 0 | 2021-03-01 | 2021-03-07 | S10 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| SUPP UAT | 2022-03-07 | 2022-03-25 | 19 | 12% | 11 | 13 |  | #REF! | 14% | 1610 | SUPP UAT | 1380 |  |  |  |  | 460 | 460 | 460 | [45 empty] | 0 | 2021-03-08 | 2021-03-14 | S11 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! |  | 0 | 0 | 0 | [52 empty] | 0 | 2021-03-15 | 2021-03-21 | S12 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! |  | 0 | 0 | 0 | [52 empty] | 0 | 2021-03-22 | 2021-03-28 | S13 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! |  | 0 | 0 | 0 | [52 empty] | 0 | 2021-03-29 | 2021-04-04 | S14 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! |  | 0 | 0 | 0 | [52 empty] | 0 | 2021-04-05 | 2021-04-11 | S15 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[13 empty] | 11500 | 1610 | 1380 | 2760 | 2300 | 2530 | 460 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-12 | 2021-04-18 | S16 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[13 empty] | 0 | [52 empty] | 0 | 2021-04-19 | 2021-04-25 | S17 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2021-04-26 | 2021-05-02 | S18 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| Offerta |  | 70 | 16100 | [5 empty] | % Compl | % Budget | Costo | Tempo | [52 empty] | 0 | 2021-05-03 | 2021-05-09 | S19 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[10 empty] | 98.2% | #REF! | #REF! | #REF! | [52 empty] | 0 | 2021-05-10 | 2021-05-16 | S20 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | [52 empty] | 0 | 2021-05-17 | 2021-05-23 | S21 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2021-05-24 | 2021-05-30 | S22 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | Malacrida Alessandro | #REF! | [52 empty] | 0 | 2021-05-31 | 2021-06-06 | S23 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | Tosti Nicola | #REF! | [52 empty] | 0 | 2021-06-07 | 2021-06-13 | S24 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | Risorsa | #REF! | [52 empty] | 0 | 2021-06-14 | 2021-06-20 | S25 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | Risorsa | #REF! | [52 empty] | 0 | 2021-06-21 | 2021-06-27 | S26 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | Risorsa | #REF! | [52 empty] | 0 | 2021-06-28 | 2021-07-04 | S27 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | Risorsa | #REF! | [52 empty] | 0 | 2021-07-05 | 2021-07-11 | S28 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | Risorsa | #REF! | [52 empty] | 0 | 2021-07-12 | 2021-07-18 | S29 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | Risorsa | #REF! | [52 empty] | 0 | 2021-07-19 | 2021-07-25 | S30 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | gg/u | #REF! | [52 empty] | 0 | 2021-07-26 | 2021-08-01 | S31 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2021-08-02 | 2021-08-08 | S32 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2021-08-09 | 2021-08-15 | S33 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2021-08-16 | 2021-08-22 | S34 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | FTE | #REF! | [52 empty] | 0 | 2021-08-23 | 2021-08-29 | S35 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | BCWS | #REF! | [52 empty] | 0 | 2021-08-30 | 2021-09-05 | S36 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | EV | #REF! | [52 empty] | 0 | 2021-09-06 | 2021-09-12 | S37 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | ACWP | #REF! | [52 empty] | 0 | 2021-09-13 | 2021-09-19 | S38 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | CPI | #REF! | [52 empty] | 0 | 2021-09-20 | 2021-09-26 | S39 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | SPI | #REF! | [52 empty] | 0 | 2021-09-27 | 2021-10-03 | S40 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | CV | #REF! | [52 empty] | 0 | 2021-10-04 | 2021-10-10 | S41 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | SV | #REF! | [52 empty] | 0 | 2021-10-11 | 2021-10-17 | S42 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | REV_TAB | #REF! | [52 empty] | 0 | 2021-10-18 | 2021-10-24 | S43 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2021-10-25 | 2021-10-31 | S44 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2021-11-01 | 2021-11-07 | S45 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2021-11-08 | 2021-11-14 | S46 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2021-11-15 | 2021-11-21 | S47 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2021-11-22 | 2021-11-28 | S48 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2021-11-29 | 2021-12-05 | S49 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
EFFETTIVO | [65 empty] | 0 | 2021-12-06 | 2021-12-12 | S50 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2021-12-13 | 2021-12-19 | S51 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | FTE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2021-12-20 | 2021-12-26 | S52 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | ORE |  | 40 | 0 | 40 | 40 | 42 | 42 | 42 | 40 | 40 | 40 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-27 | 2022-01-02 | S53 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2022-01-03 | 2022-01-09 | S2 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 0 | 2022-01-10 | 2022-01-16 | S3 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  | 43290 | 43392 | Durata | % | n sett INIZIO | n sett FINE | NOTE Realizzazione |  |  |  |  | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 0 | 2022-01-17 | 2022-01-23 | S4 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| Dialogo Industriale 03 2022 | 0 |  | 1899-12-31 | 98.2% | 0 | 0 |  |  |  |  | Malacrida Alessandro | #REF! | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | 0 | 2022-01-24 | 2022-01-30 | S5 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| Analisi |  |  | 0 | 100% | 0 | 0 |  |  |  |  | DESIGN | 40 | 40 | [51 empty] | 0 | 2022-01-31 | 2022-02-06 | S6 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| Sviluppo |  |  | 0 | 100% | 0 | 0 |  |  |  |  | DATA PREP | 0 | [52 empty] | 1.15 | 2022-02-07 | 2022-02-13 | S7 | 1610 | 0 | 1610 | 1817 | 0 | - | 1.1286 | 1817 | 207 |  | 181.7 | 1610
| System test |  |  | 0 | 100% | 0 | 0 |  |  |  |  | EXEC 1 | 0 | [52 empty] | 0.98571 | 2022-02-14 | 2022-02-20 | S8 | 1380 | 0 | 2990 | 2449.5 | 0 | - | 0.81923 | 2449.5 | -540.5 |  | 244.95 | 2990
| UAT |  |  | 0 | 95% | 0 | 0 |  |  |  |  | MNG | 0 | [52 empty] | 1.9714 | 2022-02-21 | 2022-02-27 | S9 | 2760 | 0 | 5750 | 4807 | 0 | - | 0.836 | 4807 | -943 |  | 480.7 | 5750
| PRODUZIONE |  |  | 0 | 95% | 0 | 0 |  |  |  |  | SUPP UAT | 0 | [52 empty] | 1.6429 | 2022-02-28 | 2022-03-06 | S10 | 2300 | 0 | 8050 | 7325.5 | 0 | - | 0.91 | 7325.5 | -724.5 |  | 732.55 | 8050
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [52 empty] | 1.8071 | 2022-03-07 | 2022-03-13 | S11 | 2530 | 0 | 10580 | 9499 | 0 | - | 0.89783 | 9499 | -1081 |  | 949.9 | 10580
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [52 empty] | 0.32857 | 2022-03-14 | 2022-03-20 | S12 | 460 | 0 | 11040 | 10920.4 | 0 | - | 0.98917 | 10920.4 | -119.6 |  | 1092.04 | 11040
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [52 empty] | 0.32857 | 2022-03-21 | 2022-03-27 | S13 | 460 | 0 | 11500 | 11293 | 0 | - | 0.982 | 11293 | -207 |  | 1129.3 | 11500
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [52 empty] | 0 | 2022-03-28 | 2022-04-03 | S14 | 0 | 0 | 11500 | 11293 | 0 | - | 0.982 | 11293 | -207 |  | 1129.3 | 11500
[13 empty] | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-04-04 | 2022-04-10 | S15 | 0 | 0 | 11500 | 11293 | 0 | - | 0.982 | 11293 | -207 |  | 1129.3 | 11500
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 2022-04-11 | 2022-04-17 | S16 | 0 | 0 | 11500 | 11293 | 0 | - | 0.982 | 11293 | -207 |  | 1129.3 | 11500
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 0 | 2022-04-18 | 2022-04-24 | S17 | 0 | 0 | 11500 | 11293 | 0 | - | 0.982 | 11293 | -207 |  | 1129.3 | 11500
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 0 | 2022-04-25 | 2022-05-01 | S18 | 0 | 0 | 11500 | 11293 | 0 | - | 0.982 | 11293 | -207 |  | 1129.3 | 11500
[12 empty] | Tosti Nicola | #REF! | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 | 0 | 2022-05-02 | 2022-05-08 | S19 | 0 | 0 | 11500 | 11293 | 0 | - | 0.982 | 11293 | -207 |  | 1129.3 | 11500
[12 empty] | DESIGN | 0 | [52 empty] | 0 | 2022-05-09 | 2022-05-15 | S20 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | si | invio Stima |  |  |  | DATA PREP | 0 | [53 empty] | 2022-05-16 | 2022-05-22 | S21 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | si | accettazione STIMA |  |  |  | EXEC 1 | 326 |  |  | 40 | 40 | 42 | 42 | 42 | 40 | 40 | 40 | [43 empty] | 2022-05-23 | 2022-05-29 | S22 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | no | Pianificazione |  |  |  | MNG | 40 | [10 empty] | 32 | 8 | [41 empty] | 2022-05-30 | 2022-06-05 | S23 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | no | GO a Partire |  |  |  | SUPP UAT | 0 | [53 empty] | 2022-06-06 | 2022-06-12 | S24 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[7 empty] | si | Creazione offerta |  |  |  | 0 | 0 | [53 empty] | 2022-06-13 | 2022-06-19 | S25 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[8 empty] | invio proposta Formale |  |  |  | 0 | 0 | [53 empty] | 2022-06-20 | 2022-06-26 | S26 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[8 empty] | Creazione work order |  |  |  | 0 | 0 | [53 empty] | 2022-06-27 | 2022-07-03 | S27 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | 0 | 0 | [53 empty] | 2022-07-04 | 2022-07-10 | S28 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | 366 | 0 | 0 | 40 | 40 | 42 | 42 | 42 | 40 | 40 | 40 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2022-07-11 | 2022-07-17 | S29 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | Tariffa €/h | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 |  | 2022-07-18 | 2022-07-24 | S30 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 |  | 2022-07-25 | 2022-07-31 | S31 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 |  | 2022-08-01 | 2022-08-07 | S32 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Risorsa | #REF! | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5 |  | 2022-08-08 | 2022-08-14 | S33 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | DESIGN | 0 | [53 empty] | 2022-08-15 | 2022-08-21 | S34 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | DATA PREP | 0 | [53 empty] | 2022-08-22 | 2022-08-28 | S35 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | EXEC 1 | 0 | [53 empty] | 2022-08-29 | 2022-09-04 | S36 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | MNG | 0 | [53 empty] | 2022-09-05 | 2022-09-11 | S37 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | SUPP UAT | 0 | [53 empty] | 2022-09-12 | 2022-09-18 | S38 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0 | [53 empty] | 2022-09-19 | 2022-09-25 | S39 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0 | [53 empty] | 2022-09-26 | 2022-10-02 | S40 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05
[12 empty] | Risorsa | #REF! | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5
[12 empty] | DESIGN | 0
[12 empty] | DATA PREP | 0
[12 empty] | EXEC 1 | 0
[12 empty] | MNG | 0
[12 empty] | SUPP UAT | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05
[12 empty] | Risorsa | 12.5 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5
[12 empty] | DESIGN | 0
[12 empty] | DATA PREP | 0
[12 empty] | EXEC 1 | 0
[12 empty] | MNG | 0
[12 empty] | SUPP UAT | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05
[12 empty] | Risorsa | #REF! | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5
[12 empty] | DESIGN | 0
[12 empty] | DATA PREP | 0
[12 empty] | EXEC 1 | 0
[12 empty] | MNG | 0
[12 empty] | SUPP UAT | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05
[12 empty] | Risorsa | #REF! | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5
[12 empty] | DESIGN | 0
[12 empty] | DATA PREP | 0
[12 empty] | EXEC 1 | 0
[12 empty] | MNG | 0
[12 empty] | SUPP UAT | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05
[12 empty] | Risorsa | #REF! | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5
[12 empty] | DESIGN | 0
[12 empty] | DATA PREP | 0
[12 empty] | EXEC 1 | 0
[12 empty] | MNG | 0
[12 empty] | SUPP UAT | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05
[12 empty] | Risorsa | #REF! | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5
[12 empty] | DESIGN | 0
[12 empty] | DATA PREP | 0
[12 empty] | EXEC 1 | 0
[12 empty] | MNG | 0
[12 empty] | SUPP UAT | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05
[12 empty] | ACWP | #REF! | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5
[12 empty] | DESIGN | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | DATA PREP | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | EXEC 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | MNG | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | SUPP UAT | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05
[12 empty] | % completamento | 98.2% | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5
[12 empty] | DESIGN | 100% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | DATA PREP | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | EXEC 1 | 100% | 0% | 0% | 50% | 75% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | MNG | 95% | 20% | 20% | 20% | 80% | 90% | 94% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
[12 empty] | SUPP UAT | 95% | 0% | 0% | 0% | 0% | 0% | 70% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
0 | bar: 98.2% to S5
0 | bar: 98.2% to S5
0 | bar: 98.2% to S5
0 | bar: 98.2% to S5
[14 empty] | 15.8% | 21.3% | 41.8% | 63.7% | 82.6% | 94.96% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2%
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05
[12 empty] | EV | 11293 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5
[12 empty] | DESIGN | 2530 | 1265 | 1897.5 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530
[12 empty] | DATA PREP | 1380 | 0 | 0 | 0 | 0 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380
[12 empty] | EXEC 1 | 3450 | 0 | 0 | 1725 | 2587.5 | 3105 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450
[12 empty] | MNG | 2622 | 552 | 552 | 552 | 2208 | 2484 | 2594.4 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622
[12 empty] | SUPP UAT | 1311 | 0 | 0 | 0 | 0 | 0 | 966 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 1817 | 2449.5 | 4807 | 7325.5 | 9499 | 10920.4 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293
[12 empty] | AVANZAMENTO PROGETTO | 98.2%: gg tot; S7: %avanz.; S8: risorsa; S9: gg effettivi; S10: coperto
Gestione Progetto
Recepimento requisiti funzionali e coordinamento
Analisi
[12 empty] | DESIGN | 98.2%: 18
REVIEW
[12 empty] | Esecuzione Testbook (600 TC) - Retest - NRT | 98.2%: 36
[12 empty] | Mngment ALM - Reportistica | 98.2%: 10
Rilascio in Produzione | bar: S1
Rilascio in Produzione W1 | bar: S9; S1
Rilascio in Produzione W2 | bar: S9; S1
AVANZAMENTO PROGETTO | bar: 98.2% to S10; S1
AVANZAMENTO ANALISI | bar: 98.2% to S10; S1
AVANZAMENTO ESECUZIONE | bar: 98.2% to S10; S1
[12 empty] | GG RESIDUI | 98.2%: 64
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05
[12 empty] | % completamento_rev_tab | 0% | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5
[12 empty] | Mngment | 100% | 0% | 52.5% | 77.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | Design | 100% | 0% | 0% | 0% | 0% | 10% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | Esecuzione e restest | 100% | 0% | 0% | 5% | 52.5% | 76.5% | 91% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | Produzione | 95% | 0% | 20% | 20% | 26% | 81% | 90.4% | 94.1% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
[12 empty] | 0 | 95% | 0% | 0% | 0% | 0% | 0% | 7% | 72.5% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
0 | bar: 0% to S5
0 | bar: 0% to S5
0 | bar: 0% to S5
0 | bar: 0% to S5
[14 empty] | 0% | 16.35% | 23.35% | 43.99% | 65.59% | 83.84% | 95.28% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2% | 98.2%
[13 empty] | DAL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
[13 empty] | AL | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05
[12 empty] | EV_rev_tab | 11293 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S1 | S2 | S3 | S4 | S5
[12 empty] | Mngment | 2530 | 0 | 1328.25 | 1960.75 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530 | 2530
[12 empty] | Design | 1380 | 0 | 0 | 0 | 0 | 138 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380
[12 empty] | Esecuzione e restest | 3450 | 0 | 0 | 172.5 | 1811.25 | 2639.25 | 3139.5 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450 | 3450
[12 empty] | Produzione | 2622 | 0 | 552 | 552 | 717.6 | 2235.6 | 2495.04 | 2597.16 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622 | 2622
[12 empty] | 0 | 1311 | 0 | 0 | 0 | 0 | 0 | 96.6 | 1000.5 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311 | 1311
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 1880.25 | 2685.25 | 5058.85 | 7542.85 | 9641.14 | 10957.66 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293 | 11293
Formulas:
Malacrida Alessandro = MIN([Malacrida Alessandro, row below]:C30)
Descrizione = WEEKNUM([Malacrida Alessandro])
Note on N16: Chiara DE RIGGI: compresi 60gg di settembre Mail: CONTRATTI DIGITALI - Test Factory proseguio attività
Note on M213: Chiara DE RIGGI: Scritti 200 tc ne eseguono 300
Note on M214: Chiara DE RIGGI: Scritti 400 tc

## BRB 227 Delibere (2022) (hidden)
| Nome Progetto | BRB 227 Delibere
| Responsabile | Malacrida Alessandro | [80 empty] | Note | BM | Referente | Workorder | Status | Text WO | Data Inizio | Data Fine | Fatturazione | OFFERTA | Residuo da Maturato | M% | Residuo da RevTab | RT% | Text Ressource | Time Code |  | PriceList | Hours 202003 | Hours 202004 | Hours 202005 | Hours 202006 | Hours 202007 | Hours 202008 | Hours 202009 | Hours 202010 | Hours 202011 | Hours 202012 | Hours 202101 | Hours 202102 | Hours 202103 | Hours 202104 | Hours 202105 | Hours 202106 | Hours 202107 | Maturato al 29/02 | Maturato 202003 | Maturato 202004 | Maturato 202005 | Maturato 202006 | Maturato 202007 | Maturato 202008 | Maturato 202009 | Maturato 202010 | Maturato 202011 | Maturato 202012 | Maturato 202101 | Maturato 202102 | Maturato 202103 | Maturato 202104 | Maturato 202105 | Maturato 202106 | Maturato 202107 | Totale Maturato | RevTab al 29/02 | RevTab 202003 | RevTab 202004 | RevTab 202005 | RevTab 202006 | RevTab 202007 | RevTab 202008 | RevTab 202009 | RevTab 202010 | RevTab 202011 | RevTab 202012 | RevTab 202101 | RevTab 202102 | RevTab 202103 | RevTab 202104 | RevTab 202105 | RevTab 202106 | RevTab 202107 | Totale RevTab
| Richiedente | Dambra | [6 empty] | Stima | SI | [73 empty] | DOR | Crediti - Pensabene | P1717072.10 | Nuovo | ISGS20211011123_BRB227_Delibere | 2021-07-15 | 2021-12-31 |  | 28290 | 28290 | 0% | 28290 | 0% | Arcari, Gabriella | NSW | P1717072.10Arcari, GabriellaNSW | 34.62 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
| Ambito | - | [6 empty] | Pianificazione | SI | [73 empty] | DOR | Crediti - Pensabene | [7 empty] | 0 | #DIV/0! | 0 | #DIV/0! | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
| Risorse | Risorsa | Risorsa | Risorsa | Risorsa | Risorsa | Risorsa |  | Go A partire | SI | [73 empty] | DOR | Crediti - Automation | [7 empty] | 0 | #DIV/0! | 0 | #DIV/0! | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Release | Release | [6 empty] | Creazione Offerta | SI | [73 empty] | DOR | Crediti - Automation | [7 empty] | 0 | #DIV/0! | 0 | #DIV/0!
| Data Avvio lavori | 2021-10-22
| Bucket | Da Avviare |  |  |  | Descrizione | ISGS20211011123_BRB227_Delibere da stimare Piano per 2022
| %completamento | 89.84%
| Prossima MIlestone | TBD
| Riferimenti Stima | -
| Stima | 123 | 984 | 28290 | 230 | #REF! | [5 empty] | 44655 | 44753
| Stato | Coerente
BASELINE | [65 empty] | FTE pianificate |  |  | Settimana | BASELINE | EFFETTIVO | BCWS | EV | ACWP | CPI | SPI | CV | SV | COMMESSA | REV TAB | BCWS-ACWP
[66 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | FTE | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 25 | 8 | 20 | 10 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-01-03 | 2022-01-09 | S2 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[12 empty] | ORE | 984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 200 | 64 | 160 | 80 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-01-10 | 2022-01-16 | S3 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[66 empty] | 0 | 2022-01-17 | 2022-01-23 | S4 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 0 | 2022-01-24 | 2022-01-30 | S5 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  | Data Inizio | Data Fine | Durata | PESO | n sett INIZIO | n sett FINE | NOTE Pianificazione | FTE Allocati |  |  |  | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 0 | 2022-01-31 | 2022-02-06 | S6 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| BRB 227 Delibere | 2022-04-05 | 2022-07-08 | 95 | 100% | 15 | 28 |  | #REF! | 100% | allocazione budget "ideale" | Baseline | € | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | 0 | 2022-02-07 | 2022-02-13 | S7 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| DESIGN |  |  | 0 | 4.065% | 0 | 0 |  | 1 | 0% | 0 | DESIGN | 1150 | [24 empty] | 1150 | [27 empty] | 0 | 2022-02-14 | 2022-02-20 | S8 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| EXEC | 2022-04-05 | 2022-07-08 | 95 | 55.28% | 15 | 28 |  | #REF! | 55% | 15559.5 | EXEC | 15640 | [24 empty] | 4600 | 4600 | 690 | 2300 | 1150 | 1150 | 1150 | [21 empty] | 0 | 2022-02-21 | 2022-02-27 | S9 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
| MNG | 2022-04-05 | 2022-04-15 | 11 | 40.65% | 15 | 16 |  | #REF! | 45% | 12730.5 | MNG | 11500 | [24 empty] | 1150 | 1150 | 1150 | 2300 | 1150 | 2300 | 2300 | [21 empty] | 0 | 2022-02-28 | 2022-03-06 | S10 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! |  | 0 | 0 | 0 | [52 empty] | 0 | 2022-03-07 | 2022-03-13 | S11 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 | 2022 | #REF! |  | 0 | 0 | 0 | [52 empty] | 0 | 2022-03-14 | 2022-03-20 | S12 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! |  | 0 | 0 | 0 | [52 empty] | 0 | 2022-03-21 | 2022-03-27 | S13 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! |  | 0 | 0 | 0 | [52 empty] | 0 | 2022-03-28 | 2022-04-03 | S14 | 0 | 0 | 0 | 0 | 0 | - | - | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! |  | 0 | 0 | 0 | [52 empty] | 4.9286 | 2022-04-04 | 2022-04-10 | S15 | 6900 | 0 | 6900 | 8510 | 0 | - | 1.2333 | 8510 | 1610 |  | 851 | 6900
|  |  |  | 0 | 0% | 0 | 0 |  | #REF! |  | 0 | 0 | 0 | [52 empty] | 4.1071 | 2022-04-11 | 2022-04-17 | S16 | 5750 | 0 | 12650 | 12995 | 0 | - | 1.0273 | 12995 | 345 |  | 1299.5 | 12650
[13 empty] | 28290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6900 | 5750 | 1840 | 4600 | 2300 | 3450 | 3450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3143 | 2022-04-18 | 2022-04-24 | S17 | 1840 | 0 | 14490 | 15341 | 0 | - | 1.0587 | 15341 | 851 |  | 1534.1 | 14490
[13 empty] | 0 | [52 empty] | 3.2857 | 2022-04-25 | 2022-05-01 | S18 | 4600 | 0 | 19090 | 20815 | 0 | - | 1.0904 | 20815 | 1725 |  | 2081.5 | 19090
[66 empty] | 1.6429 | 2022-05-02 | 2022-05-08 | S19 | 2300 | 0 | 21390 | 22540 | 0 | - | 1.0538 | 22540 | 1150 |  | 2254 | 21390
| Offerta | ISGS20211011123_BRB227_Delibere | 29 | 6670 | [5 empty] | % Compl | % Budget | Costo | Tempo | [52 empty] | 2.4643 | 2022-05-09 | 2022-05-15 | S20 | 3450 | 0 | 24840 | 25415 | 0 | - | 1.0231 | 25415 | 575 |  | 2541.5 | 24840
[10 empty] | 89.84% | #REF! | #REF! | #REF! | [52 empty] | 2.4643 | 2022-05-16 | 2022-05-22 | S21 | 3450 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[11 empty] | #REF! | #REF! | #REF! | [52 empty] | 0 | 2022-05-23 | 2022-05-29 | S22 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[66 empty] | 0 | 2022-05-30 | 2022-06-05 | S23 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | Arcari Gabriella | #REF! | [52 empty] | 0 | 2022-06-06 | 2022-06-12 | S24 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | Capodici Paolo | #REF! | [52 empty] | 0 | 2022-06-13 | 2022-06-19 | S25 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | Malacrida Alessandro | #REF! | [52 empty] | 0 | 2022-06-20 | 2022-06-26 | S26 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | Risorsa | #REF! | [52 empty] | 0 | 2022-06-27 | 2022-07-03 | S27 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | Risorsa | #REF! | [52 empty] | 0 | 2022-07-04 | 2022-07-10 | S28 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | Risorsa | #REF! | [52 empty] | 0 | 2022-07-11 | 2022-07-17 | S29 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | Risorsa | #REF! | [52 empty] | 0 | 2022-07-18 | 2022-07-24 | S30 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | Risorsa | #REF! | [52 empty] | 0 | 2022-07-25 | 2022-07-31 | S31 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | gg/u | #REF! | [52 empty] | 0 | 2022-08-01 | 2022-08-07 | S32 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2022-08-08 | 2022-08-14 | S33 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[66 empty] | 0 | 2022-08-15 | 2022-08-21 | S34 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | #REF! | #REF! | [52 empty] | 0 | 2022-08-22 | 2022-08-28 | S35 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | FTE | #REF! | [52 empty] | 0 | 2022-08-29 | 2022-09-04 | S36 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | BCWS | #REF! | [52 empty] | 0 | 2022-09-05 | 2022-09-11 | S37 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | EV | #REF! | [52 empty] | 0 | 2022-09-12 | 2022-09-18 | S38 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | ACWP | #REF! | [52 empty] | 0 | 2022-09-19 | 2022-09-25 | S39 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | CPI | #REF! | [52 empty] | 0 | 2022-09-26 | 2022-10-02 | S40 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | SPI | #REF! | [52 empty] | 0 | 2022-10-03 | 2022-10-09 | S41 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | CV | #REF! | [52 empty] | 0 | 2022-10-10 | 2022-10-16 | S42 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | SV | #REF! | [52 empty] | 0 | 2022-10-17 | 2022-10-23 | S43 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | REV_TAB | #REF! | [52 empty] | 0 | 2022-10-24 | 2022-10-30 | S44 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[66 empty] | 0 | 2022-10-31 | 2022-11-06 | S45 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290 | 0
[66 empty] | 0 | 2022-11-07 | 2022-11-13 | S46 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[66 empty] | 0 | 2022-11-14 | 2022-11-20 | S47 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[66 empty] | 0 | 2022-11-21 | 2022-11-27 | S48 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[66 empty] | 0 | 2022-11-28 | 2022-12-04 | S49 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[66 empty] | 0 | 2022-12-05 | 2022-12-11 | S50 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
EFFETTIVO | [66 empty] | 2022-12-12 | 2022-12-18 | S51 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[67 empty] | 2022-12-19 | 2022-12-25 | S52 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | FTE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 2022-12-26 | 2023-01-01 | S53 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | ORE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2023-01-02 | 2023-01-08 | S1 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 2023-01-09 | 2023-01-15 | S2 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 |  | 2023-01-16 | 2023-01-22 | S3 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
|  | 43290 | 43392 | Durata | % | n sett INIZIO | n sett FINE | NOTE Realizzazione |  |  |  |  | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 |  | 2023-01-23 | 2023-01-29 | S4 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
| BRB 227 Delibere | 0 |  | 1899-12-31 | 89.84% | 0 | 0 |  |  |  |  | Arcari Gabriella | #REF! | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 |  | 2023-01-30 | 2023-02-05 | S5 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
| Analisi |  |  | 0 | 0% | 0 | 0 |  |  |  |  | DESIGN | 0 | [53 empty] | 2023-02-06 | 2023-02-12 | S6 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
| Sviluppo |  |  | 0 | 100% | 0 | 0 |  |  |  |  | EXEC | 32 | [24 empty] | 32 | [28 empty] | 2023-02-13 | 2023-02-19 | S7 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
| System test |  |  | 0 | 85% | 0 | 0 |  |  |  |  | MNG | 0 | [53 empty] | 2023-02-20 | 2023-02-26 | S8 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
| UAT |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [53 empty] | 2023-02-27 | 2023-03-05 | S9 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
| PRODUZIONE |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [53 empty] | 2023-03-06 | 2023-03-12 | S10 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [53 empty] | 2023-03-13 | 2023-03-19 | S11 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [53 empty] | 2023-03-20 | 2023-03-26 | S12 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [53 empty] | 2023-03-27 | 2023-04-02 | S13 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
| #REF! |  |  | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 | [53 empty] | 2023-04-03 | 2023-04-09 | S14 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[13 empty] | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2023-04-10 | 2023-04-16 | S15 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 2023-04-17 | 2023-04-23 | S16 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 |  | 2023-04-24 | 2023-04-30 | S17 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 |  | 2023-05-01 | 2023-05-07 | S18 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | Capodici Paolo | #REF! | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 |  | 2023-05-08 | 2023-05-14 | S19 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | DESIGN | 0 | [53 empty] | 2023-05-15 | 2023-05-21 | S20 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[7 empty] | si | invio Stima |  |  |  | EXEC | 32 | [24 empty] | 32 | [28 empty] | 2023-05-22 | 2023-05-28 | S21 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[7 empty] | si | accettazione STIMA |  |  |  | MNG | 0 | [53 empty] | 2023-05-29 | 2023-06-04 | S22 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[7 empty] | no | Pianificazione |  |  |  | 0 | 0 | [53 empty] | 2023-06-05 | 2023-06-11 | S23 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[7 empty] | no | GO a Partire |  |  |  | 0 | 0 | [53 empty] | 2023-06-12 | 2023-06-18 | S24 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[7 empty] | si | Creazione offerta |  |  |  | 0 | 0 | [53 empty] | 2023-06-19 | 2023-06-25 | S25 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[8 empty] | invio proposta Formale |  |  |  | 0 | 0 | [53 empty] | 2023-06-26 | 2023-07-02 | S26 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[8 empty] | Creazione work order |  |  |  | 0 | 0 | [53 empty] | 2023-07-03 | 2023-07-09 | S27 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[12 empty] | 0 | 0 | [53 empty] | 2023-07-10 | 2023-07-16 | S28 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[13 empty] | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2023-07-17 | 2023-07-23 | S29 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[13 empty] | Tariffa €/h | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 34.62 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 | 36.25 |  | 2023-07-24 | 2023-07-30 | S30 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 28290
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 |  | 2023-07-31 | 2023-08-06 | S31 | 0 | 0 | 28290 |  |  | - | 0 | 0 | -28290 |  |  | 0
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 |  | 2023-08-07 | 2023-08-13 | S32 | 0 | 0 |  |  |  | - | - | 0 | 0 |  |  | 0
[12 empty] | Malacrida Alessandro | #REF! | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 |  | 2023-08-14 | 2023-08-20 | S33 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | DESIGN | 0 | [53 empty] | 2023-08-21 | 2023-08-27 | S34 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | EXEC | 0 | [53 empty] | 2023-08-28 | 2023-09-03 | S35 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | MNG | 0 | [53 empty] | 2023-09-04 | 2023-09-10 | S36 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0 | [53 empty] | 2023-09-11 | 2023-09-17 | S37 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0 | [53 empty] | 2023-09-18 | 2023-09-24 | S38 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0 | [53 empty] | 2023-09-25 | 2023-10-01 | S39 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0 | [53 empty] | 2023-10-02 | 2023-10-08 | S40 | 0 | 0 |  |  |  | - | - | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16
[12 empty] | Risorsa | #REF! | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 0
[12 empty] | MNG | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16
[12 empty] | Risorsa | 12.5 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 0
[12 empty] | MNG | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16
[12 empty] | Risorsa | #REF! | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 0
[12 empty] | MNG | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16
[12 empty] | Risorsa | #REF! | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 0
[12 empty] | MNG | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16
[12 empty] | Risorsa | #REF! | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 0
[12 empty] | MNG | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tariffa €/h | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16
[12 empty] | Risorsa | #REF! | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42
[12 empty] | DESIGN | 0
[12 empty] | EXEC | 0
[12 empty] | MNG | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16
[12 empty] | ACWP | #REF! | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42
[12 empty] | DESIGN | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | EXEC | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | MNG | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16
[12 empty] | % completamento | 89.84% | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42
DESIGN | bar: 89.84% to S42
[12 empty] | EXEC | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 65% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | MNG | 85% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 45% | 45% | 45% | 60% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85%
0 | bar: 89.84% to S42
0 | bar: 89.84% to S42
0 | bar: 89.84% to S42
0 | bar: 89.84% to S42
0 | bar: 89.84% to S42
0 | bar: 89.84% to S42
[14 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.08% | 45.93% | 54.23% | 73.58% | 79.67% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84%
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16
[12 empty] | EV | 25415 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42
[12 empty] | DESIGN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | EXEC | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3910 | 7820 | 10166 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640
[12 empty] | MNG | 9775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 5175 | 5175 | 5175 | 6900 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8510 | 12995 | 15341 | 20815 | 22540 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415
[12 empty] | AVANZAMENTO PROGETTO | 89.84%: gg tot; S43: %avanz.; S44: risorsa; S45: gg effettivi; S46: coperto
Gestione Progetto
Recepimento requisiti funzionali e coordinamento
Analisi
[12 empty] | DESIGN | 89.84%: 18
REVIEW
[12 empty] | Esecuzione Testbook (600 TC) - Retest - NRT | 89.84%: 36
[12 empty] | Mngment ALM - Reportistica | 89.84%: 10
Rilascio in Produzione | bar: S38
Rilascio in Produzione W1 | bar: S45; S38
Rilascio in Produzione W2 | bar: S45; S38
AVANZAMENTO PROGETTO | bar: 89.84% to S46; S38
AVANZAMENTO ANALISI | bar: 89.84% to S46; S38
AVANZAMENTO ESECUZIONE | bar: 89.84% to S46; S38
[12 empty] | GG RESIDUI | 89.84%: 64
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16
[12 empty] | % completamento_rev_tab | 0% | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42
Mngment | bar: 0% to S42
[12 empty] | Design | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.5% | 27.5% | 51.5% | 68.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[12 empty] | Esecuzione e restest | 85% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4% | 40.5% | 45% | 45% | 46.5% | 62.5% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85%
Produzione | bar: 0% to S42
0 | bar: 0% to S42
0 | bar: 0% to S42
0 | bar: 0% to S42
0 | bar: 0% to S42
0 | bar: 0% to S42
[14 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.008% | 31.67% | 46.76% | 56.16% | 74.19% | 80.69% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84% | 89.84%
[13 empty] | DAL | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
[13 empty] | AL | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10 | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14 | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16
[12 empty] | EV_rev_tab | 25415 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S53 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42
[12 empty] | Mngment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Design | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391 | 4301 | 8054.6 | 10713.4 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640 | 15640
[12 empty] | Esecuzione e restest | 9775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 4657.5 | 5175 | 5175 | 5347.5 | 7187.5 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775 | 9775
[12 empty] | Produzione | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851 | 8958.5 | 13229.6 | 15888.4 | 20987.5 | 22827.5 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415 | 25415
Formulas:
Malacrida Alessandro = MIN([Malacrida Alessandro, row below]:C30)
Descrizione = WEEKNUM([Malacrida Alessandro])
Note on N16: Chiara DE RIGGI: compresi 60gg di settembre Mail: CONTRATTI DIGITALI - Test Factory proseguio attività
Note on M213: Chiara DE RIGGI: Scritti 200 tc ne eseguono 300
Note on M214: Chiara DE RIGGI: Scritti 400 tc