## README
Gate 4 ¦ 3-Concept Financial Model (Unified Skeleton)
Model File | SPINA3_Gate4_FinancialModel_C1-C3_v1.0_20251227.xlsx
Build Date (local) | 2025-12-27
Concept Runs | C1 / C2 / C3 (same definitions + logic; ScenarioSelector drives display)
Cashflow Timestep | Monthly (t = 0..N-1)
NPV Discount Rate (Base) | 11.0% nominal p.a. (DG-0052 Base)
Inflation Convention | 2.0% nominal p.a. (DG-0002 Base) — not escalated in this skeleton; prices/costs are treated as base-year inputs.
Notes | Spend totals in Spend_Curve_Params had no cached values in SSOT; totals are derived from CostPlan bucket totals and allocated across phases by GFA delivered share (see Inputs_SSOT).
Sources (SSOT) | MasterInputs, ProgramPhasing, CostPlan, ScheduleBaseline, CashFlowCurves, HardConstraints, DataGapsRanges, Hold/Ops Pack

## Inputs_SSOT
Inputs_SSOT — Snapshots (SSOT) + Trace
Source Files (Read-only SSOT)
Workstream | Filename
MasterInputs | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx
ProgramPhasing | SPINA3_Inputs_ConceptProgramPhasing_C1-C3_v1.1.2_20251226.xlsx
CostPlan | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx
ScheduleBaseline | SPINA3_ScheduleBaseline_Gantt_C1-C3_v1.0.4.5_20251227_UltraTraceRefPatch.xlsx
CashFlowCurves | SPINA3_CashFlowCurves_Params_C1-C3_v1.0.1.4_20251227_UltraTraceRefPatch.xlsx
HardConstraints | SPINA3_Inputs_HardConstraints_All_v1.0_20251224.xlsx
DataGapsRanges | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx
Hold/Ops Pack | SPINA3_Hold_Operations_AssumptionsPack_ScenarioB_v1.0.1.1_20251227_VersionLogAdd.xlsx
Concept_Metrics (Program & Phasing SSOT)
Concept_ID | Concept_Name | Metric_Group | Metric_Name | Value | Unit | Timing_or_Phase | Notes | Source_Ref
C1 | Concept 1: “Residential-Led Green Quarter” | Areas | Total GFA (overall) | 46000 | m² | All | Approx (source uses ~ / 'Approximately'). | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ Approximately 46,000 m² GFA total
C1 | Concept 1: “Residential-Led Green Quarter” | Areas | Residential GFA | 27600 | m² | All | Approx; stated explicitly. Other use GFA not explicitly quantified for C1. | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ 27,600 m² residential
C1 | Concept 1: “Residential-Led Green Quarter” | Areas | Tertiary/Office GFA | 6900 | m² | All | Only % is stated for C1; no explicit m² stated. ¦ Original Value: TBD – not specified in primary source. Derived from SSOT Total_GFA and shares; Base as exact allocation. Evidence_Tier=SSOT_Derived; Confidence=High. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0024, MI-0029, MI-0030 ¦ Derived allocation
C1 | Concept 1: “Residential-Led Green Quarter” | Areas | Commercial/Retail GFA | 4600 | m² | All | Only % is stated for C1; no explicit m² stated. ¦ Original Value: TBD – not specified in primary source. Derived from SSOT Total_GFA and shares; Base as exact allocation. Evidence_Tier=SSOT_Derived; Confidence=High. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0024, MI-0029, MI-0031 ¦ Derived allocation
C1 | Concept 1: “Residential-Led Green Quarter” | Areas | Civic/Other GFA | 6900 | m² | All | Only % is stated for C1; no explicit m² stated. ¦ Original Value: TBD – not specified in primary source. Derived from SSOT Total_GFA and shares; Base as exact allocation. Evidence_Tier=SSOT_Derived; Confidence=High. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0024, MI-0029, MI-0032 ¦ Derived allocation
C1 | Concept 1: “Residential-Led Green Quarter” | Mix | Residential share | 60 | % of GFA | All | Approx (~60%). | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ ~60% Residential
C1 | Concept 1: “Residential-Led Green Quarter” | Mix | Tertiary/Office share | 15 | % of GFA | All | Approx (~15%). | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ ~15% Office
C1 | Concept 1: “Residential-Led Green Quarter” | Mix | Commercial/Retail share | 10 | % of GFA | All | Approx (~10%). | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ ~10% Retail
C1 | Concept 1: “Residential-Led Green Quarter” | Mix | Civic/Other share | 15 | % of GFA | All | Approx (~15%). | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ ~15% Civic/
C1 | Concept 1: “Residential-Led Green Quarter” | Units | Total residential units (approx; rounded) | 300 | units | All | Source indicates ~314 units then 'round to 300'. | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ round to 300
C1 | Concept 1: “Residential-Led Green Quarter” | Units | Affordable housing (max share mentioned) | 20 | % of units | All | Stated as 'Up to 20% of units'. | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ Affordable Housing: Up to 20%
C1 | Concept 1: “Residential-Led Green Quarter” | Other | Average gross unit size (range) | 85 | m²/unit (gross) | All | Range stated; keep as text to preserve range. Original range text preserved: '80–90'; Base set to midpoint for numeric stability. Distribution_Type=Triangular. Audit note: Original source stated range '80–90' (verbatim). Stored Value is midpoint for numeric stability. Low=80; High=90; Base(midpoint)=85. | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ Average gross unit size range 80–90 m² (gross) ¦ Derived midpoint per normalization rule ¦ Range preserved in Notes; midpoint used for Base
C1 | Concept 1: “Residential-Led Green Quarter” | Other | Residential net unit size (range) | 67.5 | m²/unit (net) | All | Range stated; keep as text to preserve range. Original range text preserved: '65–70'; Base set to midpoint for numeric stability. Distribution_Type=Triangular. Audit note: Original source stated range '65–70' (verbatim). Stored Value is midpoint for numeric stability. Low=65; High=70; Base(midpoint)=67.5. | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ Residential net unit size range 65–70 m² (net) ¦ Derived midpoint per normalization rule ¦ Range preserved in Notes; midpoint used for Base
C1 | Concept 1: “Residential-Led Green Quarter” | Other | Residential net-to-gross efficiency (assumed) | 80 | % | All | Stated as assumed ~80%. | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ efficiency for residential is assumed ~80%
C1 | Concept 1: “Residential-Led Green Quarter” | Commercial | Supermarket size (if included) | 1500 | m² | All | Mentioned as a medium-sized supermarket (~1,500 m²). | 1. Cover & Version.docx ¦ Concept 1: “Residential-Led Green Quarter” ¦ medium-sized supermarket (~1,500 m²)
C2 | Concept 2: “Balanced Urban Hub” | Areas | Total GFA (overall) | 46000 | m² | All | Approx (source uses ~ / 'Still ~46,000 m²'). | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ Still ~46,000 m² GFA total
C2 | Concept 2: “Balanced Urban Hub” | Areas | Residential GFA | 18400 | m² | All | Approx; stated explicitly. ¦ Original Value: 18500. Reconciled to SSOT shares (40/40/20) from MasterInputs. Evidence_Tier=SSOT_Derived; Confidence=High. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0039, MI-0043 ¦ Derived allocation
C2 | Concept 2: “Balanced Urban Hub” | Areas | Tertiary/Office GFA | 18400 | m² | All | Approx; stated explicitly. ¦ Original Value: 18500. Reconciled to SSOT shares (40/40/20) from MasterInputs. Evidence_Tier=SSOT_Derived; Confidence=High. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0039, MI-0044 ¦ Derived allocation
C2 | Concept 2: “Balanced Urban Hub” | Areas | Commercial/Retail GFA | 9200 | m² | All | Approx; stated explicitly. ¦ Original Value: 9000. Reconciled to SSOT shares (40/40/20) from MasterInputs. Evidence_Tier=SSOT_Derived; Confidence=High. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0039, MI-0045 ¦ Derived allocation
C2 | Concept 2: “Balanced Urban Hub” | Mix | Residential share | 40 | % of GFA | All | Stated as ~40% / 40% in use mix. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ ~40% Residential
C2 | Concept 2: “Balanced Urban Hub” | Mix | Tertiary/Office share | 40 | % of GFA | All | Stated as 40% in use mix. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ 40% Tertiary
C2 | Concept 2: “Balanced Urban Hub” | Mix | Commercial/Retail share | 20 | % of GFA | All | Stated as 20% in use mix. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ 20% Commercial
C2 | Concept 2: “Balanced Urban Hub” | Units | Total residential units (about) | 200 | units | All | Stated as 'about 200 units'. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ about 200 units
C2 | Concept 2: “Balanced Urban Hub” | Buildings | Office buildings count (stated option) | 2 | buildings | All | Stated as 'Two office buildings'. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ Two office buildings
C2 | Concept 2: “Balanced Urban Hub” | Buildings | Office building size (each, approx) | 9000 | m² GFA/building | All | Stated as '~9,000 m² each'. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ ~9,000 m² each
C2 | Concept 2: “Balanced Urban Hub” | Commercial | Retail split: supermarket+mall area | 3000 | m² | All | Stated as '3,000 m² supermarket+mall'. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ 3,000 m² supermarket+mall
C2 | Concept 2: “Balanced Urban Hub” | Commercial | Retail split: high-street retail area | 6000 | m² | All | Stated as '6,000 m² of high-street retail'. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ 6,000 m² of high-street
C2 | Concept 2: “Balanced Urban Hub” | Other | Office net-to-gross (assumed range) | 87.5 | % | All | Stated as '~85–90%'. Original range text preserved: '85–90'; Base set to midpoint for numeric stability. Distribution_Type=Triangular. Audit note: Original source stated range '85–90' (verbatim). Stored Value is midpoint for numeric stability. Low=85; High=90; Base(midpoint)=87.5. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ Office net-to-gross range 85–90% ¦ Derived midpoint per normalization rule ¦ Range preserved in Notes; midpoint used for Base
C2 | Concept 2: “Balanced Urban Hub” | Other | Net office area (derived in text) | 16500 | m² net | All | Stated as 'meaning 18,500 m² GFA yields ~16,500 m² net office space'. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ yields ~16,500 m² net
C2 | Concept 2: “Balanced Urban Hub” | Other | Jobs accommodated (range; stated) | 1200 | jobs | All | Stated range; keep as text. Original range text preserved: '1,100–1,300'; Base set to midpoint for numeric stability. Distribution_Type=Triangular. Audit note: Original source stated range '1,100–1,300' (verbatim). Stored Value is midpoint for numeric stability. Low=1100; High=1300; Base(midpoint)=1200. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ Jobs accommodated range 1,100–1,300 ¦ Derived midpoint per normalization rule ¦ Range preserved in Notes; midpoint used for Base
C2 | Concept 2: “Balanced Urban Hub” | Other | Workspace density (stated) | 15 | m²/workstation | All | Stated as '~15 m² per workstation'. | 1. Cover & Version.docx ¦ Concept 2: “Balanced Urban Hub” ¦ ~15 m² per workstation
C3 | Concept 3: “Innovation Campus & Housing” | Areas | Total GFA (overall) | 46000 | m² | All | Concept 3 section does not explicitly restate total GFA. ¦ Original Value: TBD – not specified in primary source. Derived from SSOT Total_GFA (MasterInputs). Evidence_Tier=SSOT_Derived; Confidence=Medium. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0055 ¦ Derived allocation
C3 | Concept 3: “Innovation Campus & Housing” | Areas | Residential GFA | 23000 | m² | All | Approx; stated explicitly. | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ ~23,000 m² GFA residential
C3 | Concept 3: “Innovation Campus & Housing” | Areas | Tertiary/Office GFA (approx) | 13800 | m² | All | Stated as '~30% (~13,800 m²)'. | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ Tertiary ~30% (~13,800 m²)
C3 | Concept 3: “Innovation Campus & Housing” | Areas | Commercial/Retail GFA (approx) | 4600 | m² | All | Stated as '~10% (~4,600 m²)'. | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ Retail ~10% (~4,600 m²)
C3 | Concept 3: “Innovation Campus & Housing” | Areas | Special/Institutional GFA (approx) | 4600 | m² | All | Stated as 'Special 4,600 m² (10%)'. | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ Special 4,600 m² (10%)
C3 | Concept 3: “Innovation Campus & Housing” | Mix | Residential share | 50 | % of GFA | All | Approx (~50%). | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ ~50% Residential
C3 | Concept 3: “Innovation Campus & Housing” | Mix | Tertiary share | 30 | % of GFA | All | Approx (~30%). | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ ~30% Tertiary
C3 | Concept 3: “Innovation Campus & Housing” | Mix | Commercial/Retail share | 10 | % of GFA | All | Approx (~10%). | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ ~10% Commercial
C3 | Concept 3: “Innovation Campus & Housing” | Mix | Special/Institutional share | 10 | % of GFA | All | Approx (~10%). | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ ~10% Special
C3 | Concept 3: “Innovation Campus & Housing” | Units | Total residential units (if mostly regular apartments) | 250 | units | All | Stated as '~250 units'. | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ ~250 units
C3 | Concept 3: “Innovation Campus & Housing” | Units | Regular residential units (if student housing included) | 150 | units | All | Stated as '150 regular units + student residence'. | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ 150 regular units
C3 | Concept 3: “Innovation Campus & Housing” | Units | Student housing beds (if included) | 100 | beds | All | Stated as 'student residence of 100 beds'. | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ student residence of 100 beds
C3 | Concept 3: “Innovation Campus & Housing” | Other | Student housing area per bed (stated) | 20 | m² GFA/bed | All | Stated as '~20 m² GFA/bed'. | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ roughly 20 m² GFA/bed
C3 | Concept 3: “Innovation Campus & Housing” | Other | Student housing area for 100 beds (stated) | 2000 | m² | All | Stated as '100 beds = 2,000 m²'. | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ 100 beds = 2,000 m²
C3 | Concept 3: “Innovation Campus & Housing” | Buildings | Tertiary building description (stated) | one 7-story multi-use building | text | All | Text description; no further quantification. | 1. Cover & Version.docx ¦ Concept 3: “Innovation Campus & Housing” ¦ 13,800 m² could be one 7-story
Phasing_Table (Program & Phasing SSOT)
Concept_ID | Phase_ID | Phase_Timeframe | Phase_Duration | Key_Deliverables | Units_Delivered_in_Phase | Units_Unit | GFA_Delivered_in_Phase | GFA_Unit | Dependencies_or_Gates | Notes | Source_Ref | GFA_Delivered_in_Phase_num
C1 | P1 | Years 1–2 | 24 | Focus on southern part – construct ~150 housing units; build Via Ceva extension in this phase (as stated). | 150 | units | 23000 | m² | Via Ceva extension in Phase 1 (as stated). | Approx on unit count (~150). ¦ Original GFA_Delivered_in_Phase: TBD – not specified in primary source. Set from SSOT schedule input (MI-0074) for Gate4 readiness. Evidence_Tier=SSOT_Derived; Confidence=High. ¦ Original Phase_Duration: 2 years (stated as Years 1–2). Stored as numeric months=24 per deterministic conversion rule. Evidence_Tier=Derived; Confidence=Medium. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0074 ¦ Derived allocation ¦ Duration months derived from Phase_Timeframe per deterministic rule | 23000
C1 | P2 | Years 3–5 | 36 | Develop the northern residential block (~150 units) and small office/co-working building near Environment Park (as stated); complete remaining public spaces (as stated). | 150 | units | 23000 | m² | Office/co-working near Environment Park mentioned. | Approx on unit count (~150). ¦ Original GFA_Delivered_in_Phase: TBD – not specified in primary source. Set from SSOT schedule input (MI-0080) for Gate4 readiness. Evidence_Tier=SSOT_Derived; Confidence=High. ¦ Original Phase_Duration: 3 years (stated as Years 3–5). Stored as numeric months=36 per deterministic conversion rule. Evidence_Tier=Derived; Confidence=Medium. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0080 ¦ Derived allocation ¦ Duration months derived from Phase_Timeframe per deterministic rule | 23000
C1 | P3 | Year 5–6 | 24 | Project close-out – deliver any remaining civic/retail/amenities and absorption/sale of remaining units (as described). | 0 | units | 0 | m² | Narrative-only close-out phase. | Timeframe stated as Year 5–6. ¦ Original Units_Delivered_in_Phase: TBD – not specified in primary source. Set from SSOT schedule input (MI-0085) for Gate4 readiness. Evidence_Tier=SSOT_Derived; Confidence=High. ¦ Original GFA_Delivered_in_Phase: TBD – not specified in primary source. Set from SSOT schedule input (MI-0086) for Gate4 readiness. Evidence_Tier=SSOT_Derived; Confidence=High. ¦ Original Phase_Duration: TBD – not specified in primary source. Stored as numeric months=24 per deterministic conversion rule. Evidence_Tier=Derived; Confidence=Medium. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0086 ¦ Derived allocation ¦ Duration months derived from Phase_Timeframe per deterministic rule | 0
C2 | P1 | Years 1–3 | 36 | Construct one office building (~9k m²) and one residential block (~100 units) simultaneously; deliver central retail complex (at least supermarket portion) and basic infrastructure; includes opening Via Ceva and partial Via Dronero (as stated). | 100 | units | 18200 | m² | Requires coordination of office + housing + retail delivery (as described). | Approx on office size (~9k) and units (~100). ¦ Original Phase_Duration: 3 years (stated as Years 1–3). Stored as numeric months=36 per deterministic conversion rule. Evidence_Tier=Derived; Confidence=Medium. ¦ Hotfix: Reconciled phase total GFA to match 100 res units in P1 (~9,200 m²) + office (~9,000 m²); remainder allocated to P2 to preserve total 46,000 m². | SPINA3_Inputs_ConceptProgramPhasing_C1-C3_v1.1_20251226.xlsx ¦ Phasing_Table ¦ C2 P1/P2 ¦ Derived reconciliation using C2 totals and units split | 18200
C2 | P2 | Years 4–6 | 36 | Build the second office building and remaining ~100 residential units; continue/complete public space and park (as described). | 100 | units | 27800 | m² | Second office building referenced; size stated elsewhere as ~9,000 m² each (see Concept_Metrics). | Approx on unit count (~100). ¦ Original GFA_Delivered_in_Phase: TBD – not specified in primary source. Set from SSOT schedule input (MI-0098) for Gate4 readiness. Evidence_Tier=SSOT_Derived; Confidence=High. ¦ Original Phase_Duration: 3 years (stated as Years 4–6). Stored as numeric months=36 per deterministic conversion rule. Evidence_Tier=Derived; Confidence=Medium. ¦ Hotfix: Reconciled phase total GFA to match 100 res units in P1 (~9,200 m²) + office (~9,000 m²); remainder allocated to P2 to preserve total 46,000 m². | SPINA3_Inputs_ConceptProgramPhasing_C1-C3_v1.1_20251226.xlsx ¦ Phasing_Table ¦ C2 P1/P2 ¦ Derived reconciliation using C2 totals and units split | 27800
C2 | P3 | Year 6 | 12 | Finalize any leftover retail fit-outs (e.g., smaller shops once enough residents/workers); avoid flooding office market (as described). | 0 | units | 0 | m² | Narrative-only Phase 3 (no quantified delivery). | Timeframe stated as Year 6+. ¦ Original Units_Delivered_in_Phase: TBD – not specified in primary source. Set from SSOT schedule input (MI-0103) for Gate4 readiness. Evidence_Tier=SSOT_Derived; Confidence=High. ¦ Original GFA_Delivered_in_Phase: TBD – not specified in primary source. Set from SSOT schedule input (MI-0104) for Gate4 readiness. Evidence_Tier=SSOT_Derived; Confidence=High. ¦ Original Phase_Duration: TBD – not specified in primary source. Stored as numeric months=12 per deterministic conversion rule. Original Phase_Timeframe: Year 6+. 'Year 6+' normalized to finite Year 6; duration set to 12 months per default rule. Evidence_Tier=Derived; Confidence=Medium. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0104 ¦ Derived allocation ¦ Duration months derived from Phase_Timeframe per deterministic rule | 0
C3 | P1 | Years 1–3 | 36 | Develop the core Innovation Campus building(s) and initial housing (~100 units); anchor institution early is key (as stated). | 100 | units | 18400 | m² | Dependency: securing anchor institution early (as stated). | Approx on unit count (~100). ¦ Original GFA_Delivered_in_Phase: TBD – not specified in primary source. Set from SSOT schedule input (MI-0110) for Gate4 readiness. Evidence_Tier=SSOT_Derived; Confidence=High. ¦ Original Phase_Duration: 3 years (stated as Years 1–3). Stored as numeric months=36 per deterministic conversion rule. Evidence_Tier=Derived; Confidence=Medium. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0110 ¦ Derived allocation ¦ Duration months derived from Phase_Timeframe per deterministic rule | 18400
C3 | P2 | Years 4–5 | 24 | Build remaining housing (~150 units) and a secondary office/tertiary component if not done in phase 1 (as described). | 150 | units | 27600 | m² | Secondary office/tertiary component referenced conditionally. | Approx on unit count (~150). ¦ Original GFA_Delivered_in_Phase: TBD – not specified in primary source. Set from SSOT schedule input (MI-0116) for Gate4 readiness. Evidence_Tier=SSOT_Derived; Confidence=High. ¦ Original Phase_Duration: 2 years (stated as Years 4–5). Stored as numeric months=24 per deterministic conversion rule. Evidence_Tier=Derived; Confidence=Medium. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0116 ¦ Derived allocation ¦ Duration months derived from Phase_Timeframe per deterministic rule | 27600
C3 | P3 | Year 5–6 | 24 | Complete special features and remaining retail; fully animate site with residents and daily population from institution (as described). | 0 | units | 0 | m² | Narrative-only Phase 3 (no quantified delivery). | Timeframe stated as Year 5–6. ¦ Original Units_Delivered_in_Phase: TBD – not specified in primary source. Set from SSOT schedule input (MI-0121) for Gate4 readiness. Evidence_Tier=SSOT_Derived; Confidence=High. ¦ Original GFA_Delivered_in_Phase: TBD – not specified in primary source. Set from SSOT schedule input (MI-0122) for Gate4 readiness. Evidence_Tier=SSOT_Derived; Confidence=High. ¦ Original Phase_Duration: TBD – not specified in primary source. Stored as numeric months=24 per deterministic conversion rule. Evidence_Tier=Derived; Confidence=Medium. | SPINA3_Inputs_MasterInputs_All_v1.3.2_UnleveredSwitch_20251226.xlsx ¦ Master_Inputs ¦ MI-0122 ¦ Derived allocation ¦ Duration months derived from Phase_Timeframe per deterministic rule | 0
Spend_Curve_Params (SSOT timing + curve; Total_Cost_Base derived from CostPlan bucket totals)
Param_ID | Concept_ID | Phase_ID | Cashflow_Bucket | WBS_Level1 | Curve_Profile_ID | Curve_Horizon_Months | Anchor_Window | Spend_Start_Month | Spend_End_Month | Total_Cost_Base | Evidence_Tier | Linked_Gap_ID | Notes | Source_Ref
SP-0001 | C1 | P1 | Land | Land / Demolition / Site & Remediation | SPEND_12_C1 | 12 | Pre-Construction | 12 | 15 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0002 | C1 | P1 | Demolition | Land / Demolition / Site & Remediation | SPEND_12_C1 | 12 | Pre-Construction | 12 | 15 | 658881 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0003 | C1 | P1 | Site | Land / Demolition / Site & Remediation | SPEND_12_C1 | 12 | Pre-Construction | 12 | 15 | 2306083.5 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0004 | C1 | P1 | HardCost | Hard Costs (Construction) | SPEND_12_C1 | 12 | Construction | 15 | 39 | 32944050 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0005 | C1 | P1 | SoftCost | Soft Costs (Professional & Development) | SPEND_12_C1 | 12 | Pre-Construction | 12 | 15 | 5765208.75 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0006 | C1 | P1 | PublicWorks | Public Works (Roads / Public space / Utilities) | SPEND_12_C1 | 12 | Construction | 15 | 39 | 1976643 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0007 | C1 | P1 | FinancingFees | Soft Costs (Professional & Development) | SPEND_12_C1 | 12 | Pre-Construction | 12 | 15 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0008 | C1 | P1 | Contingency | Hard Costs (Construction) | SPEND_12_C1 | 12 | Construction | 15 | 39 | 3294405 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0009 | C1 | P2 | Land | Land / Demolition / Site & Remediation | SPEND_12_C1 | 12 | Pre-Construction | 21 | 24 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0010 | C1 | P2 | Demolition | Land / Demolition / Site & Remediation | SPEND_12_C1 | 12 | Pre-Construction | 21 | 24 | 658881 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0011 | C1 | P2 | Site | Land / Demolition / Site & Remediation | SPEND_12_C1 | 12 | Pre-Construction | 21 | 24 | 2306083.5 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0012 | C1 | P2 | HardCost | Hard Costs (Construction) | SPEND_12_C1 | 12 | Construction | 24 | 60 | 32944050 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0013 | C1 | P2 | SoftCost | Soft Costs (Professional & Development) | SPEND_12_C1 | 12 | Pre-Construction | 21 | 24 | 5765208.75 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0014 | C1 | P2 | PublicWorks | Public Works (Roads / Public space / Utilities) | SPEND_12_C1 | 12 | Construction | 24 | 60 | 1976643 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0015 | C1 | P2 | FinancingFees | Soft Costs (Professional & Development) | SPEND_12_C1 | 12 | Pre-Construction | 21 | 24 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0016 | C1 | P2 | Contingency | Hard Costs (Construction) | SPEND_12_C1 | 12 | Construction | 24 | 60 | 3294405 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0017 | C1 | P3 | Land | Land / Demolition / Site & Remediation | SPEND_12_C1 | 12 | Pre-Construction | 45 | 48 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0018 | C1 | P3 | Demolition | Land / Demolition / Site & Remediation | SPEND_12_C1 | 12 | Pre-Construction | 45 | 48 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0019 | C1 | P3 | Site | Land / Demolition / Site & Remediation | SPEND_12_C1 | 12 | Pre-Construction | 45 | 48 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0020 | C1 | P3 | HardCost | Hard Costs (Construction) | SPEND_12_C1 | 12 | Construction | 48 | 72 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0021 | C1 | P3 | SoftCost | Soft Costs (Professional & Development) | SPEND_12_C1 | 12 | Pre-Construction | 45 | 48 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0022 | C1 | P3 | PublicWorks | Public Works (Roads / Public space / Utilities) | SPEND_12_C1 | 12 | Construction | 48 | 72 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0023 | C1 | P3 | FinancingFees | Soft Costs (Professional & Development) | SPEND_12_C1 | 12 | Pre-Construction | 45 | 48 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0024 | C1 | P3 | Contingency | Hard Costs (Construction) | SPEND_12_C1 | 12 | Construction | 48 | 72 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0025 | C2 | P1 | Land | Land / Demolition / Site & Remediation | SPEND_12_C2 | 12 | Pre-Construction | 12 | 15 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0026 | C2 | P1 | Demolition | Land / Demolition / Site & Remediation | SPEND_12_C2 | 12 | Pre-Construction | 12 | 15 | 522303.6 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0027 | C2 | P1 | Site | Land / Demolition / Site & Remediation | SPEND_12_C2 | 12 | Pre-Construction | 12 | 15 | 1828062.6 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0028 | C2 | P1 | HardCost | Hard Costs (Construction) | SPEND_12_C2 | 12 | Construction | 15 | 51 | 26115180 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0029 | C2 | P1 | SoftCost | Soft Costs (Professional & Development) | SPEND_12_C2 | 12 | Pre-Construction | 12 | 15 | 4570156.5 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0030 | C2 | P1 | PublicWorks | Public Works (Roads / Public space / Utilities) | SPEND_12_C2 | 12 | Construction | 15 | 51 | 1566910.8 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0031 | C2 | P1 | FinancingFees | Soft Costs (Professional & Development) | SPEND_12_C2 | 12 | Pre-Construction | 12 | 15 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0032 | C2 | P1 | Contingency | Hard Costs (Construction) | SPEND_12_C2 | 12 | Construction | 15 | 51 | 2611518 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0033 | C2 | P2 | Land | Land / Demolition / Site & Remediation | SPEND_12_C2 | 12 | Pre-Construction | 33 | 36 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0034 | C2 | P2 | Demolition | Land / Demolition / Site & Remediation | SPEND_12_C2 | 12 | Pre-Construction | 33 | 36 | 797804.4 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0035 | C2 | P2 | Site | Land / Demolition / Site & Remediation | SPEND_12_C2 | 12 | Pre-Construction | 33 | 36 | 2792315.4 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0036 | C2 | P2 | HardCost | Hard Costs (Construction) | SPEND_12_C2 | 12 | Construction | 36 | 72 | 39890220 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0037 | C2 | P2 | SoftCost | Soft Costs (Professional & Development) | SPEND_12_C2 | 12 | Pre-Construction | 33 | 36 | 6980788.5 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0038 | C2 | P2 | PublicWorks | Public Works (Roads / Public space / Utilities) | SPEND_12_C2 | 12 | Construction | 36 | 72 | 2393413.2 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0039 | C2 | P2 | FinancingFees | Soft Costs (Professional & Development) | SPEND_12_C2 | 12 | Pre-Construction | 33 | 36 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0040 | C2 | P2 | Contingency | Hard Costs (Construction) | SPEND_12_C2 | 12 | Construction | 36 | 72 | 3989022 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0041 | C2 | P3 | Land | Land / Demolition / Site & Remediation | SPEND_12_C2 | 12 | Pre-Construction | 57 | 60 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0042 | C2 | P3 | Demolition | Land / Demolition / Site & Remediation | SPEND_12_C2 | 12 | Pre-Construction | 57 | 60 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0043 | C2 | P3 | Site | Land / Demolition / Site & Remediation | SPEND_12_C2 | 12 | Pre-Construction | 57 | 60 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0044 | C2 | P3 | HardCost | Hard Costs (Construction) | SPEND_12_C2 | 12 | Construction | 60 | 72 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0045 | C2 | P3 | SoftCost | Soft Costs (Professional & Development) | SPEND_12_C2 | 12 | Pre-Construction | 57 | 60 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0046 | C2 | P3 | PublicWorks | Public Works (Roads / Public space / Utilities) | SPEND_12_C2 | 12 | Construction | 60 | 72 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0047 | C2 | P3 | FinancingFees | Soft Costs (Professional & Development) | SPEND_12_C2 | 12 | Pre-Construction | 57 | 60 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0048 | C2 | P3 | Contingency | Hard Costs (Construction) | SPEND_12_C2 | 12 | Construction | 60 | 72 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0049 | C3 | P1 | Land | Land / Demolition / Site & Remediation | SPEND_12_C3 | 12 | Pre-Construction | 12 | 15 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0050 | C3 | P1 | Demolition | Land / Demolition / Site & Remediation | SPEND_12_C3 | 12 | Pre-Construction | 12 | 15 | 538200 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0051 | C3 | P1 | Site | Land / Demolition / Site & Remediation | SPEND_12_C3 | 12 | Pre-Construction | 12 | 15 | 1883700 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0052 | C3 | P1 | HardCost | Hard Costs (Construction) | SPEND_12_C3 | 12 | Construction | 15 | 51 | 26910000 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0053 | C3 | P1 | SoftCost | Soft Costs (Professional & Development) | SPEND_12_C3 | 12 | Pre-Construction | 12 | 15 | 4709250 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0054 | C3 | P1 | PublicWorks | Public Works (Roads / Public space / Utilities) | SPEND_12_C3 | 12 | Construction | 15 | 51 | 1614600 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0055 | C3 | P1 | FinancingFees | Soft Costs (Professional & Development) | SPEND_12_C3 | 12 | Pre-Construction | 12 | 15 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0056 | C3 | P1 | Contingency | Hard Costs (Construction) | SPEND_12_C3 | 12 | Construction | 15 | 51 | 2691000 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0057 | C3 | P2 | Land | Land / Demolition / Site & Remediation | SPEND_12_C3 | 12 | Pre-Construction | 33 | 36 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0058 | C3 | P2 | Demolition | Land / Demolition / Site & Remediation | SPEND_12_C3 | 12 | Pre-Construction | 33 | 36 | 807300 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0059 | C3 | P2 | Site | Land / Demolition / Site & Remediation | SPEND_12_C3 | 12 | Pre-Construction | 33 | 36 | 2825550 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0060 | C3 | P2 | HardCost | Hard Costs (Construction) | SPEND_12_C3 | 12 | Construction | 36 | 60 | 40365000 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0061 | C3 | P2 | SoftCost | Soft Costs (Professional & Development) | SPEND_12_C3 | 12 | Pre-Construction | 33 | 36 | 7063875 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0062 | C3 | P2 | PublicWorks | Public Works (Roads / Public space / Utilities) | SPEND_12_C3 | 12 | Construction | 36 | 60 | 2421900 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0063 | C3 | P2 | FinancingFees | Soft Costs (Professional & Development) | SPEND_12_C3 | 12 | Pre-Construction | 33 | 36 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0064 | C3 | P2 | Contingency | Hard Costs (Construction) | SPEND_12_C3 | 12 | Construction | 36 | 60 | 4036500 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0065 | C3 | P3 | Land | Land / Demolition / Site & Remediation | SPEND_12_C3 | 12 | Pre-Construction | 45 | 48 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0066 | C3 | P3 | Demolition | Land / Demolition / Site & Remediation | SPEND_12_C3 | 12 | Pre-Construction | 45 | 48 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0067 | C3 | P3 | Site | Land / Demolition / Site & Remediation | SPEND_12_C3 | 12 | Pre-Construction | 45 | 48 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0068 | C3 | P3 | HardCost | Hard Costs (Construction) | SPEND_12_C3 | 12 | Construction | 48 | 72 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0069 | C3 | P3 | SoftCost | Soft Costs (Professional & Development) | SPEND_12_C3 | 12 | Pre-Construction | 45 | 48 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0070 | C3 | P3 | PublicWorks | Public Works (Roads / Public space / Utilities) | SPEND_12_C3 | 12 | Construction | 48 | 72 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0071 | C3 | P3 | FinancingFees | Soft Costs (Professional & Development) | SPEND_12_C3 | 12 | Pre-Construction | 45 | 48 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Procurement'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
SP-0072 | C3 | P3 | Contingency | Hard Costs (Construction) | SPEND_12_C3 | 12 | Construction | 48 | 72 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); timing window='Construction'. Total_Cost_Base blank unless available from CostPlan. | SPINA3_CostPlan_WBS_C1-C3_v1.2.1_20251226.xlsx ¦ Cashflow_Mapping ¦ WBS_Code
Receipt_Curve_Params (SSOT timing + curve; Total_Revenue_Base derived using ProgramPhasing mix + MasterInputs/ HoldPack)
Param_ID | Concept_ID | Phase_ID | Receipt_Channel | Pricing_MI_Input_ID | Absorption_MI_Input_ID | Curve_Profile_ID | Horizon_Months | Anchor_Window | Receipt_Start_Month | Receipt_End_Month | Total_Revenue_Base | Evidence_Tier | Linked_Gap_ID | Notes | Source_Ref | Total_Revenue_Derived
RC-0001 | C1 | P1 | Res_Sales | MI-0129 | MI-0132 | RECEIPT_12_C1 | 12 | Presales_Absorption | 39 | 51 | 19614400 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0129 | 19614400
RC-0002 | C1 | P1 | Office_Rent | MI-0130 | MI-0133 | RECEIPT_12_C1 | 12 | Post-Delivery | 51 | 54 | 3688912.5 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0130 | 3688912.5
RC-0003 | C1 | P1 | Retail_Rent | MI-0131 |  | RECEIPT_12_C1 | 12 | Post-Delivery | 51 | 54 | 3997224.3437 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Absorption assumption for retail not specified (no MI reference). | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0131 | 3997224.3437
RC-0004 | C1 | P1 | Res_Rent |  |  | RECEIPT_12_C1 | 12 | Post-Delivery | 51 | 54 | 3427595.2941 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Tenure split and residential rent assumptions are TBD; treat as placeholder. | TBD – not specified in sources | 3427595.2941
RC-0005 | C1 | P2 | Res_Sales | MI-0129 | MI-0132 | RECEIPT_12_C1 | 12 | Presales_Absorption | 60 | 72 | 19614400 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0129 | 19614400
RC-0006 | C1 | P2 | Office_Rent | MI-0130 | MI-0133 | RECEIPT_12_C1 | 12 | Post-Delivery | 72 | 75 | 3688912.5 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0130 | 3688912.5
RC-0007 | C1 | P2 | Retail_Rent | MI-0131 |  | RECEIPT_12_C1 | 12 | Post-Delivery | 72 | 75 | 3997224.3437 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Absorption assumption for retail not specified (no MI reference). | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0131 | 3997224.3437
RC-0008 | C1 | P2 | Res_Rent |  |  | RECEIPT_12_C1 | 12 | Post-Delivery | 72 | 75 | 3427595.2941 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Tenure split and residential rent assumptions are TBD; treat as placeholder. | TBD – not specified in sources | 3427595.2941
RC-0009 | C1 | P3 | Res_Sales | MI-0129 | MI-0132 | RECEIPT_12_C1 | 12 | Presales_Absorption | 72 | 84 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0129 | 0
RC-0010 | C1 | P3 | Office_Rent | MI-0130 | MI-0133 | RECEIPT_12_C1 | 12 | Post-Delivery | 84 | 87 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0130 | 0
RC-0011 | C1 | P3 | Retail_Rent | MI-0131 |  | RECEIPT_12_C1 | 12 | Post-Delivery | 84 | 87 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Absorption assumption for retail not specified (no MI reference). | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0131 | 0
RC-0012 | C1 | P3 | Res_Rent |  |  | RECEIPT_12_C1 | 12 | Post-Delivery | 84 | 87 | 0 | Assumed | DG-0010 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Tenure split and residential rent assumptions are TBD; treat as placeholder. | TBD – not specified in sources | 0
RC-0013 | C2 | P1 | Res_Sales | MI-0129 | MI-0132 | RECEIPT_12_C2 | 12 | Presales_Absorption | 51 | 63 | 9551360 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0129 | 9551360
RC-0014 | C2 | P1 | Office_Rent | MI-0130 | MI-0133 | RECEIPT_12_C2 | 12 | Post-Delivery | 63 | 66 | 5838105 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0130 | 5838105
RC-0015 | C2 | P1 | Retail_Rent | MI-0131 |  | RECEIPT_12_C2 | 12 | Post-Delivery | 63 | 66 | 4217361.3365 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Absorption assumption for retail not specified (no MI reference). | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0131 | 4217361.3365
RC-0016 | C2 | P1 | Res_Rent |  |  | RECEIPT_12_C2 | 12 | Post-Delivery | 63 | 66 | 1669089.8824 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Tenure split and residential rent assumptions are TBD; treat as placeholder. | TBD – not specified in sources | 1669089.8824
RC-0017 | C2 | P2 | Res_Sales | MI-0129 | MI-0132 | RECEIPT_12_C2 | 12 | Presales_Absorption | 72 | 84 | 14589440 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0129 | 14589440
RC-0018 | C2 | P2 | Office_Rent | MI-0130 | MI-0133 | RECEIPT_12_C2 | 12 | Post-Delivery | 84 | 87 | 8917545 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0130 | 8917545
RC-0019 | C2 | P2 | Retail_Rent | MI-0131 |  | RECEIPT_12_C2 | 12 | Post-Delivery | 84 | 87 | 6441903.58 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Absorption assumption for retail not specified (no MI reference). | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0131 | 6441903.58
RC-0020 | C2 | P2 | Res_Rent |  |  | RECEIPT_12_C2 | 12 | Post-Delivery | 84 | 87 | 2549488.9412 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Tenure split and residential rent assumptions are TBD; treat as placeholder. | TBD – not specified in sources | 2549488.9412
RC-0021 | C2 | P3 | Res_Sales | MI-0129 | MI-0132 | RECEIPT_12_C2 | 12 | Presales_Absorption | 72 | 84 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0129 | 0
RC-0022 | C2 | P3 | Office_Rent | MI-0130 | MI-0133 | RECEIPT_12_C2 | 12 | Post-Delivery | 84 | 87 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0130 | 0
RC-0023 | C2 | P3 | Retail_Rent | MI-0131 |  | RECEIPT_12_C2 | 12 | Post-Delivery | 84 | 87 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Absorption assumption for retail not specified (no MI reference). | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0131 | 0
RC-0024 | C2 | P3 | Res_Rent |  |  | RECEIPT_12_C2 | 12 | Post-Delivery | 84 | 87 | 0 | Assumed | DG-0014 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Tenure split and residential rent assumptions are TBD; treat as placeholder. | TBD – not specified in sources | 0
RC-0025 | C3 | P1 | Res_Sales | MI-0129 | MI-0132 | RECEIPT_12_C3 | 12 | Presales_Absorption | 51 | 63 | 12070400 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0129 | 12070400
RC-0026 | C3 | P1 | Office_Rent | MI-0130 | MI-0133 | RECEIPT_12_C3 | 12 | Post-Delivery | 63 | 66 | 5902260 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0130 | 5902260
RC-0027 | C3 | P1 | Retail_Rent | MI-0131 |  | RECEIPT_12_C3 | 12 | Post-Delivery | 63 | 66 | 2131852.9833 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Absorption assumption for retail not specified (no MI reference). | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0131 | 2131852.9833
RC-0028 | C3 | P1 | Res_Rent |  |  | RECEIPT_12_C3 | 12 | Post-Delivery | 63 | 66 | 2109289.4118 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Tenure split and residential rent assumptions are TBD; treat as placeholder. | TBD – not specified in sources | 2109289.4118
RC-0029 | C3 | P2 | Res_Sales | MI-0129 | MI-0132 | RECEIPT_12_C3 | 12 | Presales_Absorption | 60 | 72 | 18105600 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0129 | 18105600
RC-0030 | C3 | P2 | Office_Rent | MI-0130 | MI-0133 | RECEIPT_12_C3 | 12 | Post-Delivery | 72 | 75 | 8853390 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0130 | 8853390
RC-0031 | C3 | P2 | Retail_Rent | MI-0131 |  | RECEIPT_12_C3 | 12 | Post-Delivery | 72 | 75 | 3197779.4749 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Absorption assumption for retail not specified (no MI reference). | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0131 | 3197779.4749
RC-0032 | C3 | P2 | Res_Rent |  |  | RECEIPT_12_C3 | 12 | Post-Delivery | 72 | 75 | 3163934.1176 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Tenure split and residential rent assumptions are TBD; treat as placeholder. | TBD – not specified in sources | 3163934.1176
RC-0033 | C3 | P3 | Res_Sales | MI-0129 | MI-0132 | RECEIPT_12_C3 | 12 | Presales_Absorption | 72 | 84 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0129 | 0
RC-0034 | C3 | P3 | Office_Rent | MI-0130 | MI-0133 | RECEIPT_12_C3 | 12 | Post-Delivery | 84 | 87 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0130 | 0
RC-0035 | C3 | P3 | Retail_Rent | MI-0131 |  | RECEIPT_12_C3 | 12 | Post-Delivery | 84 | 87 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Absorption assumption for retail not specified (no MI reference). | SPINA3_Inputs_MasterInputs_All_v1.4.2.1_C2GFAFix_TraceHotfix_20251227.xlsx ¦ Master_Inputs ¦ MI-0131 | 0
RC-0036 | C3 | P3 | Res_Rent |  |  | RECEIPT_12_C3 | 12 | Post-Delivery | 84 | 87 | 0 | Assumed | DG-0019 | Template profile assumed (Curve_Library); Total_Revenue_Base blank unless computable without invention. Tenure split and residential rent assumptions are TBD; treat as placeholder. | TBD – not specified in sources | 0
Curve_Library (SSOT)
Profile_ID | Curve_Type | Horizon_Months | Month_Index | Weight | Evidence_Tier | Linked_Gap_ID | Notes | Source_Ref
SPEND_12_C1 | Spend | 12 | 1 | 0.0222 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C1 | Spend | 12 | 2 | 0.0333 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C1 | Spend | 12 | 3 | 0.0556 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C1 | Spend | 12 | 4 | 0.0778 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C1 | Spend | 12 | 5 | 0.1 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C1 | Spend | 12 | 6 | 0.1222 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C1 | Spend | 12 | 7 | 0.1333 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C1 | Spend | 12 | 8 | 0.1333 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C1 | Spend | 12 | 9 | 0.1222 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C1 | Spend | 12 | 10 | 0.1 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C1 | Spend | 12 | 11 | 0.0778 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C1 | Spend | 12 | 12 | 0.0223 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 1 | 0.01 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 2 | 0.02 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 3 | 0.03 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 4 | 0.05 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 5 | 0.07 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 6 | 0.09 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 7 | 0.11 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 8 | 0.12 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 9 | 0.13 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 10 | 0.14 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 11 | 0.12 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
RECEIPT_12_C1 | Receipt | 12 | 12 | 0.11 | Assumed | DG-0010 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0010
SPEND_12_C2 | Spend | 12 | 1 | 0.0222 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C2 | Spend | 12 | 2 | 0.0333 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C2 | Spend | 12 | 3 | 0.0556 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C2 | Spend | 12 | 4 | 0.0778 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C2 | Spend | 12 | 5 | 0.1 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C2 | Spend | 12 | 6 | 0.1222 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C2 | Spend | 12 | 7 | 0.1333 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C2 | Spend | 12 | 8 | 0.1333 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C2 | Spend | 12 | 9 | 0.1222 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C2 | Spend | 12 | 10 | 0.1 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C2 | Spend | 12 | 11 | 0.0778 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C2 | Spend | 12 | 12 | 0.0223 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 1 | 0.01 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 2 | 0.02 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 3 | 0.03 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 4 | 0.05 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 5 | 0.07 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 6 | 0.09 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 7 | 0.11 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 8 | 0.12 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 9 | 0.13 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 10 | 0.14 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 11 | 0.12 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
RECEIPT_12_C2 | Receipt | 12 | 12 | 0.11 | Assumed | DG-0014 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0014
SPEND_12_C3 | Spend | 12 | 1 | 0.0222 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
SPEND_12_C3 | Spend | 12 | 2 | 0.0333 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
SPEND_12_C3 | Spend | 12 | 3 | 0.0556 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
SPEND_12_C3 | Spend | 12 | 4 | 0.0778 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
SPEND_12_C3 | Spend | 12 | 5 | 0.1 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
SPEND_12_C3 | Spend | 12 | 6 | 0.1222 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
SPEND_12_C3 | Spend | 12 | 7 | 0.1333 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
SPEND_12_C3 | Spend | 12 | 8 | 0.1333 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
SPEND_12_C3 | Spend | 12 | 9 | 0.1222 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
SPEND_12_C3 | Spend | 12 | 10 | 0.1 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
SPEND_12_C3 | Spend | 12 | 11 | 0.0778 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
SPEND_12_C3 | Spend | 12 | 12 | 0.0223 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 1 | 0.01 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 2 | 0.02 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 3 | 0.03 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 4 | 0.05 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 5 | 0.07 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 6 | 0.09 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 7 | 0.11 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 8 | 0.12 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 9 | 0.13 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 10 | 0.14 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 11 | 0.12 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
RECEIPT_12_C3 | Receipt | 12 | 12 | 0.11 | Assumed | DG-0019 | Assumed template; editable; not factual. | SPINA3_Inputs_DataGapsRanges_All_v1.3_20251227.xlsx ¦ Gap_Register ¦ DG-0019
HardConstraints (Locked)
Constraint_ID | Category | Parameter_Name | Requirement_or_Limit | Value | Unit | Applies_To | Lock_Status | Notes | Source_Ref
HC-001 | Zoning | Zoning Code | Urban Transformation Zone ZUT 4.13/2 (Art.15 NUEA) – site-specific redevelopment zone requiring plan | Urban Transformation Zone ZUT 4.13/2 (Art.15 NUEA) – site-specific redevelopment zone requiring plan | text | All | Locked |  | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ Urban Transformation Zone ZUT 4.13/2
HC-002 | Site | Site Area (ST) | 109,183 m² total land area | 109,183 | m² | All | Locked |  | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ 109,183 m² total land
HC-003 | Density | Max Buildable GFA | 46,006 m² gross floor area (all uses combined) | 46,006 | m² | All | Locked |  | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ 46,006 m² gross floor
HC-004 | Density | Density (FAR) | ~0.42 m²/m² average (indicative: subzones at 0.4–0.7 m²/m²) | ~0.42 (indicative: 0.4–0.7) | m²/m² | All | Locked | Approx in source. | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ ~0.42 m²/m² average
HC-005 | Mix | Residential Use | ≥40% of total GFA must be residential | ≥40 | % of total GFA | All | Locked |  | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ ≥40% of total GFA
HC-006 | Mix | Tertiary/Office Use | ≤40% of GFA may be tertiary (offices, “Eurotorino”) | ≤40 | % of total GFA | All | Locked |  | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ ≤40% of GFA
HC-007 | Mix | Commercial/Retail Use | ≤20% of GFA may be ASPI (retail and services) | ≤20 | % of total GFA | All | Locked |  | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ ≤20% of GFA
HC-008 | PublicSpace | Public Service Land | ≈56,649 m² (52% of site) for public spaces & facilities (parks, plazas, etc.) | ≈56,649 | m² | All | Locked | Approx in source; also states (52% of site). | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ 56,649 m² (52% of site)
HC-009 | Roads | New Public Roads | Extend Via Dronero and Via Ceva through site (connect to C.so Oddone) – dedicated public right-of-way | Extend Via Dronero and Via Ceva through site; dedicated public right-of-way | text | Site connections as stated | Locked |  | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ Extend Via Dronero and Via
HC-010 | Height | Max building height – Via Ceva extension / internal axis | 5 floors max on Via Ceva extension, internal E–W axis, and Via Savigliano; 7 floors max on other fronts (Oddone, Vigevano, etc.) | 5 | floors | Via Ceva extension / internal E–W axis (as stated) | Locked | Approx wording retained where shown in source (contains ellipsis). | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ 5 floors max on Via Ceva
HC-011 | Height | Max building height – other fronts | 5 floors max on Via Ceva extension, internal E–W axis, and Via Savigliano; 7 floors max on other fronts (Oddone, Vigevano, etc.) | 7 | floors | Other fronts (Oddone, Vigevano, etc.) as stated | Locked | Approx wording retained where shown in source (contains ellipsis). | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ 7 floors max on other
HC-012 | Other | Setbacks & distances | Not explicitly specified – default building code rules apply (e.g. ~10 m between facing facades) | TBD – not specified in source (default rules referenced) | text | All | TBD | Source states not explicitly specified; mentions default building code rules (e.g. ~10 m between facing facades). | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ Not explicitly specified
HC-013 | Parking | Parking provision – Residential baseline | ~1 space per 100 m² GFA residential (≈1 per dwelling); offices/retail per local standards; mostly on-site (underground) | ~1 per 100 m² GFA residential (≈1 per dwelling) | text | Residential | Locked | Approx in source; non-residential also referenced separately. | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ 1 space per 100 m²
HC-014 | Parking | Parking provision – Offices/Retail | ~1 space per 100 m² GFA residential (≈1 per dwelling); offices/retail per local standards; mostly on-site (underground) | Offices/retail per local standards; mostly on-site (underground) | text | Office / Retail | Locked | No numeric value stated for offices/retail in source beyond 'per local standards'. | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ offices/retail per local
HC-015 | Process | Implementation | Detailed Executive Plan or Permesso Convenzionato required (no straight permit without agreement) | Detailed Executive Plan or Permesso Convenzionato required (no straight permit without agreement) | text | All | Locked |  | 1. Cover & Version.docx ¦ 3. A) Hard-Constraints Matrix ¦ Permesso Convenzionato
Hold/Ops Assumptions (subset used for exit value proxy)
Parameter_Group | Asset_Class | Parameter_Name | Units | Low | Base | High | Distribution_Type | Time_Basis/Notes | Recommended_For (C1/C2/C3/All) | Source_Ref | Evidence_Tier | Confidence
Hold Share / Exit Strategy | Residential | Hold share of residential delivered product (%) | % | 10 | 20 | 30 | Triangular | Scenario B policy proposal. Sell share implied = 100%-Hold%. | All | No primary/secondary source found ¦ Policy recommendation for Scenario B ¦ 2025-12-27 | Assumption_Default | Low
Hold Share / Exit Strategy | Office | Hold share of office delivered product (%) | % | 75 | 100 | 100 | Triangular | Scenario B policy proposal. Sell share implied = 100%-Hold%. | All | No primary/secondary source found ¦ Policy recommendation for Scenario B ¦ 2025-12-27 | Assumption_Default | Low
Hold Share / Exit Strategy | Retail | Hold share of retail delivered product (%) | % | 50 | 100 | 100 | Triangular | Scenario B policy proposal. Sell share implied = 100%-Hold%. | All | No primary/secondary source found ¦ Policy recommendation for Scenario B ¦ 2025-12-27 | Assumption_Default | Low
Hold Share / Exit Strategy | Residential | Stabilization / lease-up period to stabilized occupancy | months | 6 | 12 | 18 | Triangular | Assumed linear ramp. | All | No primary/secondary source found ¦ Standard underwriting practice ¦ 2025-12-27 | Assumption_Default | Low
Hold Share / Exit Strategy | Office | Stabilization / lease-up period to stabilized occupancy | months | 12 | 24 | 36 | Triangular | Assumed linear ramp. | All | No primary/secondary source found ¦ Standard underwriting practice ¦ 2025-12-27 | Assumption_Default | Low
Hold Share / Exit Strategy | Retail | Stabilization / lease-up period to stabilized occupancy | months | 12 | 18 | 30 | Triangular | Assumed linear ramp. | All | No primary/secondary source found ¦ Standard underwriting practice ¦ 2025-12-27 | Assumption_Default | Low
Hold Share / Exit Strategy | Residential | Exit yield / cap rate proxy (gross, derived from OMI rent & value) | % | 3.15 | 5.1 | 7.05 | Triangular | Derived gross yield proxy from OMI rent/value; net cap rate will be lower after opex. | All | OMI Price and Rent of D9 C8 C9 C10 C17 C19 2016-2025.xlsx ¦ D9 ¦ row 62 (Anno 2025 - Semestre 1) ¦ Derived yield from rent/value | Derived | Medium
Hold Share / Exit Strategy | Office | Exit yield / cap rate (net yield) | % | 7 | 7.6 | 8.2 | Triangular | Anchored to Torino office market indicators; Base=midpoint. | All | Centro Studi Gruppo IPI ¦ Torino Mercato Uffici (Q3 2024) ¦ Q3 2024 ¦ https://www.ipi-spa.com/file-download/download/public/2424 ¦ p.1 (prime net yield) & p.2 (Grade B net yield) ¦ Base=midpoint | Web_Industry | High
Hold Share / Exit Strategy | Retail | Exit yield / cap rate (net yield) | % | 6.75 | 8.38 | 10 | Triangular | Low from Italy prime shopping-centre yields; High reflects secondary/value-add 'double-digit returns' commentary. Base=midpoint. | All | Cushman & Wakefield ¦ Italy Retail Marketbeat Q3 2025 ¦ Q3 2025 ¦ https://assets.cushmanwakefield.com/-/media/cw/marketbeat-pdfs/2025/q3/emea/italy-retail-marketbeat-q3-2025.pdf ¦ p.1 (shopping centre yield 6.75%) ; Assoimmobiliare/C&W ¦ Italy Retail Marketbeat Q1 2024 ¦ Q1 2024 ¦ https://www.assoimmobiliare.it/wp-content/uploads/2024/05/Italy-Retail-Marketbeat.pdf ¦ p.1 (secondary assets 'double-digit returns') ¦ Base=midpoint | Derived | Medium
Rent & Leasing | Residential | Stabilized occupancy | % | 90 | 95 | 97 | Triangular | Vacancy = 100%-occupancy. | All | No primary/secondary/web source found ¦ Assumption_Default ¦ 2025-12-27 | Assumption_Default | Low
Rent & Leasing | Office | Stabilized occupancy | % | 88 | 92 | 95 | Triangular | Underwriting occupancy; prime vacancy reference ~2.6% (Grade A). | All | Centro Studi Gruppo IPI ¦ Torino Mercato Uffici (Q3 2024) ¦ Q3 2024 ¦ https://www.ipi-spa.com/file-download/download/public/2424 ¦ p.2 (vacancy rate Grade A 2.60%) ¦ Underwriting more conservative | Derived | Medium
Rent & Leasing | Retail | Stabilized occupancy | % | 85 | 90 | 93 | Triangular | Underwriting occupancy for neighborhood retail. | All | No primary/secondary/web source found ¦ Assumption_Default ¦ 2025-12-27 | Assumption_Default | Low
Operating Expenses | Residential | Non-recoverable opex (for NOI) as % of Gross Rental Income | % of GRI | 5 | 10 | 15 | Triangular | Applied to gross rental income to estimate NOI. | All | No primary/secondary/web source found ¦ Assumption_Default ¦ 2025-12-27 | Assumption_Default | Low
Operating Expenses | Office | Non-recoverable opex (for NOI) as % of Gross Rental Income | % of GRI | 10 | 15 | 20 | Triangular | Applied to gross rental income to estimate NOI. | All | No primary/secondary/web source found ¦ Assumption_Default ¦ 2025-12-27 | Assumption_Default | Low
Operating Expenses | Retail | Non-recoverable opex (for NOI) as % of Gross Rental Income | % of GRI | 8 | 12 | 18 | Triangular | Applied to gross rental income to estimate NOI. | All | No primary/secondary/web source found ¦ Assumption_Default ¦ 2025-12-27 | Assumption_Default | Low
Operating Expenses | Residential | Property management fee | % of EGI | 3 | 4 | 6 | Triangular | Assumption; % of EGI (after vacancy). | All | No primary/secondary/web source found ¦ Assumption_Default ¦ 2025-12-27 | Assumption_Default | Low
Operating Expenses | Office | Property management fee | % of EGI | 3 | 4 | 6 | Triangular | Assumption; % of EGI (after vacancy). | All | No primary/secondary/web source found ¦ Assumption_Default ¦ 2025-12-27 | Assumption_Default | Low
Operating Expenses | Retail | Property management fee | % of EGI | 3 | 4 | 6 | Triangular | Assumption; % of EGI (after vacancy). | All | No primary/secondary/web source found ¦ Assumption_Default ¦ 2025-12-27 | Assumption_Default | Low

## Inputs_User
Inputs_User — True Gaps / TBD Knobs (DG-TBD-xxxx)
User Inputs (placeholders)
DG_TBD_ID | Input_Name | Value | Unit | Status | Notes
DG-TBD-0001 | Debt Interest Rate (annual, nominal) | 6% | %/year | TBD | Not specified in SSOT; placeholder used for financing module.
DG-TBD-0002 | Max Debt LTC (Debt / Total Cost) | 60% | % | TBD | Not specified in SSOT; placeholder used for financing module.
DG-TBD-0003 | Tax on Profit at Exit (post-tax toggle) | 0% | % | TBD | Gate0 specifies pre-tax; set to 0% by default.
DG-TBD-0004 | Retail Net-to-Gross Efficiency | 90% | % | TBD | Not specified in SSOT; placeholder for rental valuation basis.

## ScenarioSelector
Scenario Selector
Select Concept: | C1
Selected Concept Name | C1
Inputs_User (TBD) summary
Debt interest (annual) | 6%
Max LTC | 60%
Tax on profit at exit | 0%
Retail net-to-gross | 90%

## Calc_Cashflow_Monthly
Calc_Cashflow_Monthly
Selected concept (driven by ScenarioSelector!B3): | C1
Line Item | Unit | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86
Outflow - Land | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Demolition | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124462.6209 | 322061.0328 | 212357.3463 | 0 | 0 | 0 | 0 | 0 | 0 | 124462.6209 | 322061.0328 | 212357.3463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Site | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435619.1731 | 1127213.6148 | 743250.712 | 0 | 0 | 0 | 0 | 0 | 0 | 435619.1731 | 1127213.6148 | 743250.712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - HardCost | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365678.955 | 365678.955 | 548518.4325 | 548518.4325 | 915844.59 | 915844.59 | 1281523.545 | 1281523.545 | 1647202.5 | 1890988.47 | 2256667.425 | 2256667.425 | 2561399.8875 | 2561399.8875 | 2561399.8875 | 2806283.9925 | 2623444.515 | 2623444.515 | 2501551.53 | 2501551.53 | 2135872.575 | 2379658.545 | 1465461.1575 | 1465461.1575 | 1341920.97 | 1341920.97 | 1341920.97 | 1463813.955 | 1463813.955 | 1463813.955 | 1463813.955 | 1463813.955 | 1463813.955 | 1341920.97 | 1341920.97 | 1341920.97 | 1098135 | 1098135 | 1098135 | 854349.03 | 854349.03 | 854349.03 | 244884.105 | 244884.105 | 244884.105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - SoftCost | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1089047.9329 | 2818034.037 | 1858126.7801 | 0 | 0 | 0 | 0 | 0 | 0 | 1089047.9329 | 2818034.037 | 1858126.7801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - PublicWorks | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21940.7373 | 21940.7373 | 32911.1059 | 32911.1059 | 54950.6754 | 54950.6754 | 76891.4127 | 76891.4127 | 98832.15 | 113459.3082 | 135400.0455 | 135400.0455 | 153683.9933 | 153683.9932 | 153683.9933 | 168377.0395 | 157406.6709 | 157406.6709 | 150093.0918 | 150093.0918 | 128152.3545 | 142779.5127 | 87927.6694 | 87927.6695 | 80515.2582 | 80515.2582 | 80515.2582 | 87828.8373 | 87828.8373 | 87828.8373 | 87828.8373 | 87828.8373 | 87828.8373 | 80515.2582 | 80515.2582 | 80515.2582 | 65888.1 | 65888.1 | 65888.1 | 51260.9418 | 51260.9418 | 51260.9418 | 14693.0463 | 14693.0463 | 14693.0463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - FinancingFees | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Contingency | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36567.8955 | 36567.8955 | 54851.8433 | 54851.8433 | 91584.459 | 91584.459 | 128152.3545 | 128152.3545 | 164720.25 | 189098.847 | 225666.7425 | 225666.7425 | 256139.9888 | 256139.9887 | 256139.9888 | 280628.3992 | 262344.4515 | 262344.4515 | 250155.153 | 250155.153 | 213587.2575 | 237965.8545 | 146546.1157 | 146546.1158 | 134192.097 | 134192.097 | 134192.097 | 146381.3955 | 146381.3955 | 146381.3955 | 146381.3955 | 146381.3955 | 146381.3955 | 134192.097 | 134192.097 | 134192.097 | 109813.5 | 109813.5 | 109813.5 | 85434.903 | 85434.903 | 85434.903 | 24488.4105 | 24488.4105 | 24488.4105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Outflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1649129.7269 | 4267308.6846 | 2813734.8385 | 424187.5878 | 424187.5878 | 636281.3817 | 636281.3817 | 1062379.7244 | 1062379.7244 | 3135697.0391 | 5753875.9968 | 4724489.7385 | 2193546.6252 | 2617734.213 | 2617734.213 | 2971223.8695 | 2971223.8695 | 2971223.8695 | 3255289.4313 | 3043195.6374 | 3043195.6374 | 2901799.7748 | 2901799.7748 | 2477612.187 | 2760403.9122 | 1699934.9427 | 1699934.9427 | 1556628.3252 | 1556628.3252 | 1556628.3252 | 1698024.1878 | 1698024.1878 | 1698024.1878 | 1698024.1878 | 1698024.1878 | 1698024.1878 | 1556628.3252 | 1556628.3252 | 1556628.3252 | 1273836.6 | 1273836.6 | 1273836.6 | 991044.8748 | 991044.8748 | 991044.8748 | 284065.5618 | 284065.5618 | 284065.5618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Res_Sales | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196144 | 392288 | 588432 | 980720 | 1373008 | 1765296 | 2157584 | 2353728 | 2549872 | 2746016 | 2353728 | 2157584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196144 | 392288 | 588432 | 980720 | 1373008 | 1765296 | 2157584 | 2353728 | 2549872 | 2746016 | 2353728 | 2157584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Res_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377035.4824 | 1336762.1647 | 1713797.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377035.4824 | 1336762.1647 | 1713797.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Office_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405780.375 | 1438675.875 | 1844456.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405780.375 | 1438675.875 | 1844456.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Retail_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439694.6778 | 1558917.494 | 1998612.1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439694.6778 | 1558917.494 | 1998612.1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Inflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196144 | 392288 | 588432 | 980720 | 1373008 | 1765296 | 2157584 | 2353728 | 2549872 | 2746016 | 2353728 | 2157584 | 1222510.5352 | 4334355.5337 | 5556866.0689 | 0 | 0 | 0 | 0 | 0 | 0 | 196144 | 392288 | 588432 | 980720 | 1373008 | 1765296 | 2157584 | 2353728 | 2549872 | 2746016 | 2353728 | 2157584 | 1222510.5352 | 4334355.5337 | 5556866.0689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Project Cashflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1649129.7269 | -4267308.6846 | -2813734.8385 | -424187.5878 | -424187.5878 | -636281.3817 | -636281.3817 | -1062379.7244 | -1062379.7244 | -3135697.0391 | -5753875.9968 | -4724489.7385 | -2193546.6252 | -2617734.213 | -2617734.213 | -2971223.8695 | -2971223.8695 | -2971223.8695 | -3255289.4313 | -3043195.6374 | -3043195.6374 | -2901799.7748 | -2901799.7748 | -2477612.187 | -2760403.9122 | -1699934.9427 | -1699934.9427 | -1360484.3252 | -1164340.3252 | -968196.3252 | -717304.1878 | -325016.1878 | 67271.8122 | 459559.8122 | 655703.8122 | 851847.8122 | 1189387.6748 | 797099.6748 | 600955.6748 | -51326.0648 | 3060518.9337 | 4283029.4689 | -991044.8748 | -991044.8748 | -991044.8748 | -284065.5618 | -284065.5618 | -284065.5618 | 196144 | 392288 | 588432 | 980720 | 1373008 | 1765296 | 2157584 | 2353728 | 2549872 | 2746016 | 2353728 | 2157584 | 1222510.5352 | 4334355.5337 | 5556866.0689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Project CF | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1649129.7269 | -5916438.4115 | -8730173.25 | -9154360.8378 | -9578548.4256 | -10214829.8073 | -10851111.189 | -11913490.9134 | -12975870.6378 | -16111567.6769 | -21865443.6737 | -26589933.4122 | -28783480.0374 | -31401214.2504 | -34018948.4634 | -36990172.3329 | -39961396.2024 | -42932620.0719 | -46187909.5032 | -49231105.1406 | -52274300.778 | -55176100.5528 | -58077900.3276 | -60555512.5146 | -63315916.4268 | -65015851.3695 | -66715786.3122 | -68076270.6374 | -69240610.9626 | -70208807.2878 | -70926111.4756 | -71251127.6634 | -71183855.8512 | -70724296.039 | -70068592.2268 | -69216744.4146 | -68027356.7398 | -67230257.065 | -66629301.3902 | -66680627.455 | -63620108.5213 | -59337079.0524 | -60328123.9272 | -61319168.802 | -62310213.6768 | -62594279.2386 | -62878344.8004 | -63162410.3622 | -62966266.3622 | -62573978.3622 | -61985546.3622 | -61004826.3622 | -59631818.3622 | -57866522.3622 | -55708938.3622 | -53355210.3622 | -50805338.3622 | -48059322.3622 | -45705594.3622 | -43548010.3622 | -42325499.827 | -37991144.2933 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244
Concept C1 (values)
Outflow - Land | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Demolition | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124462.6209 | 322061.0328 | 212357.3463 | 0 | 0 | 0 | 0 | 0 | 0 | 124462.6209 | 322061.0328 | 212357.3463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Site | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435619.1731 | 1127213.6148 | 743250.712 | 0 | 0 | 0 | 0 | 0 | 0 | 435619.1731 | 1127213.6148 | 743250.712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - HardCost | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365678.955 | 365678.955 | 548518.4325 | 548518.4325 | 915844.59 | 915844.59 | 1281523.545 | 1281523.545 | 1647202.5 | 1890988.47 | 2256667.425 | 2256667.425 | 2561399.8875 | 2561399.8875 | 2561399.8875 | 2806283.9925 | 2623444.515 | 2623444.515 | 2501551.53 | 2501551.53 | 2135872.575 | 2379658.545 | 1465461.1575 | 1465461.1575 | 1341920.97 | 1341920.97 | 1341920.97 | 1463813.955 | 1463813.955 | 1463813.955 | 1463813.955 | 1463813.955 | 1463813.955 | 1341920.97 | 1341920.97 | 1341920.97 | 1098135 | 1098135 | 1098135 | 854349.03 | 854349.03 | 854349.03 | 244884.105 | 244884.105 | 244884.105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - SoftCost | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1089047.9329 | 2818034.037 | 1858126.7801 | 0 | 0 | 0 | 0 | 0 | 0 | 1089047.9329 | 2818034.037 | 1858126.7801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - PublicWorks | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21940.7373 | 21940.7373 | 32911.1059 | 32911.1059 | 54950.6754 | 54950.6754 | 76891.4127 | 76891.4127 | 98832.15 | 113459.3082 | 135400.0455 | 135400.0455 | 153683.9933 | 153683.9932 | 153683.9933 | 168377.0395 | 157406.6709 | 157406.6709 | 150093.0918 | 150093.0918 | 128152.3545 | 142779.5127 | 87927.6694 | 87927.6695 | 80515.2582 | 80515.2582 | 80515.2582 | 87828.8373 | 87828.8373 | 87828.8373 | 87828.8373 | 87828.8373 | 87828.8373 | 80515.2582 | 80515.2582 | 80515.2582 | 65888.1 | 65888.1 | 65888.1 | 51260.9418 | 51260.9418 | 51260.9418 | 14693.0463 | 14693.0463 | 14693.0463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - FinancingFees | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Contingency | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36567.8955 | 36567.8955 | 54851.8433 | 54851.8433 | 91584.459 | 91584.459 | 128152.3545 | 128152.3545 | 164720.25 | 189098.847 | 225666.7425 | 225666.7425 | 256139.9888 | 256139.9887 | 256139.9888 | 280628.3992 | 262344.4515 | 262344.4515 | 250155.153 | 250155.153 | 213587.2575 | 237965.8545 | 146546.1157 | 146546.1158 | 134192.097 | 134192.097 | 134192.097 | 146381.3955 | 146381.3955 | 146381.3955 | 146381.3955 | 146381.3955 | 146381.3955 | 134192.097 | 134192.097 | 134192.097 | 109813.5 | 109813.5 | 109813.5 | 85434.903 | 85434.903 | 85434.903 | 24488.4105 | 24488.4105 | 24488.4105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Outflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1649129.7269 | 4267308.6846 | 2813734.8385 | 424187.5878 | 424187.5878 | 636281.3817 | 636281.3817 | 1062379.7244 | 1062379.7244 | 3135697.0391 | 5753875.9968 | 4724489.7385 | 2193546.6252 | 2617734.213 | 2617734.213 | 2971223.8695 | 2971223.8695 | 2971223.8695 | 3255289.4313 | 3043195.6374 | 3043195.6374 | 2901799.7748 | 2901799.7748 | 2477612.187 | 2760403.9122 | 1699934.9427 | 1699934.9427 | 1556628.3252 | 1556628.3252 | 1556628.3252 | 1698024.1878 | 1698024.1878 | 1698024.1878 | 1698024.1878 | 1698024.1878 | 1698024.1878 | 1556628.3252 | 1556628.3252 | 1556628.3252 | 1273836.6 | 1273836.6 | 1273836.6 | 991044.8748 | 991044.8748 | 991044.8748 | 284065.5618 | 284065.5618 | 284065.5618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Res_Sales | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196144 | 392288 | 588432 | 980720 | 1373008 | 1765296 | 2157584 | 2353728 | 2549872 | 2746016 | 2353728 | 2157584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196144 | 392288 | 588432 | 980720 | 1373008 | 1765296 | 2157584 | 2353728 | 2549872 | 2746016 | 2353728 | 2157584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Res_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377035.4824 | 1336762.1647 | 1713797.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377035.4824 | 1336762.1647 | 1713797.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Office_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405780.375 | 1438675.875 | 1844456.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405780.375 | 1438675.875 | 1844456.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Retail_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439694.6778 | 1558917.494 | 1998612.1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439694.6778 | 1558917.494 | 1998612.1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Inflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196144 | 392288 | 588432 | 980720 | 1373008 | 1765296 | 2157584 | 2353728 | 2549872 | 2746016 | 2353728 | 2157584 | 1222510.5352 | 4334355.5337 | 5556866.0689 | 0 | 0 | 0 | 0 | 0 | 0 | 196144 | 392288 | 588432 | 980720 | 1373008 | 1765296 | 2157584 | 2353728 | 2549872 | 2746016 | 2353728 | 2157584 | 1222510.5352 | 4334355.5337 | 5556866.0689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Project Cashflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1649129.7269 | -4267308.6846 | -2813734.8385 | -424187.5878 | -424187.5878 | -636281.3817 | -636281.3817 | -1062379.7244 | -1062379.7244 | -3135697.0391 | -5753875.9968 | -4724489.7385 | -2193546.6252 | -2617734.213 | -2617734.213 | -2971223.8695 | -2971223.8695 | -2971223.8695 | -3255289.4313 | -3043195.6374 | -3043195.6374 | -2901799.7748 | -2901799.7748 | -2477612.187 | -2760403.9122 | -1699934.9427 | -1699934.9427 | -1360484.3252 | -1164340.3252 | -968196.3252 | -717304.1878 | -325016.1878 | 67271.8122 | 459559.8122 | 655703.8122 | 851847.8122 | 1189387.6748 | 797099.6748 | 600955.6748 | -51326.0648 | 3060518.9337 | 4283029.4689 | -991044.8748 | -991044.8748 | -991044.8748 | -284065.5618 | -284065.5618 | -284065.5618 | 196144 | 392288 | 588432 | 980720 | 1373008 | 1765296 | 2157584 | 2353728 | 2549872 | 2746016 | 2353728 | 2157584 | 1222510.5352 | 4334355.5337 | 5556866.0689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Project CF | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1649129.7269 | -5916438.4115 | -8730173.25 | -9154360.8378 | -9578548.4256 | -10214829.8073 | -10851111.189 | -11913490.9134 | -12975870.6378 | -16111567.6769 | -21865443.6737 | -26589933.4122 | -28783480.0374 | -31401214.2504 | -34018948.4634 | -36990172.3329 | -39961396.2024 | -42932620.0719 | -46187909.5032 | -49231105.1406 | -52274300.778 | -55176100.5528 | -58077900.3276 | -60555512.5146 | -63315916.4268 | -65015851.3695 | -66715786.3122 | -68076270.6374 | -69240610.9626 | -70208807.2878 | -70926111.4756 | -71251127.6634 | -71183855.8512 | -70724296.039 | -70068592.2268 | -69216744.4146 | -68027356.7398 | -67230257.065 | -66629301.3902 | -66680627.455 | -63620108.5213 | -59337079.0524 | -60328123.9272 | -61319168.802 | -62310213.6768 | -62594279.2386 | -62878344.8004 | -63162410.3622 | -62966266.3622 | -62573978.3622 | -61985546.3622 | -61004826.3622 | -59631818.3622 | -57866522.3622 | -55708938.3622 | -53355210.3622 | -50805338.3622 | -48059322.3622 | -45705594.3622 | -43548010.3622 | -42325499.827 | -37991144.2933 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244 | -32434278.2244
Concept C2 (values)
Outflow - Land | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Demolition | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98663.15 | 255301.9997 | 168338.4503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150705.2512 | 389966.7907 | 257132.3581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Site | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345321.0251 | 893556.9989 | 589184.576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527468.3791 | 1364883.7675 | 899963.2534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - HardCost | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193252.332 | 193252.332 | 193252.332 | 289878.498 | 289878.498 | 289878.498 | 484001.336 | 484001.336 | 484001.336 | 677253.668 | 677253.668 | 677253.668 | 870506 | 870506 | 870506 | 1063758.332 | 1063758.332 | 1063758.332 | 1160384.498 | 1160384.498 | 1160384.498 | 1455572.126 | 1455572.126 | 1455572.126 | 1506539.774 | 1506539.774 | 1506539.774 | 1609804.744 | 1609804.744 | 1609804.744 | 1711740.04 | 1711740.04 | 1711740.04 | 1523796.838 | 1523796.838 | 1523796.838 | 1624861.628 | 1624861.628 | 1624861.628 | 1772455.442 | 1772455.442 | 1772455.442 | 1772455.442 | 1772455.442 | 1772455.442 | 1624861.628 | 1624861.628 | 1624861.628 | 1329674 | 1329674 | 1329674 | 1034486.372 | 1034486.372 | 1034486.372 | 296517.302 | 296517.302 | 296517.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - SoftCost | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863302.5628 | 2233892.4972 | 1472961.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318670.9476 | 3412209.4188 | 2249908.1335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - PublicWorks | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11595.1399 | 11595.1399 | 11595.1399 | 17392.7099 | 17392.7099 | 17392.7099 | 29040.0802 | 29040.0802 | 29040.0802 | 40635.2201 | 40635.2201 | 40635.2201 | 52230.36 | 52230.36 | 52230.36 | 63825.4999 | 63825.4999 | 63825.4999 | 69623.0699 | 69623.0699 | 69623.0699 | 87334.3276 | 87334.3276 | 87334.3276 | 90392.3864 | 90392.3864 | 90392.3864 | 96588.2846 | 96588.2846 | 96588.2846 | 102704.4024 | 102704.4024 | 102704.4024 | 91427.8103 | 91427.8103 | 91427.8103 | 97491.6977 | 97491.6977 | 97491.6977 | 106347.3265 | 106347.3265 | 106347.3265 | 106347.3265 | 106347.3265 | 106347.3265 | 97491.6977 | 97491.6977 | 97491.6977 | 79780.44 | 79780.44 | 79780.44 | 62069.1823 | 62069.1823 | 62069.1823 | 17791.0381 | 17791.0381 | 17791.0381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - FinancingFees | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Contingency | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19325.2332 | 19325.2332 | 19325.2332 | 28987.8498 | 28987.8498 | 28987.8498 | 48400.1336 | 48400.1336 | 48400.1336 | 67725.3668 | 67725.3668 | 67725.3668 | 87050.6 | 87050.6 | 87050.6 | 106375.8332 | 106375.8332 | 106375.8332 | 116038.4498 | 116038.4498 | 116038.4498 | 145557.2126 | 145557.2126 | 145557.2126 | 150653.9774 | 150653.9774 | 150653.9774 | 160980.4744 | 160980.4744 | 160980.4744 | 171174.004 | 171174.004 | 171174.004 | 152379.6838 | 152379.6838 | 152379.6838 | 162486.1628 | 162486.1628 | 162486.1628 | 177245.5442 | 177245.5442 | 177245.5442 | 177245.5442 | 177245.5442 | 177245.5442 | 162486.1628 | 162486.1628 | 162486.1628 | 132967.4 | 132967.4 | 132967.4 | 103448.6372 | 103448.6372 | 103448.6372 | 29651.7302 | 29651.7302 | 29651.7302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Outflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307286.738 | 3382751.4958 | 2230484.4662 | 224172.7051 | 224172.7051 | 224172.7051 | 336259.0577 | 336259.0577 | 336259.0577 | 561441.5498 | 561441.5498 | 561441.5498 | 785614.2549 | 785614.2549 | 785614.2549 | 1009786.96 | 1009786.96 | 1009786.96 | 1233959.6651 | 1233959.6651 | 1233959.6651 | 3342890.5956 | 6513105.9947 | 4753049.7628 | 1688463.6662 | 1688463.6662 | 1688463.6662 | 1747586.1378 | 1747586.1378 | 1747586.1378 | 1867373.503 | 1867373.503 | 1867373.503 | 1985618.4464 | 1985618.4464 | 1985618.4464 | 1767604.3321 | 1767604.3321 | 1767604.3321 | 1884839.4885 | 1884839.4885 | 1884839.4885 | 2056048.3127 | 2056048.3127 | 2056048.3127 | 2056048.3127 | 2056048.3127 | 2056048.3127 | 1884839.4885 | 1884839.4885 | 1884839.4885 | 1542421.84 | 1542421.84 | 1542421.84 | 1200004.1915 | 1200004.1915 | 1200004.1915 | 343960.0703 | 343960.0703 | 343960.0703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Res_Sales | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95513.6 | 191027.2 | 286540.8 | 477568 | 668595.2 | 859622.4 | 1050649.6 | 1146163.2 | 1241676.8 | 1337190.4 | 1146163.2 | 1050649.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145894.4 | 291788.8 | 437683.2 | 729472 | 1021260.8 | 1313049.6 | 1604838.4 | 1750732.8 | 1896627.2 | 2042521.6 | 1750732.8 | 1604838.4 | 0 | 0 | 0
Inflow - Res_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183599.8871 | 650945.0541 | 834544.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280443.7835 | 994300.6871 | 1274744.4706
Inflow - Office_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642191.55 | 2276860.95 | 2919052.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980929.95 | 3477842.55 | 4458772.5
Inflow - Retail_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 463909.747 | 1644770.9212 | 2108680.6683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708609.3938 | 2512342.3962 | 3220951.79
Total Inflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95513.6 | 191027.2 | 286540.8 | 477568 | 668595.2 | 859622.4 | 1050649.6 | 1146163.2 | 1241676.8 | 1337190.4 | 1146163.2 | 1050649.6 | 1289701.1841 | 4572576.9254 | 5862278.1094 | 0 | 0 | 0 | 0 | 0 | 0 | 145894.4 | 291788.8 | 437683.2 | 729472 | 1021260.8 | 1313049.6 | 1604838.4 | 1750732.8 | 1896627.2 | 2042521.6 | 1750732.8 | 1604838.4 | 1969983.1273 | 6984485.6332 | 8954468.7606
Net Project Cashflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1307286.738 | -3382751.4958 | -2230484.4662 | -224172.7051 | -224172.7051 | -224172.7051 | -336259.0577 | -336259.0577 | -336259.0577 | -561441.5498 | -561441.5498 | -561441.5498 | -785614.2549 | -785614.2549 | -785614.2549 | -1009786.96 | -1009786.96 | -1009786.96 | -1233959.6651 | -1233959.6651 | -1233959.6651 | -3342890.5956 | -6513105.9947 | -4753049.7628 | -1688463.6662 | -1688463.6662 | -1688463.6662 | -1747586.1378 | -1747586.1378 | -1747586.1378 | -1867373.503 | -1867373.503 | -1867373.503 | -1985618.4464 | -1985618.4464 | -1985618.4464 | -1767604.3321 | -1767604.3321 | -1767604.3321 | -1789325.8885 | -1693812.2885 | -1598298.6885 | -1578480.3127 | -1387453.1127 | -1196425.9127 | -1005398.7127 | -909885.1127 | -814371.5127 | -547649.0885 | -738676.2885 | -834189.8885 | -252720.6559 | 3030155.0854 | 4319856.2694 | -1200004.1915 | -1200004.1915 | -1200004.1915 | -343960.0703 | -343960.0703 | -343960.0703 | 145894.4 | 291788.8 | 437683.2 | 729472 | 1021260.8 | 1313049.6 | 1604838.4 | 1750732.8 | 1896627.2 | 2042521.6 | 1750732.8 | 1604838.4 | 1969983.1273 | 6984485.6332 | 8954468.7606
Cumulative Project CF | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1307286.738 | -4690038.2338 | -6920522.7 | -7144695.4051 | -7368868.1102 | -7593040.8154 | -7929299.873 | -8265558.9307 | -8601817.9884 | -9163259.5382 | -9724701.0879 | -10286142.6377 | -11071756.8926 | -11857371.1474 | -12642985.4023 | -13652772.3623 | -14662559.3223 | -15672346.2823 | -16906305.9474 | -18140265.6126 | -19374225.2777 | -22717115.8732 | -29230221.8679 | -33983271.6307 | -35671735.2969 | -37360198.963 | -39048662.6292 | -40796248.767 | -42543834.9049 | -44291421.0427 | -46158794.5458 | -48026168.0488 | -49893541.5518 | -51879159.9982 | -53864778.4446 | -55850396.891 | -57618001.2231 | -59385605.5552 | -61153209.8873 | -62942535.7758 | -64636348.0642 | -66234646.7527 | -67813127.0654 | -69200580.1782 | -70397006.0909 | -71402404.8036 | -72312289.9163 | -73126661.429 | -73674310.5175 | -74412986.806 | -75247176.6945 | -75499897.3504 | -72469742.265 | -68149885.9956 | -69349890.1871 | -70549894.3787 | -71749898.5702 | -72093858.6405 | -72437818.7108 | -72781778.7811 | -72635884.3811 | -72344095.5811 | -71906412.3811 | -71176940.3811 | -70155679.5811 | -68842629.9811 | -67237791.5811 | -65487058.7811 | -63590431.5811 | -61547909.9811 | -59797177.1811 | -58192338.7811 | -56222355.6538 | -49237870.0206 | -40283401.26
Concept C3 (values)
Outflow - Land | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Demolition | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101665.98 | 263072.16 | 173461.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152498.97 | 394608.24 | 260192.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Site | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355830.93 | 920752.56 | 607116.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 533746.395 | 1381128.84 | 910674.765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - HardCost | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199134 | 199134 | 199134 | 298701 | 298701 | 298701 | 498732 | 498732 | 498732 | 697866 | 697866 | 697866 | 897000 | 897000 | 897000 | 1096134 | 1096134 | 1096134 | 1195701 | 1195701 | 1195701 | 1643752.5 | 1643752.5 | 1867778.25 | 1768211.25 | 2218281 | 2218281 | 2467198.5 | 2467198.5 | 2915250 | 2716116 | 3164167.5 | 3164167.5 | 2890358.25 | 2890358.25 | 2890358.25 | 2690327.25 | 2466301.5 | 2466301.5 | 2018250 | 2018250 | 1570198.5 | 1570198.5 | 450069.75 | 450069.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - SoftCost | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 889577.325 | 2301881.4 | 1517791.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1334365.9875 | 3452822.1 | 2276686.9125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - PublicWorks | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11948.04 | 11948.04 | 11948.04 | 17922.06 | 17922.06 | 17922.06 | 29923.92 | 29923.92 | 29923.92 | 41871.96 | 41871.96 | 41871.96 | 53820 | 53820 | 53820 | 65768.04 | 65768.04 | 65768.04 | 71742.06 | 71742.06 | 71742.06 | 98625.15 | 98625.15 | 112066.695 | 106092.675 | 133096.86 | 133096.86 | 148031.91 | 148031.91 | 174915 | 162966.96 | 189850.05 | 189850.05 | 173421.495 | 173421.495 | 173421.495 | 161419.635 | 147978.09 | 147978.09 | 121095 | 121095 | 94211.91 | 94211.91 | 27004.185 | 27004.185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - FinancingFees | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outflow - Contingency | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19913.4 | 19913.4 | 19913.4 | 29870.1 | 29870.1 | 29870.1 | 49873.2 | 49873.2 | 49873.2 | 69786.6 | 69786.6 | 69786.6 | 89700 | 89700 | 89700 | 109613.4 | 109613.4 | 109613.4 | 119570.1 | 119570.1 | 119570.1 | 164375.25 | 164375.25 | 186777.825 | 176821.125 | 221828.1 | 221828.1 | 246719.85 | 246719.85 | 291525 | 271611.6 | 316416.75 | 316416.75 | 289035.825 | 289035.825 | 289035.825 | 269032.725 | 246630.15 | 246630.15 | 201825 | 201825 | 157019.85 | 157019.85 | 45006.975 | 45006.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Outflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1347074.235 | 3485706.12 | 2298369.645 | 230995.44 | 230995.44 | 230995.44 | 346493.16 | 346493.16 | 346493.16 | 578529.12 | 578529.12 | 578529.12 | 809524.56 | 809524.56 | 809524.56 | 1040520 | 1040520 | 1040520 | 1271515.44 | 1271515.44 | 1271515.44 | 3407624.5125 | 6615572.34 | 4834567.6275 | 1906752.9 | 1906752.9 | 2166622.77 | 2051125.05 | 2573205.96 | 2573205.96 | 2861950.26 | 2861950.26 | 3381690 | 3150694.56 | 3670434.3 | 3670434.3 | 3352815.57 | 3352815.57 | 3352815.57 | 3120779.61 | 2860909.74 | 2860909.74 | 2341170 | 2341170 | 1821430.26 | 1821430.26 | 522080.91 | 522080.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Res_Sales | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120704 | 241408 | 362112 | 603520 | 844928 | 1086336 | 1327744 | 1448448 | 1569152 | 1870912 | 1810560 | 1870912 | 905280 | 1267392 | 1629504 | 1991616 | 2172672 | 2353728 | 2534784 | 2172672 | 1991616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Res_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232021.8353 | 822622.8706 | 1054644.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 348032.7529 | 1233934.3059 | 1581967.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Office_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649248.6 | 2301881.4 | 2951130 | 0 | 0 | 0 | 0 | 0 | 0 | 973872.9 | 3452822.1 | 4426695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflow - Retail_Rent | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234503.8282 | 831422.6635 | 1065926.4916 | 0 | 0 | 0 | 0 | 0 | 0 | 351755.7422 | 1247133.9952 | 1598889.7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Inflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120704 | 241408 | 362112 | 603520 | 844928 | 1086336 | 1327744 | 1448448 | 1569152 | 1870912 | 1810560 | 1870912 | 2021054.2635 | 5223318.9341 | 6701205.1975 | 1991616 | 2172672 | 2353728 | 2534784 | 2172672 | 1991616 | 1673661.3952 | 5933890.4011 | 7607551.7963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Project Cashflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1347074.235 | -3485706.12 | -2298369.645 | -230995.44 | -230995.44 | -230995.44 | -346493.16 | -346493.16 | -346493.16 | -578529.12 | -578529.12 | -578529.12 | -809524.56 | -809524.56 | -809524.56 | -1040520 | -1040520 | -1040520 | -1271515.44 | -1271515.44 | -1271515.44 | -3407624.5125 | -6615572.34 | -4834567.6275 | -1906752.9 | -1906752.9 | -2166622.77 | -2051125.05 | -2573205.96 | -2573205.96 | -2861950.26 | -2861950.26 | -3381690 | -3150694.56 | -3670434.3 | -3670434.3 | -3352815.57 | -3352815.57 | -3352815.57 | -3000075.61 | -2619501.74 | -2498797.74 | -1737650 | -1496242 | -735094.26 | -493686.26 | 926367.09 | 1047071.09 | 1870912 | 1810560 | 1870912 | 2021054.2635 | 5223318.9341 | 6701205.1975 | 1991616 | 2172672 | 2353728 | 2534784 | 2172672 | 1991616 | 1673661.3952 | 5933890.4011 | 7607551.7963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Project CF | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1347074.235 | -4832780.355 | -7131150 | -7362145.44 | -7593140.88 | -7824136.32 | -8170629.48 | -8517122.64 | -8863615.8 | -9442144.92 | -10020674.04 | -10599203.16 | -11408727.72 | -12218252.28 | -13027776.84 | -14068296.84 | -15108816.84 | -16149336.84 | -17420852.28 | -18692367.72 | -19963883.16 | -23371507.6725 | -29987080.0125 | -34821647.64 | -36728400.54 | -38635153.44 | -40801776.21 | -42852901.26 | -45426107.22 | -47999313.18 | -50861263.44 | -53723213.7 | -57104903.7 | -60255598.26 | -63926032.56 | -67596466.86 | -70949282.43 | -74302098 | -77654913.57 | -80654989.18 | -83274490.92 | -85773288.66 | -87510938.66 | -89007180.66 | -89742274.92 | -90235961.18 | -89309594.09 | -88262523 | -86391611 | -84581051 | -82710139 | -80689084.7365 | -75465765.8025 | -68764560.6049 | -66772944.6049 | -64600272.6049 | -62246544.6049 | -59711760.6049 | -57539088.6049 | -55547472.6049 | -53873811.2098 | -47939920.8086 | -40332369.0124 | -40332369.0124 | -40332369.0124 | -40332369.0124 | -40332369.0124 | -40332369.0124 | -40332369.0124 | -40332369.0124 | -40332369.0124 | -40332369.0124 | -40332369.0124 | -40332369.0124 | -40332369.0124

## Calc_Financing
Calc_Financing
Selected concept: | C1
Line Item | Unit | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86
Debt Draw | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1649129.7269 | 4275335.9069 | 2842572.4745 | 466861.5891 | 469134.0615 | 683511.3892 | 686838.4154 | 1116279.9788 | 1121713.5281 | 3200490.8401 | 5834248.3488 | 4833260.5893 | 2325843.6163 | 2761352.3656 | 2774793.3878 | 3141789.4914 | 3157082.3107 | 3172449.5684 | 3471957.1889 | 3276763.3222 | 3292713.1334 | 1780204.2666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311219.3987 | 0 | 0 | 1219186.5075 | 1225120.9595 | 1231084.2977 | 530097.3498 | 532677.6255 | 535270.4607 | 57666.355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120027.2651 | 120611.5039 | 121198.5865 | 121788.5267 | 122381.3385 | 122977.0359 | 123575.6328 | 124177.1435 | 124781.582 | 125388.9627 | 125999.2998 | 126612.6077
Debt Repay | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185349.6343 | 382395.833 | 580401.164 | 920766.1586 | 532960.0345 | 339410.2444 | 0 | 2799110.7237 | 4035246.0719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138196.9511 | 335013.6318 | 728932.3276 | 1124768.4425 | 1522531.3098 | 1922230.3079 | 2127730.8612 | 2334231.6987 | 2541737.6895 | 2161821.7263 | 1976200.5028 | 1050746.2939 | 4167705.8532 | 5410502.9073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26138177.5718
Interest | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8027.2223 | 28837.636 | 42674.0013 | 44946.4737 | 47230.0075 | 50557.0337 | 53900.2544 | 59333.8037 | 64793.801 | 80372.352 | 108770.8508 | 132296.9911 | 143618.1526 | 157059.1748 | 170565.6219 | 185858.4412 | 201225.6989 | 216667.7576 | 233567.6848 | 249517.496 | 265544.9437 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 273307.9792 | 271446.6482 | 268621.5162 | 264139.6403 | 261545.4304 | 259893.3339 | 261408.21 | 247783.397 | 228141.6327 | 234076.0847 | 240039.4229 | 246031.788 | 248612.0637 | 251204.8989 | 253810.355 | 254091.0489 | 253418.3682 | 251787.6724 | 248239.5575 | 242764.6902 | 235353.6921 | 225997.1388 | 215640.3013 | 204278.3105 | 191906.2737 | 181383.4972 | 171764.2413 | 166649.6806 | 146363.1616 | 120027.2651 | 120611.5039 | 121198.5865 | 121788.5267 | 122381.3385 | 122977.0359 | 123575.6328 | 124177.1435 | 124781.582 | 125388.9627 | 125999.2998 | 126612.6077
Debt Balance | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1649129.7269 | 5924465.6339 | 8767038.1084 | 9233899.6975 | 9703033.759 | 10386545.1481 | 11073383.5635 | 12189663.5424 | 13311377.0704 | 16511867.9105 | 22346116.2593 | 27179376.8486 | 29505220.465 | 32266572.8305 | 35041366.2184 | 38183155.7098 | 41340238.0205 | 44512687.5889 | 47984644.7778 | 51261408.1001 | 54554121.2334 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56148975.8657 | 55766580.0328 | 55186178.8687 | 54265412.7101 | 53732452.6756 | 53393042.4312 | 53704261.8299 | 50905151.1062 | 46869905.0343 | 48089091.5419 | 49314212.5014 | 50545296.7992 | 51075394.149 | 51608071.7744 | 52143342.2352 | 52201008.5901 | 52062811.639 | 51727798.0072 | 50998865.6797 | 49874097.2371 | 48351565.9274 | 46429335.6194 | 44301604.7583 | 41967373.0595 | 39425635.37 | 37263813.6437 | 35287613.1409 | 34236866.847 | 30069160.9939 | 24658658.0866 | 24778685.3517 | 24899296.8556 | 25020495.4421 | 25142283.9688 | 25264665.3074 | 25387642.3433 | 25511217.9761 | 25635395.1196 | 25760176.7016 | 25885565.6642 | 26011564.964 | 0
Equity Cashflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1387140.4519 | -3176009.9527 | -2751822.3649 | -3034614.0901 | -1974145.1206 | -1974145.1206 | -1634694.5031 | -1438550.5031 | -1242406.5031 | -991514.3657 | -599226.3657 | -206938.3657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26138177.5718
Cumulative Equity CF | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1387140.4519 | -4563150.4046 | -7314972.7696 | -10349586.8597 | -12323731.9803 | -14297877.101 | -15932571.6041 | -17371122.1072 | -18613528.6104 | -19605042.9761 | -20204269.3419 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -46549385.2794
Concept C1 (values)
Debt Draw | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1649129.7269 | 4275335.9069 | 2842572.4745 | 466861.5891 | 469134.0615 | 683511.3892 | 686838.4154 | 1116279.9788 | 1121713.5281 | 3200490.8401 | 5834248.3488 | 4833260.5893 | 2325843.6163 | 2761352.3656 | 2774793.3878 | 3141789.4914 | 3157082.3107 | 3172449.5684 | 3471957.1889 | 3276763.3222 | 3292713.1334 | 1780204.2666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311219.3987 | 0 | 0 | 1219186.5075 | 1225120.9595 | 1231084.2977 | 530097.3498 | 532677.6255 | 535270.4607 | 57666.355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120027.2651 | 120611.5039 | 121198.5865 | 121788.5267 | 122381.3385 | 122977.0359 | 123575.6328 | 124177.1435 | 124781.582 | 125388.9627 | 125999.2998 | 126612.6077
Debt Repay | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185349.6343 | 382395.833 | 580401.164 | 920766.1586 | 532960.0345 | 339410.2444 | 0 | 2799110.7237 | 4035246.0719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138196.9511 | 335013.6318 | 728932.3276 | 1124768.4425 | 1522531.3098 | 1922230.3079 | 2127730.8612 | 2334231.6987 | 2541737.6895 | 2161821.7263 | 1976200.5028 | 1050746.2939 | 4167705.8532 | 5410502.9073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26138177.5718
Interest | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8027.2223 | 28837.636 | 42674.0013 | 44946.4737 | 47230.0075 | 50557.0337 | 53900.2544 | 59333.8037 | 64793.801 | 80372.352 | 108770.8508 | 132296.9911 | 143618.1526 | 157059.1748 | 170565.6219 | 185858.4412 | 201225.6989 | 216667.7576 | 233567.6848 | 249517.496 | 265544.9437 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 274210.1779 | 273307.9792 | 271446.6482 | 268621.5162 | 264139.6403 | 261545.4304 | 259893.3339 | 261408.21 | 247783.397 | 228141.6327 | 234076.0847 | 240039.4229 | 246031.788 | 248612.0637 | 251204.8989 | 253810.355 | 254091.0489 | 253418.3682 | 251787.6724 | 248239.5575 | 242764.6902 | 235353.6921 | 225997.1388 | 215640.3013 | 204278.3105 | 191906.2737 | 181383.4972 | 171764.2413 | 166649.6806 | 146363.1616 | 120027.2651 | 120611.5039 | 121198.5865 | 121788.5267 | 122381.3385 | 122977.0359 | 123575.6328 | 124177.1435 | 124781.582 | 125388.9627 | 125999.2998 | 126612.6077
Debt Balance | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1649129.7269 | 5924465.6339 | 8767038.1084 | 9233899.6975 | 9703033.759 | 10386545.1481 | 11073383.5635 | 12189663.5424 | 13311377.0704 | 16511867.9105 | 22346116.2593 | 27179376.8486 | 29505220.465 | 32266572.8305 | 35041366.2184 | 38183155.7098 | 41340238.0205 | 44512687.5889 | 47984644.7778 | 51261408.1001 | 54554121.2334 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56334325.5 | 56148975.8657 | 55766580.0328 | 55186178.8687 | 54265412.7101 | 53732452.6756 | 53393042.4312 | 53704261.8299 | 50905151.1062 | 46869905.0343 | 48089091.5419 | 49314212.5014 | 50545296.7992 | 51075394.149 | 51608071.7744 | 52143342.2352 | 52201008.5901 | 52062811.639 | 51727798.0072 | 50998865.6797 | 49874097.2371 | 48351565.9274 | 46429335.6194 | 44301604.7583 | 41967373.0595 | 39425635.37 | 37263813.6437 | 35287613.1409 | 34236866.847 | 30069160.9939 | 24658658.0866 | 24778685.3517 | 24899296.8556 | 25020495.4421 | 25142283.9688 | 25264665.3074 | 25387642.3433 | 25511217.9761 | 25635395.1196 | 25760176.7016 | 25885565.6642 | 26011564.964 | 0
Equity Cashflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1387140.4519 | -3176009.9527 | -2751822.3649 | -3034614.0901 | -1974145.1206 | -1974145.1206 | -1634694.5031 | -1438550.5031 | -1242406.5031 | -991514.3657 | -599226.3657 | -206938.3657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26138177.5718
Cumulative Equity CF | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1387140.4519 | -4563150.4046 | -7314972.7696 | -10349586.8597 | -12323731.9803 | -14297877.101 | -15932571.6041 | -17371122.1072 | -18613528.6104 | -19605042.9761 | -20204269.3419 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -20411207.7076 | -46549385.2794
Concept C2 (values)
Debt Draw | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307286.738 | 3389114.7801 | 2253344.4381 | 258000.945 | 259256.7776 | 260518.7231 | 373873.1637 | 375693.0102 | 377521.715 | 604541.8131 | 607484.4509 | 610441.4122 | 837585.4718 | 841662.4614 | 845759.296 | 1074048.7773 | 1079276.764 | 1084530.1982 | 1313981.9089 | 1320377.7823 | 1326804.7879 | 3442194.0077 | 6629164.4603 | 4901376.0216 | 1860647.6206 | 1869704.417 | 1878805.2978 | 1947072.9492 | 1956550.4253 | 1966074.0334 | 2095431.3634 | 2105630.9815 | 2115880.2468 | 2244424.3442 | 1020555.4166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1441534.9225 | 1448551.6667 | 1455602.5652 | 606643.663 | 609596.5317 | 612563.7737 | 125690.9885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Debt Repay | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755456.7335 | 4058570.2425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19591.6042 | 165581.3674 | 458176.143 | 752195.1386 | 1047645.2865 | 1344533.5529 | 1496972.5379 | 1650153.5274 | 1804080.1332 | 1521072.7845 | 1382582.2831 | 1754456.7996 | 6777499.2127 | 35746233.7642
Interest | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6363.2843 | 22859.9719 | 33828.2399 | 35084.0725 | 36346.018 | 37614.106 | 39433.9526 | 41262.6573 | 43100.2633 | 46042.9012 | 48999.8625 | 51971.2169 | 56048.2065 | 60145.0411 | 64261.8173 | 69489.804 | 74743.2382 | 80022.2438 | 86418.1172 | 92845.1228 | 99303.4122 | 116058.4656 | 148326.2588 | 172183.9544 | 181240.7508 | 190341.6316 | 199486.8114 | 208964.2874 | 218487.8955 | 228057.8603 | 238257.4784 | 248506.7437 | 258805.8978 | 269730.7468 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 274698.3519 | 261286.0269 | 241530.731 | 248547.4752 | 255598.3736 | 262683.5927 | 265636.4614 | 268603.7034 | 271585.3885 | 272197.1958 | 272101.8326 | 271295.857 | 269065.6614 | 265404.3135 | 260304.8471 | 253760.2621 | 246473.6726 | 238441.4668 | 229660.0155 | 222256.1169 | 215526.3277 | 206986.4205 | 173996.6004
Debt Balance | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307286.738 | 4696401.5181 | 6949745.9562 | 7207746.9011 | 7467003.6788 | 7727522.4019 | 8101395.5656 | 8477088.5758 | 8854610.2908 | 9459152.1039 | 10066636.5548 | 10677077.967 | 11514663.4388 | 12356325.9002 | 13202085.1962 | 14276133.9735 | 15355410.7375 | 16439940.9357 | 17753922.8446 | 19074300.6269 | 20401105.4148 | 23843299.4226 | 30472463.8829 | 35373839.9044 | 37234487.525 | 39104191.942 | 40982997.2397 | 42930070.189 | 44886620.6142 | 46852694.6476 | 48948126.011 | 51053756.9924 | 53169637.2392 | 55414061.5834 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 56434617 | 53679160.2665 | 49620590.024 | 51062124.9465 | 52510676.6132 | 53966279.1784 | 54572922.8414 | 55182519.3732 | 55795083.1468 | 55920774.1354 | 55901182.5311 | 55735601.1638 | 55277425.0207 | 54525229.8821 | 53477584.5957 | 52133051.0428 | 50636078.5049 | 48985924.9774 | 47181844.8442 | 45660772.0598 | 44278189.7766 | 42523732.977 | 35746233.7642 | 0
Equity Cashflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1234793.7766 | -2260316.7983 | -2042302.684 | -2042302.684 | -2042302.684 | -2064024.2404 | -1968510.6404 | -1872997.0404 | -1853178.6646 | -1662151.4646 | -1471124.2646 | -1280097.0646 | -1184583.4646 | -1089069.8646 | -822347.4404 | -1013374.6404 | -1108888.2404 | -527419.0078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26965761.604
Cumulative Equity CF | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1234793.7766 | -3495110.5749 | -5537413.2588 | -7579715.9428 | -9622018.6268 | -11686042.8671 | -13654553.5075 | -15527550.5479 | -17380729.2125 | -19042880.6771 | -20514004.9417 | -21794102.0063 | -22978685.4709 | -24067755.3355 | -24890102.7758 | -25903477.4162 | -27012365.6566 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -27539784.6644 | -54505546.2684
Concept C3 (values)
Debt Draw | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1347074.235 | 3492263.072 | 2321925.364 | 265853.2482 | 267147.3023 | 268447.6553 | 385252.0578 | 387127.2917 | 389011.6534 | 622941.1473 | 625973.3448 | 629020.3017 | 863077.5298 | 867278.6033 | 871500.1258 | 1106737.6367 | 1112124.7381 | 1117538.0615 | 1353973.1746 | 1360563.7075 | 1367186.3201 | 3509950.2411 | 6734982.9289 | 4986761.0864 | 2083219.6706 | 2093359.8477 | 2363419.2526 | 2259425.5953 | 2792504.3737 | 2806097.0299 | 3108500.1491 | 3123630.9308 | 636257.3228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53432.6162 | 53692.7021 | 53954.0541 | 54216.6782 | 54480.5806 | 54745.7676 | 55012.2454 | 55280.0202 | 55549.0985 | 55819.4866 | 56091.1908 | 56364.2175
Debt Repay | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646384.973 | 770235.2846 | 1597825.3538 | 1545250.8495 | 1613124.4361 | 1771118.6643 | 4982004.3446 | 6484140.7661 | 1806113.4517 | 1995960.8002 | 2186732.2403 | 2378432.2701 | 2027897.4094 | 1856712.3026 | 1547795.3388 | 5815558.3168 | 7517527.2362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11635949.6195
Interest | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6556.952 | 23555.719 | 34857.8082 | 36151.8623 | 37452.2153 | 38758.8978 | 40634.1317 | 42518.4934 | 44412.0273 | 47444.2248 | 50491.1817 | 53552.9698 | 57754.0433 | 61975.5658 | 66217.6367 | 71604.7381 | 77018.0615 | 82457.7346 | 89048.2675 | 95670.8801 | 102325.7286 | 119410.5889 | 152193.4589 | 176466.7706 | 186606.9477 | 196796.4826 | 208300.5453 | 219298.4137 | 232891.0699 | 246549.8891 | 261680.6708 | 276885.1023 | 279982.117 | 279982.117 | 279982.117 | 279982.117 | 279982.117 | 279982.117 | 279982.117 | 279982.117 | 279982.117 | 279982.117 | 279982.117 | 279982.117 | 279982.117 | 279982.117 | 276835.8054 | 273086.6462 | 265309.1505 | 257787.5639 | 249935.5991 | 241314.5895 | 217064.4314 | 185502.5483 | 176711.1998 | 166995.7597 | 156351.7299 | 144774.5906 | 134903.6974 | 125866.0564 | 118332.0843 | 90024.5601 | 53432.6162 | 53692.7021 | 53954.0541 | 54216.6782 | 54480.5806 | 54745.7676 | 55012.2454 | 55280.0202 | 55549.0985 | 55819.4866 | 56091.1908 | 56364.2175
Debt Balance | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1347074.235 | 4839337.307 | 7161262.671 | 7427115.9192 | 7694263.2215 | 7962710.8767 | 8347962.9346 | 8735090.2263 | 9124101.8796 | 9747043.0269 | 10373016.3717 | 11002036.6734 | 11865114.2032 | 12732392.8066 | 13603892.9324 | 14710630.5691 | 15822755.3073 | 16940293.3688 | 18294266.5434 | 19654830.2508 | 21022016.5709 | 24531966.8121 | 31266949.741 | 36253710.8274 | 38336930.498 | 40430290.3457 | 42793709.5984 | 45053135.1937 | 47845639.5674 | 50651736.5973 | 53760236.7464 | 56883867.6772 | 57520125 | 57520125 | 57520125 | 57520125 | 57520125 | 57520125 | 57520125 | 57520125 | 57520125 | 57520125 | 57520125 | 57520125 | 57520125 | 57520125 | 56873740.027 | 56103504.7424 | 54505679.3886 | 52960428.5391 | 51347304.103 | 49576185.4387 | 44594181.0941 | 38110040.3279 | 36303926.8763 | 34307966.0761 | 32121233.8357 | 29742801.5656 | 27714904.1562 | 25858191.8536 | 24310396.5148 | 18494838.198 | 10977310.9618 | 11030743.578 | 11084436.2801 | 11138390.3342 | 11192607.0124 | 11247087.593 | 11301833.3606 | 11356845.6059 | 11412125.6262 | 11467674.7247 | 11523494.2113 | 11579585.4021 | 0
Equity Cashflow | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3022317.7795 | -3430676.677 | -3950416.417 | -3950416.417 | -3632797.687 | -3632797.687 | -3632797.687 | -3280057.727 | -2899483.857 | -2778779.857 | -2017632.117 | -1776224.117 | -1015076.377 | -773668.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11635949.6195
Cumulative Equity CF | € | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3022317.7795 | -6452994.4564 | -10403410.8734 | -14353827.2904 | -17986624.9773 | -21619422.6643 | -25252220.3512 | -28532278.0782 | -31431761.9352 | -34210541.7921 | -36228173.9091 | -38004398.0261 | -39019474.403 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -39793142.78 | -51429092.3995

## Outputs_KPIs
Outputs_KPIs (Values pre-computed in Python)
KPI | C1 | C2 | C3
Project NPV (€) | -34449181.099 | -37033241.5643 | -37100988.3944
Project IRR (annual) | -17.3% | -19.76% | -22.44%
Profit on Cost | -34.54% | -42.83% | -42.07%
Profit Margin | -52.78% | -74.91% | -72.63%
Peak Cash Need (€) | 71251127.6634 | 75499897.3504 | 90235961.18
Equity IRR (annual) | -100% | -100% | -100%
Equity Multiple | 0 | 0 | 0
Peak Equity Need (€) | 46549385.2794 | 54505546.2684 | 51429092.3995
Payback Month (Equity) | -1 | -1 | -1
Notes: | Discount rate: 11.00% (DG-0052). Debt interest/LTC/Tax are TBD placeholders in Inputs_User. Equity IRR/Payback = -1 when no positive equity distributions (undefined IRR).

## Outputs_Charts
Outputs_Charts
Charts are linked to the Selected Concept block in Calc_Cashflow_Monthly.

## Constraints_Checks
Constraints_Checks
Quality Gate Metrics
Phase_Windows OK rows | 54
Spend_Curve_Params timing blanks (start/end) | 0
Receipt_Curve_Params timing blanks (start/end) | 0
Constraint & Sanity Checks (PASS/FAIL)
Concept | Check | Status | Breach
C1 | Total GFA <= Max (HC-003) | PASS | -6
C1 | Residential share >=40% (HC-005) | PASS | 0%
C1 | Office/Tertiary share <=40% (HC-006) | PASS | 0%
C1 | Retail share <=20% (HC-007) | PASS | 0%
C1 | Sum Phase GFA = Total GFA (ProgramPhasing) | PASS | 0
C1 | Public Works share of total cost (info) | INFO | 4.211%
C2 | Total GFA <= Max (HC-003) | PASS | -6
C2 | Residential share >=40% (HC-005) | PASS | 0%
C2 | Office/Tertiary share <=40% (HC-006) | PASS | 0%
C2 | Retail share <=20% (HC-007) | PASS | 0%
C2 | Sum Phase GFA = Total GFA (ProgramPhasing) | PASS | 0
C2 | Public Works share of total cost (info) | INFO | 4.211%
C3 | Total GFA <= Max (HC-003) | PASS | -6
C3 | Residential share >=40% (HC-005) | PASS | 0%
C3 | Office/Tertiary share <=40% (HC-006) | PASS | 0%
C3 | Retail share <=20% (HC-007) | PASS | 0%
C3 | Sum Phase GFA = Total GFA (ProgramPhasing) | PASS | 0
C3 | Public Works share of total cost (info) | INFO | 4.211%

## Traceability_Index
Traceability_Index
Item | Primary Source | Notes
Discount rate (NPV) | DG-0052 in DataGapsRanges (Ranges_ModelReady) | Base=11% nominal p.a.
Inflation assumption | DG-0002 in DataGapsRanges (Ranges_ModelReady) | Base=2% p.a.; not escalated in this skeleton.
Spend timings + curve profiles | CashFlowCurves (Spend_Curve_Params) | Start/end months and Curve_Profile_ID used; Total_Cost_Base derived from CostPlan bucket totals.
Spend totals by bucket | CostPlan (CostPlan_C1-C3) | Sum(Line_Cost_Base) by Concept_ID + Cashflow_Bucket.
Phase cost split | ProgramPhasing (Phasing_Table) | Bucket totals split across phases by GFA_Delivered_in_Phase share (Land forced to P1).
Receipt timings + curve profiles | CashFlowCurves (Receipt_Curve_Params) | Start/end months and Curve_Profile_ID used; Total_Revenue_Base derived using mix + pricing assumptions.
Program mix shares | ProgramPhasing (Concept_Metrics) | C1 Civic/Other 15% reallocated 5% each to Res/Office/Retail for modeling.
Residential sale price | MasterInputs MI-0129 | €/m²
Office rent (proxy) | MasterInputs MI-0130 | €/m²/year
Retail rent (proxy) | MasterInputs MI-0131 | €/m²/year
Residential rent (proxy for hold) | MasterInputs MI-HOLD-0101 | €/m²/month
Exit yields, opex, occupancy, hold shares | Hold/Ops Pack (Assumptions_Pack) | Used to compute capitalized value proxy for held assets.
Hard constraints | HardConstraints (Constraints_Locked) | Max GFA and mix checks.