## PerformanceEMP1
| Task Allocated | Process Design
| Working Tool | Process Design Sofwates
| Date of allocation | 24/09/2019
| Duration of Task to be completed | 8 | Days max.
| Total Scheduled task (Hrs) | 64 | hours
| effort per day | 8 | hours/day
| Cost per day of employee | 800 | Per Day
| Cost per HOUR of employee | 100 | per hour
| BAC of assignment | 6400 | Per Task
| Days to deadline | 8 | Days max.
| Planned Completion date | 2019-03-10
[14 empty] | Project Performance Measures | [8 empty] | Project Forecasting and Earned Schedule
[14 empty] | Performance Indices |  | Variances
| Days | scheduled activity/day | actual Activity/day | unit | Planned % work | BW (SAC) (Hrs) | Actual % work | AW (Hrs) | BC | ACWP | BCWS | BCWP | EV | SPI | CPI | CV | CV % | SV | SV % | Resourcce Variance RV | Resource Flow Index RI | BAC | Estimate to Complete (ETC) Euro | Estimate at Completion (EAC) Euro | CV at Completion Euro | Planned Accomplishment Rate (PAR) Per hour | Time Variance (TV) Hours | TV% | Earned Schedule (ES) Hours | Time Performance Index TPI | Expected Accomplishment Rate EAR | Time Estimate at Completion TEAC (Hrs) | Time Variance at Completion TVAC (Hrs)
0.125 | 1 | 8 | 4 | hrs | 12.5% | 8 | 6.25% | 4 | 800 | 800 | 800 | 400 | 400 | 0.5 | 0.5 | -400 | -100% | -400 | -50% | 0 | 1 | 800 | 800 | 1600 | -800 | 100 | -4 | -50% | 4 | 0.5 | 50 | 16 | -8
0.25 | 2 | 8 | 5 | hrs | 25% | 16 | 14.06% | 9 | 1600 | 1600 | 1600 | 900 | 900 | 0.5625 | 0.5625 | -700 | -77.78% | -700 | -43.75% | 0 | 1 | 1600 | 1244.4444 | 2844.4444 | -1244.4444 | 100 | -7 | -43.75% | 9 | 0.5625 | 56.25 | 28.4444 | -12.4444
0.375 | 3 | 8 | 3 | hrs | 37.5% | 24 | 18.75% | 12 | 2400 | 2400 | 2400 | 1200 | 1200 | 0.5 | 0.5 | -1200 | -100% | -1200 | -50% | 0 | 1 | 2400 | 2400 | 4800 | -2400 | 100 | -12 | -50% | 12 | 0.5 | 50 | 48 | -24
0.5 | 4 | 8 | 4 | hrs | 50% | 32 | 25% | 16 | 3200 | 3200 | 3200 | 1600 | 1600 | 0.5 | 0.5 | -1600 | -100% | -1600 | -50% | 0 | 1 | 3200 | 3200 | 6400 | -3200 | 100 | -16 | -50% | 16 | 0.5 | 50 | 64 | -32
0.625 | 5 | 8 | 5 | hrs | 62.5% | 40 | 32.81% | 21 | 4000 | 4000 | 4000 | 2100 | 2100 | 0.525 | 0.525 | -1900 | -90.48% | -1900 | -47.5% | 0 | 1 | 4000 | 3619.0476 | 7619.0476 | -3619.0476 | 100 | -19 | -47.5% | 21 | 0.525 | 52.5 | 76.1905 | -36.1905
0.75 | 6 | 8 | 7 | hrs | 75% | 48 | 43.75% | 28 | 4800 | 4800 | 4800 | 2800 | 2800 | 0.58333 | 0.58333 | -2000 | -71.43% | -2000 | -41.67% | 0 | 1 | 4800 | 3428.5714 | 8228.5714 | -3428.5714 | 100 | -20 | -41.67% | 28 | 0.58333 | 58.3333 | 82.2857 | -34.2857
0.875 | 7 | 8 | 6 | hrs | 87.5% | 56 | 53.12% | 34 | 5600 | 5600 | 5600 | 3400 | 3400 | 0.60714 | 0.60714 | -2200 | -64.71% | -2200 | -39.29% | 0 | 1 | 5600 | 3623.5294 | 9223.5294 | -3623.5294 | 100 | -22 | -39.29% | 34 | 0.60714 | 60.7143 | 92.2353 | -36.2353
1 | 8 | 8 | 3 | hrs | 100% | 64 | 57.81% | 37 | 6400 | 6400 | 6400 | 3700 | 3700 | 0.57812 | 0.57812 | -2700 | -72.97% | -2700 | -42.19% | 0 | 1 | 6400 | 4670.2703 | 11070.2703 | -4670.2703 | 100 | -27 | -42.19% | 37 | 0.57812 | 57.8125 | 110.7027 | -46.7027
|  | 64 | 37 | [11 empty] | 0.54451
Overall Evaluation of employee
| Evaluation (days) | 8 | Days
| Employee Performance | 57.81%
| Status of Task | Task is Behind Schedule
| Task is Behind Schedule | 42.19%
| Estimated time of completion | 11.375 | Days
| Status according to deadline (Delay/Ahead) | -3.375 | Days
Task does not meet deadlines, it will delay
performance Evaluation of Single Day
| Days of Evaluation (nos) | 5 | th day
| effort on the day | 5 | hours
| effort per day required | 8 | hours
| Performance Evaluation | 62.5%
| Status of current day | Behind Schedule