## Activities
|  | Relevant data for the organization and categorization of activities Some data may be omitted or additional data may be added as appropriate |  |  |  | Year: 2025 | It is recommended not to edit cells with gray background. The fields in red should be completed according to the analyzed context. |  |  |  | The entire dataset is freely modifiable to fit its context.
SANTA CATERINA HOSPITAL
|  | Description | Category the main functional areas of activities | Responsible | Involved team | Involved stakeholders | Priority | Impact | Risks | Status | Update rate
Staff Management | Activity 1 | Sign initial agreements for internships, training programs, and clinical rotations | Training | HR Manager | HR team | Universities, Training institutions | High | High | Administrative delays | Completed | 2025-01-14
| Activity 2 | Create an internal committee to manage academic partnerships | Management | Operations Director | Management team | Educational institutions | Medium | Medium | Lack of engagement | In progress | 2025-01-14
| Activity 3 | Develop an internal and external communication plan highlighting the Hospital's value | Marketing | Communication Manager | Marketing team | Staff, Patients, Visitors, Media | Medium | Medium | Poor audience engagement | In progress | 2025-01-14
| Activity 4 | Schedule optimization and task redistribution | Management | Operations Director | HR team | School, Universities | High | High | Resistance to change | Completed | 2025-01-14
| Activity 5 | Enter into a collaboration agreement with local universities | Training | HR Manager | HR team | School, Universities | Medium | High | Bureaucratic delays | In progress | 2025-01-14
| Activity 6 | Continuously improve the Hospital's employer reputation through workplace surveys | Human Resources | HR Manager | HR team | Employees | Medium | Medium | Low partecipation | To be started | 2025-01-09
| Activity 7 | Implement training programs in collaboration with new staff | Training | Training Coordinator | HR team, Training team | New employees | High | High | Lack of trainers | In progress | 2025-01-14
| Activity 8 | Implement young talent retention programs with exclusive benefits | Human Resources | HR Manager | HR team, Finance team | Young professionals | Medium | Medium | Budget constraints | To be started | 2025-01-09
| Activity 9 | Partial retirement plans | Finance | CFO | Finance team | Senior employees | Low | Medium | Workforce gaps | To be started | 2025-01-09
Waste Management | Activity 10 | Train staff on new waste management technologies and regulations | Sustainability | Sustainability Manager | Facilities team | Enviromental agencies | Medium | High | Compliance issues | In progress | 2025-01-18
| Activity 11 | Conduct an assessment of current infrastructure and technologies | Technology | IT Manager | Facilities team | Consultants | Medium | Medium | Budget constraints | In progress | 2025-01-18
| Activity 12 | Implement a pilot digital waste monitoring system | Sustainability | Sustainability Manager | Facilities team | Waste management companies | High | High | Technical failures | Completed | 2025-01-22
| Activity 13 | Certify facilities according to global environmental standards | Sustainability | Sustainability Manager | Facilities team | Certification Bodies | High | Medium | Cost of certification | To be started | 2025-01-15
| Activity 14 | Develop partnerships with entities for the safe disposal of hospital waste | Sustainability | Sustainability Manager | Facilities team | Research Institutions | High | High | Regulatory changes | In progress | 2025-01-18
| Activity 15 | Implement solutions for neutralization and biodegradation of hospital waste | Sustainability | Sustainability Manager | Facilities team | Goverment, NGOs | Medium | Medium | Technology limitations | In progress | 2025-01-18
| Activity 16 | Promote public policies to improve waste management at a societal level | Sustainability | Public Realtions Officer | Sustainabilty team | Government, Local Authorities | Low | Medium | Policy resistance | To be started | 2025-01-15
| Activity 17 | Expand environmental education to schools and universities | Sustainability | Sustainability Manager | PR team | School, Universities | Medium | Medium | Engagement challenges | To be started | 2025-01-15
| Activity 18 | Optimize processes through AI and big data for waste prediction | Technology | IT Manager | Sustainabilty team | Tech providers | Medium | Medium | Data privacy issues | To be started | 2025-01-15
Emissions | Activity 19 | Basic training for staff on the efficient use of HVAC | Training | Training Coordinator | Facilities team | Employees | High | Medium | Low partecipation | Blocked | 2015-01-03
| Activity 20 | Upgrade of obsolete equipment with high-efficiency technology | Sustainability | Facilities Manager | Facilities team, Finance team | Equipment providers | Medium | Medium | Budget constraints | Blocked | 2015-01-03
| Activity 21 | Implementation of HVAC based on renewable energy (solar thermal, geothermal) | Sustainability | Facilities Manager | Facilities team, Sustainibility team | Energy providers | Low | High | Installation costs | Blocked | 2015-01-03
Note on C3: Briefly describe the activity.
Note on E3: Identify the person responsible for the activity
Note on G3: Identify the stakeholders involved in the activity and list them in the cell, separated by a comma.
Note on H3: The activity’s contribution to achieving the objectives.
Note on I3: It refers to the importance of the activity in relation to the overall objectives.
Note on J3: It refers to the main risks involved in carrying out and completing the activity.
Note on K3: The current status of the task.
Note on L3: Enter the last update date of the collected data.