## Slide 1
Project Management Methodologies Applied to a Pressurized Lunar Rover
Candidate
Agnese SERAFINI
Department of Management and Production Engineering
Politecnico di Torino
Supervisors
Prof. Marco PETROLO
Prof. Alfonso PAGANI
Assistant Prof. Giuseppe PALAIA
Assistant Prof. Karim Abu SALEM

## Slide 2
Introduction
2
Project Management Methodologies Applied to a Pressurized Lunar Rover
What is a rover?
A rover is a mobile vehicle designed for planetary exploration, enabling scientific activities and mobility on extraterrestrial surfaces.
Apollo 15 Lunar Rover
Perseverance Mars rover

## Slide 3
Introduction
2
Project Management Methodologies Applied to a Pressurized Lunar Rover
What is a rover?
A rover is a mobile vehicle designed for planetary exploration, enabling scientific activities and mobility on extraterrestrial surfaces.
What makes a pressurized rover different?
A Pressurized Lunar Rover (PLR) provides a habitable environment for astronauts, allowing them to live and work inside for extended periods, with higher autonomy and safety.
Apollo 15 Lunar Rover
Perseverance Mars rover
Pressurized Rover

## Slide 4
Introduction
3
Project Management Methodologies Applied to a Pressurized Lunar Rover
Context of this work
This thesis was carried out within the Space It Up! project, in collaboration with Thales Alenia Space, through regular meetings and continuous technical exchange.

## Slide 5
Introduction
3
Project Management Methodologies Applied to a Pressurized Lunar Rover
Context of this work
This thesis was carried out within the Space It Up! project, in collaboration with Thales Alenia Space, through regular meetings and continuous technical exchange.
Why focus on project management in space?
Space projects requiring strict coordination of cost, schedule, risk, and quality-challenges even greater than in many terrestrial industries.

## Slide 6
Introduction
3
Project Management Methodologies Applied to a Pressurized Lunar Rover
Context of this work
This thesis was carried out within the Space It Up! project, in collaboration with Thales Alenia Space, through regular meetings and continuous technical exchange.
Why focus on project management in space?
Space projects requiring strict coordination of cost, schedule, risk, and quality-challenges even greater than in many terrestrial industries.
What are the main challenges?
Two Pressurized Lunar Rover mission profiles-one semi-stationary and one transport-are analyzed. Budget constraints, long development timelines, high technological uncertainty, and strict safety requirements make planning and decision critical.

## Slide 7
Objectives
4
Project Management Methodologies Applied to a Pressurized Lunar Rover
MY MAIN OBJECTIVE IS TO STUDY THE FEASIBILITY AND THE COSTS INVOLVED IN DEVELOPING A PRESSURIZED LUNAR ROVER

## Slide 8
Objectives
4
Project Management Methodologies Applied to a Pressurized Lunar Rover
MY MAIN OBJECTIVE IS TO STUDY THE FEASIBILITY AND THE COSTS INVOLVED IN DEVELOPING A PRESSURIZED LUNAR ROVER
Differentiate Semi-Stationary and Transport missions and establish their profiles using mission statements, functions, and corresponding requirements

## Slide 9
Objectives
4
Project Management Methodologies Applied to a Pressurized Lunar Rover
MY MAIN OBJECTIVE IS TO STUDY THE FEASIBILITY AND THE COSTS INVOLVED IN DEVELOPING A PRESSURIZED LUNAR ROVER
Differentiate Semi-Stationary and Transport missions and establish their profiles using mission statements, functions, and corresponding requirements
Scheduling Study:
  Construction scheduling for both rover missions, considering duration, costs, and resources
  Development of Work Breakdown Structure (WBS), Gantt chart, and Critical Path Method (CPM)

## Slide 10
Objectives
4
Project Management Methodologies Applied to a Pressurized Lunar Rover
MY MAIN OBJECTIVE IS TO STUDY THE FEASIBILITY AND THE COSTS INVOLVED IN DEVELOPING A PRESSURIZED LUNAR ROVER
Differentiate Semi-Stationary and Transport missions and establish their profiles using mission statements, functions, and corresponding requirements
Scheduling Study:
  Construction scheduling for both rover missions, considering duration, costs, and resources
  Development of Work Breakdown Structure (WBS), Gantt chart, and Critical Path Method (CPM)
Risk and Quality Analysis:
  Implementation of risk analysis
  Implementation of quality analysis

## Slide 11
Methodological Approach
5
Frameworks & Tools:
  PMBOK: Structured approach to project management phases and knowledge areas
  Microsoft Project: Used for Work Breakdown Structure (WBS), Gantt Charts, and Critical Path Method (CPM) scheduling
Risk & Quality Management:
  Risk Breakdown Structure (RBS): Systematic risk identification and classification
  Failure Modes, Effects, and Criticality Analysis (FMECA): Proactive identification and prioritization of potential failures
Project Management Methodologies Applied to a Pressurized Lunar Rover

## Slide 12
Mission Concepts
6
Project Management Methodologies Applied to a Pressurized Lunar Rover
Semi-Stationary Rover (SSPR)
Transport Rover (TPR)

## Slide 13
Mission Concepts
6
Project Management Methodologies Applied to a Pressurized Lunar Rover
Semi-Stationary Rover (SSPR)
  Designed for localized exploration
  Minimal mobility: slow repositioning only (few cm/s)
  Mission duration: ~14 days (one lunar daytime)
  Internal volume: 30–40 m³ for 2 astronauts
  Focus on sample analysis on board
  Lower complexity, cost, and risk
Transport Rover (TPR)

## Slide 14
Mission Concepts
6
Project Management Methodologies Applied to a Pressurized Lunar Rover
Semi-Stationary Rover (SSPR)
  Designed for localized exploration
  Minimal mobility: slow repositioning only (few cm/s)
  Mission duration: ~14 days (one lunar daytime)
  Internal volume: 30–40 m³ for 2 astronauts
  Focus on sample analysis on board
  Lower complexity, cost, and risk
Transport Rover (TPR)
  Designed for long-range exploration & logistics
  High mobility: 10–15 km/h, up to 800–1200 km
  Mission duration: ~18 days, including lunar night operations
  Internal volume: 55–60 m³ for 2 astronauts
  Focus on sample collection and transport
  Higher complexity, autonomy, and cost

## Slide 15
Launch Vehicle Evaluation
Project Management Methodologies Applied to a Pressurized Lunar Rover
Semi-Stationary Mission
Approx. 4,000 to 5,000 kg
Est. occupy volume 30-40 m³
Transport Mission
Approx. 7,000 to 8,000 kg
Est. occupy volume 55-60 m³
Launcher | Payload Volume | GTO Capacity | Est. Cost per Launch
Falcon 9 | 5.2 x 13.2 m | 8,300 kg | $67 million
Proton-M | 5.2 x 17.6 m | 6,900 kg | $650 million
GSLV | 5 x 10 m | 4,000 kg | $50 million
Vulcan Centaur (ULA) | 5.4 x 19 m | 13,000 kg | $250 million
Delta IV Heavy | 5 x 13 m | 14,220 kg | $450 million
SLS Block 1 | 8.4 x 20 m | 26,000 kg | $2000 million
Notes: Backup slide

## Slide 16
Work Breakdown Structure (WBS)
7
Project Management Methodologies Applied to a Pressurized Lunar Rover
Decomposes the project into manageable work packages:
  Structured decomposition up to 3 levels
  11 main branches common to both rovers
Ensures scope definition, cost estimation, and schedule traceability
Differences of the Transport Rover:
  Power System Integration
  Mobility System
  Life Support System
  Communication & Autonomy
Semi-Stationary Rover remains simpler, with fewer autonomy and endurance requirements
Notes: Power System Integration → extended battery pack, dual DIPS validation
Mobility System → stereo vision & LIDAR calibration, high-torque motor testing
Life Support System → larger food supply for 18-day mission
Communication & Autonomy → AI-based navigation logic

## Slide 17
Gantt Chart on Microsoft Project
8
Project Management Methodologies Applied to a Pressurized Lunar Rover
The Gantt chart highlights the longest-duration tasks:
  Environmental Protection Systems (~2472 days)
  System Integration & Testing (~2290 days)
These durations do not represent continuous effort:
  They extend across the whole project timeline
  Activities are revisited periodically as the mission evolves
Uncertainties in estimation:
  Long development cycles → high schedule variability
  Possible delays from technology readiness, verification, and testing campaigns

## Slide 18
Cost Estimation on Microsoft Project
9
Project Management Methodologies Applied to a Pressurized Lunar Rover
Costs derived from three main sources:
  Work resources → engineering teams, integration teams, technicians
  Material resources → composite materials, batteries, heat pipes, tanks, radiators, etc.
  Fixed/variable costs → environmental testing, launch integration, software licenses
Allocation of resources performed combining hourly rates, quantities, and unit prices
Highest costs linked to:
  Environmental Protection Systems ~221 M€
  System Integration & Testing ~200 M€
Estimates affected by uncertainties: technology readiness, testing needs, and potential delays

## Slide 19
Costs and Duration Comparison
10
Project Management Methodologies Applied to a Pressurized Lunar Rover
Mobility system
Communication & Autonomy System
121 Mln
141 Mln
50 Mln
71 Mln
Power system integration
Mobility system
System
Integration & Testing
Semi-Stationary Rover prioritizes stability, internal scientific analysis, and minimal locomotion
Transport Rover is optimized for long-distance traversal, autonomy, and logistical flexibility
Total cost Semi-Stationary ~ 1.0 BLN € Total cost Transport ~ 1.1 BLN €

## Slide 20
Risk Analysis
11
Project Management Methodologies Applied to a Pressurized Lunar Rover
Abbreviations:
Prob. = Probability, Imp. = Impact, Sev. = Severity (Prob. × Impact)
BM = Before Mitigation, AM = After Mitigation
ID | Category | Risk | Prob. | Imp. | Sev. | Prob. | Imp. | Sev.
R-R-10 | Rover | Dust infiltration into mechanisms | 4 | 5 | 20 | 2 | 3 | 6
R-SC-1 | Supply chain | Critical component unavailability | 4 | 4 | 16 | 2 | 3 | 6
R-R-1 | Rover | Mobility system mulfunction | 3 | 5 | 15 | 2 | 3 | 6
BM
AM
The severity values are significantly educed after applying mitigation measures:
  Disable affected components and rely on redundant or manual alternatives
  Use pre-qualified substitutes or adjust integration schedule
  Use alternate route planning or limited-range fallback mode
Among all identified risks, these three represent the highest severity values:

## Slide 21
Quality Analysis
12
Sensors
Motors
Navigation
software
Shelters
EVA seals
Project Management Methodologies Applied to a Pressurized Lunar Rover
Sensors
Motors
Navigation
software
Shelters
EVA seals
  Sensors → covers and self-cleaning system
  Motors → thermal shielding and dust-proof housings
  Navigation software → runtime recovery protocols
  Shelters → periodic testing and water used as passive protection
  EVA seals → dust-resistant materials and alarm for rapid isolation
RPN = Severity × Occurrence × Detection
  Severity (S): seriousness of the failure’s effect
  Occurrence (O): likelihood of the failure happening
  Detection (D): likelihood that the failure is not detected before causing problems

## Slide 22
Conclusions
13
Project Management Methodologies Applied to a Pressurized Lunar Rover
Rover Semi-Stationary (~ 1.0 BLN €)→ simpler, cost-effective, lower risks
Rover Transport (~ 1.1 BLN €) → higher range & autonomy, but greater cost and complexity
Semi-Stationary vs Transport

## Slide 23
Conclusions
13
Project Management Methodologies Applied to a Pressurized Lunar Rover
Rover Semi-Stationary (~ 1.0 BLN €)→ simpler, cost-effective, lower risks
Rover Transport (~ 1.1 BLN €) → higher range & autonomy, but greater cost and complexity
Risk Mitigation: High-severity risks up to 20 reduced to medium/low levels, ~50% improvement
Quality (FMECA) improved by 50–65%; some components reduced to negligible risk
Semi-Stationary vs Transport
Risk and Quality results

## Slide 24
Conclusions
13
Project Management Methodologies Applied to a Pressurized Lunar Rover
Rover Semi-Stationary (~ 1.0 BLN €)→ simpler, cost-effective, lower risks
Rover Transport (~ 1.1 BLN €) → higher range & autonomy, but greater cost and complexity
Risk Mitigation: High-severity risks up to 20 reduced to medium/low levels, ~50% improvement
Quality (FMECA) improved by 50–65%; some components reduced to negligible risk
Semi-Stationary vs Transport
Risk and Quality results
Mobility (reduction of ~55%), power (improvement of over 80–90%), life support (risks to the low zone)
Economic view: ambitious missions must justify their costs with clear returns
Critical subsystems and cost

## Slide 25
Conclusions
13
Project Management Methodologies Applied to a Pressurized Lunar Rover
Rover Semi-Stationary (~ 1.0 BLN €)→ simpler, cost-effective, lower risks
Rover Transport (~ 1.1 BLN €) → higher range & autonomy, but greater cost and complexity
Risk Mitigation: High-severity risks up to 20 reduced to medium/low levels, ~50% improvement
Quality (FMECA) improved by 50–65%; some components reduced to negligible risk
PM a decision-making enabler
WBS, CPM, RBS, FMECA: essential from the earliest planning stages
Lunar exploration  engineering innovation and managerial discipline
Semi-Stationary vs Transport
Risk and Quality results
Strategic Role of PM
Mobility (reduction of ~55%; ), power (improvement of over 80–90% ), life support (risks to the low zone)
Economic view: ambitious missions must justify their costs with clear returns
Critical subsystems and cost

## Slide 26
Future Developments
14
Project Management Methodologies Applied to a Pressurized Lunar Rover
Short-term
(1–3 years)
Refine cost models, prototype key subsystems (mobility, power, ECLSS), test in analog environments

## Slide 27
Future Developments
14
Project Management Methodologies Applied to a Pressurized Lunar Rover
Medium-term
(3–7 years)
  Establish standardized PM practices, adopt agile methods, integrate AI and digital twins
Short-term
(1–3 years)
Refine cost models, prototype key subsystems (mobility, power, ECLSS), test in analog environments

## Slide 28
Future Developments
14
Project Management Methodologies Applied to a Pressurized Lunar Rover
Long-term (>7 years)
  Pressurized rovers as operational assets for sustained lunar presence, stepping stone for Mars exploration
Medium-term
(3–7 years)
  Establish standardized PM practices, adopt agile methods, integrate AI and digital twins
Short-term
(1–3 years)
Refine cost models, prototype key subsystems (mobility, power, ECLSS), test in analog environments

## Slide 29
Candidate
Agnese SERAFINI
Department of Management and Production Engineering
Politecnico di Torino
Supervisors
Prof. Marco PETROLO
Prof. Alfonso PAGANI
Assistant Prof. Giuseppe PALAIA
Assistant Prof. Karim Abu SALEM
Thank you for your attention!